## Consolidated_Report__crosstab
Project ID | Project | Project Project owner | Project Project stage | Project Project Status | RAG Status | Project Booked Date | Project Delivery Start Date | Project Delivery End Date | TO Expiry Date | Date Status Last Updated | Project % Complete | Project Margin Variance (%) | Delivery Days Variance (%) | Project Reason for Overrun | Project Theater | Project Operating Area | Project Delivery Country | Project Primary Practice | Project Secondary Practice | Project Tertiary Practice | Project Customer | Project End User | Project Revenue Source | Project Invoice Method | Project Type | Project Secondary Service Product | Project Categorization | Project Revenue ($) | Amount Invoiced to Date | Remaining Revenue | Project Cost Budget ($) | Project Total Cost Actual ($) | Project Cost Budget Remaining | Forecast Remaining Cost ($) | Forecast Total Cost ($) | Forecast Budget Variance | Project Margin Budget ($) | Project Margin Forecast ($) | Project Margin Budget (%) | Project Margin Forecast (%) | Forecast Resources Cost | Project Margin Variance (%) | Resources Cost Budget | Resource Cost Actual | Resource Cost Budget Remaining | Forecast Resources Remaining Cost | Forecast Resources Cost | Forecast Resources Variance($) | Expenses Cost Budget | Expense Cost Actual | Expense Budget Remaining | Expenses Variance($) | Purchases Cost Budget | Purchases Cost Actual | Purchase Budget Remaining | Purchases Variance($) | Delivery Days Budget (LOE Baseline) | Delivery Days Forecast (Planned) | Total Delivery Days Actual | Delivery Days Remaining | Delivery Days Variance | PM Days Budget (Baseline) | PM Days Forecast (Planned) | PM Days | PM Days Remaining | PM Budget (%) | PM Forecast (%) | PreSales Days | Travel Days | Consultant Delivery Days | PM Days | Delivery (Other) Days | 3rd Party Days | Product Issues Days | Data | Total Days (All) | # of Baselines | Level 1 | Level 2 | Level 3
13300 | 13300 - Fidelity Information Services, 30 day T&M - Security Consultant | Kouzionis, Nicholas | Awarded | On Hold | Green | 2013-04-08 | 2013-04-15 | 2017-08-31 | 2015-08-21 | 2017-06-27 | 116% | 59% | -16% | Scoping Issues | AMER | GLOBAL FINANCIAL SERVICES | United States of America | Security |  |  | SYNERCOMM, INC.-Customer | FIDELITY INFORMATION SERVICES-EndUser | PO | Monthly in Arrears | Consulting – T & M |  | A | 63113 | 12623 | 50490 | 24000 | 25812 | -1812 | 0 | 25812 | -1812 | 39113 | 37301 | 0% | 59% | 25812 | 59% | 24000 | 25812 | -1812 | 0 | 25812 | -1812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 34.8 | 0 | -4.8125 | 0 | 7.5 | 13.1 | 0 | 0% | 61% | 0 | 0 | 6.8 | 13.1 | 0 | 0 | 14.9 |  | 34.8 | 1 | 13300 - Fidelity Information Services, 30 day T&M - Security Consultant
15006 | 15006 - Vodafone CGNAT Logging Support | Jacobs, Christo | Awarded | In Progress | Green | 2013-03-14 | 2013-09-16 | 2017-09-15 |  | 2017-06-22 | 72% | 26% | 0% | Under/Not Over budget | APAC | India | Remote | Core & Edge |  |  | IBM-Customer | Vodafone South Limited-EndUser | PO | Custom | Consulting – Fixed Price Custom |  | C | 192001 | 192001 | 0 | 160000 | 102307 | 57693 | 11826 | 114132 | 45868 | 32001 | 77869 | 15% | 41% | 67830 | 26% | 160000 | 56005 | 103995 | 11826 | 67830 | 92170 | 0 | 0 | 0 | 0 | 0 | 46302 | 0 | -46302 | 100 | 100 | 71.5 | 28.5 | 0 | 100 | 100 | 34.4 | 65.6 | 0% | 0% | 0.5 | 5.6 | 35.8 | 34.4 | 0 | 0 | 1.4 |  | 77.6 | 1 | 15006 - Vodafone CGNAT Logging Support
16138 | 16138 Riyad Bank Junos Space Implementation FFP 4 MS | Al Aswad, Waseem | Awarded | On Hold | Red | 2013-11-15 | 2014-11-09 | 2017-12-31 |  | 2016-07-28 | 31% | 36% | 0% | Under/Not Over budget | EMEA | MEA | Saudi Arabia | Network Automation |  |  | WESTCON ME-CUSTOMER | Riyad Bank-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 103796 | 71298 | 32498 | 66430 | 11850 | 54580 | 33875 | 45725 | 20705 | 37366 | 58071 | 20% | 56% | 35423 | 36% | 56127 | 11850 | 44277 | 23573 | 35423 | 20705 | 10303 | 0 | 10303 | 0 | 0 | 0 | 0 | 0 | 54 | 54 | 16.9 | 37.1 | 0 | 0 | 0 | 10.4 | 0 | 0% | 24% | 1.5 | 1.3 | 6.5 | 10.4 | 0 | 0 | 0 |  | 19.7 | 1 | 16138 Riyad Bank Junos Space Implementation FFP 4 MS
16154 | 16154 - CME Group, DC Best Practice & Assessment | Kouzionis, Nicholas | Awarded | On Hold | Green | 2013-06-07 | 2013-07-01 | 2017-06-30 | 2016-10-28 | 2017-05-03 |  | 9% | 32% |  | AMER | US TERRITORIES | United States of America | Cloud |  |  | DIMENSION DATA HOLDINGS LTD-Customer | CME GROUP-EndUser | PO | Monthly in Arrears | Consulting – T & M |  | B | 287777 | 138336 | 149441 | 120560 | 74800 | 45760 | 19795 | 94595 | 25965 | 167217 | 193182 | 58% | 67% | 54595 | 9% | 80560 | 54595 | 25965 | 0 | 54595 | 25965 | 40000 | 20205 | 19795 | 0 | 0 | 0 | 0 | 0 | 106 | 0 | 72.3 | 0 | 33.6562 | 0 | 0 | 19.5 | 0 | 0% | 37% | 3.1 | 12.2 | 50.6 | 19.5 | 0 | 0 | 2.3 |  | 87.6 | 1 | 16154 - CME Group, DC Best Practice & Assessment
16358 | 16358 Mobily Mega Projects T&M Consulting 60 days | Al Aswad, Waseem | Awarded | In Progress | Green | 2013-06-28 | 2013-06-16 | 2017-12-31 |  | 2016-06-29 | 184% | 4% | -84% | Under/Not Over budget | EMEA | MEA | Saudi Arabia | Core & Edge | Core & Edge |  | BUSINESS MANAGEMENT COMPANY-Customer | MOBILY-EndUser | PO | Invoice on Signed Timesheets | Consulting – T & M |  | A | 158200 | 110732 | 47468 | 65500 | 65513 | -13 | 8182 | 73696 | -8196 | 92700 | 84504 | 50% | 53% | 63696 | 4% | 55500 | 63696 | -8196 | 0 | 63696 | -8196 | 10000 | 1818 | 8182 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 110.4 | 0 | -50.375 | 0 | 0 | 52.2 | 0 | 0% | 90% | 0.6 | 2.5 | 58.2 | 52.2 | 0 | 0 | 0 |  | 113.5 | 1 | 16358 Mobily Mega Projects T&M Consulting 60 days
16588 | 16588 City of Philadelphia - MPLS Upgrade - PO | Jeffries, Stephanie | Awarded | In Progress | Green | 2014-08-26 | 2014-09-08 | 2017-09-29 | 2017-09-02 | 2017-07-23 | 13% | -2% | -16% | Under/Not Over budget | AMER | US TERRITORIES | United States of America | Security | Cloud |  | TIG-Customer | CITY OF PHILADELPHIA-EndUser | PO | Monthly in Arrears | Consulting – T & M |  | B | 436475 | 40339 | 396136 | 65405 | 26212 | 39193 | 162189 | 188401 | -122996 | 371070 | 248074 | 59% | 57% | 181516 | -2% | 58520 | 25921 | 32599 | 155595 | 181516 | -122996 | 6885 | 291 | 6594 | 0 | 0 | 0 | 0 | 0 | 189 | 218.6 | 27.9 | 190.8 | -29.62 | 0 | 26.6 | 16.8 | 0 | 0% | 14% | 13.1 | 0 | 10.3 | 16.8 | 0 | 0 | 0 |  | 40.1 | 1 | 16588 City of Philadelphia - MPLS Upgrade - PO
17340 | 17340 7Ticks - MX/40G Block of Hours | Wiesner, Jill | Awarded | On Hold | Green | 2013-12-30 | 2014-03-01 | 2017-09-01 | 2016-03-30 | 2017-06-23 | 56% | 16% | 0% | Under/Not Over budget | AMER | GLOBAL FINANCIAL SERVICES | United States of America | Core & Edge |  |  | MARON STRUCTURES TECHNOLOGIES-Customer | 7 TICKS-EndUser | PO | Monthly in Arrears | Consulting – T & M |  | B | 108840 | 44811 | 64029 | 64849 | 21001 | 43848 | 18235 | 39236 | 25613 | 43991 | 69604 | 48% | 64% | 23236 | 16% | 48849 | 19042 | 29807 | 4194 | 23236 | 25613 | 16000 | 1959 | 14041 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 22.3 | 17.7 | 0 | 0 | 0 | 4.9 | 0 | 0% | 14% | 11.5 | 1.4 | 17.4 | 4.9 | 0 | 0 | 0 |  | 35.2 | 1 | 17340 7Ticks - MX/40G Block of Hours
17736 | 17736 - FIS, T&M - Security Consultant Extension | Kouzionis, Nicholas | Awarded | In Progress | Green | 2013-12-26 | 2014-01-06 | 2017-08-31 | 2016-03-31 | 2017-06-16 | 72% | 67% | 0% | Scoping Issues | AMER | US TERRITORIES | United States of America | Security |  |  | SYNERCOMM, INC.-Customer | FIDELITY INFORMATION SERVICES-EndUser | PO |  | Consulting – T & M |  | A | 59142 | 8843 | 50299 | 22600 | 12850 | 9750 | 6902 | 19752 | 2848 | 36542 | 39389 | 0% | 67% | 14752 | 67% | 17600 | 11742 | 5858 | 3011 | 14752 | 2848 | 5000 | 1108 | 3892 | 0 | 0 | 0 | 0 | 0 | 22 | 22 | 15.8 | 6.3 | 0 | 22 | 22 | 6.4 | 15.6 | 0% | 0% | 0.5 | 1.8 | 9.4 | 6.4 | 0 | 0 | 0 |  | 18 | 1 | 17736 - FIS, T&M - Security Consultant Extension
17916 | 17916 CNT Ecuador Data Center | Almanza, Henry | Awarded | On Hold | Green | 2014-10-22 | 2014-11-17 | 2017-10-27 | 2015-03-01 | 2017-07-20 | 503% | -155% | -403% | Product Issues | AMER | CALA | Ecuador | Core & Edge | Network Automation |  | COMGSP Ingenieria S.A. | CNT Ecuador-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 191000 | 118620 | 72380 | 133700 | 421119 | -287419 | 8987 | 430106 | -296406 | 57300 | -239106 | 30% | -125% | 321206 | -155% | 98700 | 321206 | -222506 | 0 | 321206 | -222506 | 35000 | 26013 | 8987 | 0 | 0 | 73900 | 0 | -73900 | 90.1 | 90.1 | 453.4 | 0 | -363.3188 | 0 | 0 | 53.6 | 0 | 0% | 13% | 11 | 30.9 | 320.9 | 53.6 | 0 | 0 | 78.9 |  | 495.3 | 1 | 17916 CNT Ecuador Data Center
17988 | 17988 VF Southern HUB Junos Space phase2 a&b FFP 3MS | Moreno, Carlos | Awarded | In Progress | Amber | 2016-02-25 | 2016-03-02 | 2017-12-29 |  | 2017-07-12 | 130% | 14% | -30% | SOW Issues | EMEA | UK-I | Italy | Network Automation |  |  | VODAFONE GROUP PLC-Customer | VODAFONE-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 124800 | 85875 | 38925 | 92374 | 34673 | 57701 | 42045 | 76718 | 15656 | 32426 | 48082 | 25% | 39% | 33663 | 14% | 49319 | 33663 | 15656 | 0 | 33663 | 15656 | 18920 | 1010 | 17910 | 0 | 24135 | 0 | 24135 | 0 | 48 | 48 | 62.6 | 0 | -14.5625 | 0 | 0 | 21.2 | 0 | 0% | 51% | 11.3 | 1.4 | 34 | 21.2 | 0 | 7.4 | 0 |  | 75.2 | 1 | 17988 VF Southern HUB Junos Space phase2 a&b FFP 3MS
18081 | 18081 Istekki Campus Assessment Project FFP 1 MS | Subramaniam, Ragunath | Awarded | Booked | Green | 2017-06-30 | [5 empty] | 56% | 0% |  | EMEA | ENA-R-NORTH | Finland | Cloud |  |  | Cygate-Customer | ISTEKKI OY - EU | PO | Milestone Payments | Consulting – Fixed Price Custom |  |  | 29939 | 0 | 29939 | 18282 | 0 | 18282 | 4200 | 4200 | 14082 | 11657 | 25739 | 30% | 86% | 0 | 56% | 14082 | 0 | 14082 | 0 | 0 | 14082 | 4200 | 0 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.3 |  | 18081 Istekki Campus Assessment Project FFP 1 MS
18227 | 18227 Sempra DC Core Consulting Support - T&M - PO | Wiesner, Jill | Awarded | On Hold | Green | 2015-05-14 | 2015-05-04 | 2017-08-31 | 2017-08-31 | 2017-06-16 | 115% | -1% | -15% | Under/Not Over budget | AMER | US TERRITORIES | United States of America | Cloud |  |  | INTEGRATED ARCHIVE SYSTEMS-Customer | SEMPRA ENERGY-EndUser | PO | Monthly in Arrears | Consulting – T & M |  | A | 97568 | 90854 | 6713 | 47190 | 48555 | -1365 | 0 | 48555 | -1365 | 50378 | 49013 | 52% | 50% | 37815 | -1% | 39600 | 37815 | 1785 | 0 | 37815 | 1785 | 7590 | 10740 | 0 | -3150 | 0 | 0 | 0 | 0 | 36 | 36 | 41.4 | 0 | -5.375 | 16 | 16 | 7.7 | 8.3 | 80% | 63% | 0 | 10.1 | 32.7 | 7.7 | 1 | 0 | 0 |  | 51.4 | 1 | 18227 Sempra DC Core Consulting Support - T&M - PO
18254 | 18254 Mobily T&M CONSULTING 40 Days | Al Aswad, Waseem | Awarded | On Hold | Green | 2014-03-31 | 2014-04-01 | 2017-12-31 |  |  | 111% | 31% | -11% |  | EMEA | MEA | Saudi Arabia | Core & Edge |  |  | BUSINESS MANAGEMENT COMPANY-Customer | MOBILY-EndUser | PO | Invoice on Signed Timesheets | Consulting – T & M |  | A | 109800 | 16470 | 93330 | 60000 | 36573 | 23427 | 2388 | 38961 | 21039 | 49800 | 70839 | 34% | 65% | 27961 | 31% | 49000 | 27961 | 21039 | 0 | 27961 | 21039 | 11000 | 8612 | 2388 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 44.5 | 0 | -4.5 | 0 | 0 | 18.6 | 0 | 0% | 72% | 0.8 | 16.1 | 18.8 | 18.6 | 7.2 | 0 | 0 |  | 61.4 | 1 | 18254 Mobily T&M CONSULTING 40 Days
18534 | 18534 MTS IP Pilot Migration FFP 1 MS | Tyan, Kirill | Awarded | In Progress | Green | 2015-03-31 | 2017-04-19 | 2017-09-28 |  | 2017-05-28 | 246% | -18% | -147% | Customer Issues | EMEA | ENA-R-RCIS | Russia | Core & Edge | Core & Edge |  | Marvel Computer Solutions - CUSTOMER | MTS-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 22456 | 22456 | 0 | 14658 | 21763 | -7105 | 0 | 21763 | -7105 | 7798 | 693 | 21% | 3% | 21763 | -18% | 14658 | 21763 | -7105 | 0 | 21763 | -7105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.5 | 21.6 | 53.2 | 0 | -31.6875 | 13.1 | 13.2 | 2.8 | 10.3 | 157% | 33% | 0.4 | 0 | 46.4 | 2.8 | 0 | 0 | 4 |  | 53.6 | 1 | 18534 MTS IP Pilot Migration FFP 1 MS
19344 | 19344 Finanz Informatik (PID 13707 36MTHS Ext) T&M 50 DAYS | Subramaniam, Ragunath | Awarded | In Progress | Green | 2015-08-20 | 2015-10-09 | 2017-07-28 |  | 2017-06-19 | 92% | 21% | 0% |  | EMEA | Germany | Germany | Security |  |  | WESTCON GROUP EUROPEAN OPERATIONS | FINANZ INFORMATATIK-EndUser | PO | Invoice on Signed Timesheets | Consulting – T & M |  | A | 129425 | 95774 | 33651 | 51950 | 26711 | 25239 | 8389 | 35100 | 16850 | 77475 | 94325 | 52% | 73% | 22550 | 21% | 39400 | 22550 | 16850 | 0 | 22550 | 16850 | 12550 | 4161 | 8389 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 45.8 | 4.2 | 0 | 0 | 0 | 10.7 | 0 | 0% | 27% | 9.9 | 4.9 | 35.1 | 10.7 | 0 | 0 | 0 |  | 60.6 | 1 | 19344 Finanz Informatik (PID 13707 36MTHS Ext) T&M 50 DAYS
19352 | 19352 - Bloomberg 2014 Projects - Part 2 | Gregory, Mina | Awarded | In Progress | Green | 2014-11-10 | 2014-09-15 | 2017-08-31 | 2015-06-30 | 2017-06-29 | 116% | 13% | -16% |  | AMER | GLOBAL FINANCIAL SERVICES | United States of America | Cloud |  |  | BLOOMBERG L.P.-Customer | BLOOMBERG-EndUser | PO | Monthly in Arrears | Consulting – T & M |  | B | 339000 | 0 | 339000 | 149000 | 140535 | 8465 | 2953 | 143488 | 5512 | 190000 | 195512 | 45% | 58% | 138488 | 13% | 144000 | 138488 | 5512 | 0 | 138488 | 5512 | 5000 | 2047 | 2953 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 139.5 | 0 | -19.4763 | 0 | 0 | 22.6 | 0 | 0% | 19% | 31.6 | 12.1 | 116.9 | 22.6 | 0 | 0 | 0 |  | 183.2 | 1 | 19352 - Bloomberg 2014 Projects - Part 2
19525 | 19525 Commerzbank DC/Switching for 5 LOTs FFP 34MS | Chouaieb, Mejda | Awarded | In Progress | Green | 2015-06-30 | 2015-05-20 | 2017-07-31 |  | 2017-06-30 | 92% | 40% | -17% | Product Issues | EMEA | Germany | Germany | Cloud | Security |  | WESTCON GROUP EUROPEAN OPERATIONS | Commerzbank (DE)-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 711624 | 535370 | 176254 | 467213 | 214000 | 253214 | 65866 | 279865 | 187348 | 244411 | 431759 | 21% | 61% | 195835 | 40% | 383183 | 195835 | 187348 | 0 | 195835 | 187348 | 84030 | 18164 | 65866 | 0 | 0 | 0 | 0 | 0 | 315 | 370 | 341.6 | 28.4 | -55 | 0 | 0 | 88.6 | 0 | 0% | 31% | 11.3 | 31.6 | 204.9 | 88.6 | 0 | 4.8 | 43.3 |  | 384.5 | 1 | 19525 Commerzbank DC/Switching for 5 LOTs FFP 34MS
19900 | 19900 TALK TALK Northstar FFP 4 MS | Foster, David | Awarded | In Progress | Green | 2015-12-26 | 2016-06-27 | 2017-08-25 |  | 2017-07-14 | 8% | 9% | -80% | Under/Not Over budget | EMEA | UK-I | United Kingdom | Core & Edge |  |  | AXIANS | TALK TALK-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 104175 | 0 | 104175 | 58544 | 3596 | 54948 | 57623 | 61219 | -2675 | 45631 | 42956 | 32% | 41% | 50439 | 9% | 47764 | 3596 | 44168 | 46843 | 50439 | -2675 | 10780 | 0 | 10780 | 0 | 0 | 0 | 0 | 0 | 43.5 | 78.4 | 6 | 72.4 | -34.8475 | 6.8 | 9.5 | 3 | 3.8 | 18% | 14% | 5.3 | 0 | 3 | 3 | 0 | 0 | 0 |  | 11.3 | 1 | 19900 TALK TALK Northstar FFP 4 MS
20056 | 20056 Mobily MPC5 Lab Testing FFP 1 MS | Al Aswad, Waseem | Opportunity | Complete - Working at Risk | Green |  | 2014-12-10 | 2015-02-01 |  |  |  | 75% | 100% |  | EMEA | MEA | Saudi Arabia | Core & Edge |  |  | BUSINESS MANAGEMENT COMPANY-Customer | MOBILY-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 12891 | 0 | 12891 | 2715 | 0 | 2715 | 0 | 0 | 2715 | 10176 | 12891 | 25% | 100% | 0 | 75% | 2715 | 0 | 2715 | 0 | 0 | 2715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0% | 0% | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.3 | 1 | 20056 Mobily MPC5 Lab Testing FFP 1 MS
20180 | 20180 FFP Verizon Edgecast PO CON | Stroud, Charlie | Awarded | On Hold | Green |  | 2015-07-01 | 2016-12-30 |  |  | 9% | -54% | 0% |  | AMER | VERIZON |  | Core & Edge |  |  | VERIZON COMMUNICATIONS-EndUser | VERIZON COMMUNICATIONS-EndUser | PO | Quarterly in Advance | Consulting – Fixed Price Custom |  | B | 60000 | 0 | 60000 | 26400 | 6480 | 19920 | 55746 | 62226 | -35826 | 33600 | -2226 | 50% | -4% | 62226 | -54% | 26400 | 6480 | 19920 | 55746 | 62226 | -35826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95 | 95 | 8.6 | 86.4 | 0 | 0 | 0 | 8.3 | 0 | 0% | 10% | 12.8 | 0 | 0.4 | 8.3 | 0 | 0 | 0 |  | 21.4 | 1 | 20180 FFP Verizon Edgecast PO CON
20275 | 20275 Orange Spain Sleeping Beauty (MPLS PE) FFP xMS | Oliver, Juan | Awarded | In Progress | Amber | 2015-08-28 | 2015-07-01 | 2017-08-31 |  |  | 71% | 32% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | D | 723023 | 631110 | 91913 | 1184342 | 906838 | 277504 | 48612 | 955450 | 228892 | -461319 | -232427 | -64% | -32% | 235890 | 32% | 533524 | 187279 | 346245 | 48612 | 235890 | 297634 | 0 | 1049 | 0 | -1049 | 650818 | 718510 | 0 | -67692 | 550 | 550 | 390.8 | 159.2 | 0 | 0 | 0 | 59.2 | 0 | 0% | 12% | 52.3 | 0.8 | 276.5 | 59.2 | 0 | 9.3 | 45.9 |  | 443.9 | 1 | 20275 Orange Spain Sleeping Beauty (MPLS PE) FFP xMS
20426 | 20426 KAUST SRX Upgrade FFP 2 MS | Al Aswad, Waseem | Awarded | On Hold | Green | 2015-03-11 | 2016-06-15 | 2017-12-31 |  | 2017-04-26 | 57% | 36% | 0% | Under/Not Over budget | EMEA | MEA | Saudi Arabia | Security |  |  | AL FALAK ELECTRONIC EQUIPMENT & SUPPLIES COMPANY LTD.-Customer | KAUST | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 38975 | 0 | 38975 | 20267 | 4511 | 15755 | 6635 | 11146 | 9120 | 18709 | 27829 | 35% | 71% | 7209 | 36% | 16329 | 4511 | 11818 | 2698 | 7209 | 9120 | 3938 | 0 | 3938 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 6.9 | 5.1 | 0 | 0 | 0 | 5.3 | 0 | 0% | 78% | 1.3 | 0 | 0 | 5.3 | 0 | 0 | 1.6 |  | 8.1 | 1 | 20426 KAUST SRX Upgrade FFP 2 MS
20559 | 20559 Hutchison - SBR Upgrade - FFP | Pathak, Nishant | Awarded | Booked | Green | 2017-02-05 | 2017-04-10 | 2017-10-20 |  | 2017-07-07 | 85% | -30% | -200% | Internal Issues | APAC | Greater China | Hong Kong | Core & Edge |  |  | COMMVERGE SOLUTIONS LIMITED-Customer | HUTCHISON-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | A | 25000 | 0 | 25000 | 14350 | 15749 | -1399 | 6091 | 21840 | -7490 | 10650 | 3160 | 43% | 13% | 18290 | -30% | 10800 | 15749 | -4949 | 2541 | 18290 | -7490 | 3550 | 0 | 3550 | 0 | 0 | 0 | 0 | 0 | 12 | 36 | 30.6 | 5.4 | -24 | 12 | 36 | 12.6 | 0 | 0% | 0% | 0 | 0.5 | 18 | 12.6 | 0 | 0 | 0 |  | 31.1 | 2 | 20559 Hutchison - SBR Upgrade - FFP
20695 | 20695 Etisalat Core Expansion Design FFP 4 MS | Bhinder, Muhammad Amir Rashid | Awarded | On Hold | Green | 2015-03-26 | 2015-04-01 | 2017-07-31 |  | 2017-06-28 | 83% | 46% | 0% | Under/Not Over budget | EMEA | MEA | UAE | Core & Edge |  |  | ALPHA DATA PROCESSING LLC-Customer | ETISALAT-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 97782 | 62835 | 34947 | 59450 | 26620 | 32830 | 3049 | 29670 | 29780 | 38332 | 68112 | 24% | 70% | 29670 | 46% | 59450 | 26620 | 32830 | 3049 | 29670 | 29780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 54 | 44.9 | 9.1 | 0 | 5.4 | 5.4 | 13.3 | 0 | 11% | 33% | 1.1 | 2.8 | 31.6 | 13.3 | 0 | 0 | 0 |  | 48.8 | 1 | 20695 Etisalat Core Expansion Design FFP 4 MS
20748 | 20748 Commerzbank PS NET2 Consultancy T&M 52 + 5 days | Chouaieb, Mejda | Awarded | In Progress | Green | 2016-08-02 | 2016-03-31 | 2018-03-31 | 2018-03-31 | 2017-05-03 | 66% | 34% | 0% | Under/Not Over budget | EMEA | DACH | Germany | Cloud |  |  | WESTCON GROUP EUROPEAN OPERATIONS | Commerzbank (DE)-EndUser | PO | Invoice on Signed Timesheets | Consulting – T & M |  | A | 135173 | 85940 | 49233 | 92910 | 24938 | 67972 | 23593 | 48531 | 44379 | 42263 | 86642 | 30% | 64% | 34531 | 34% | 78910 | 24599 | 54311 | 9932 | 34531 | 44379 | 14000 | 339 | 13661 | 0 | 0 | 0 | 0 | 0 | 57 | 57 | 37.8 | 19.3 | 0 | 19 | 19 | 5.8 | 13.3 | 50% | 50% | 1 | 3 | 26.8 | 5.8 | 0 | 1.8 | 3.5 |  | 41.8 | 1 | 19525 Commerzbank DC/Switching for 5 LOTs FFP 34MS | 20748 Commerzbank PS NET2 Consultancy T&M 52 + 5 days
20766 | 20766 Columbus Junos Space | Almanza, Henry | Awarded | In Progress | Green | 2015-12-28 | 2017-09-04 | 2017-12-22 | 2017-11-24 | 2017-07-20 | 54% | 42% | -110% | Under/Not Over budget | AMER | CALA | United States of America | Network Automation |  |  | Vology Data Systems | COLUMBUS NETWORKS-EndUser | Reclass | Upon Completion | Consulting – Fixed Price Custom |  | B | 77579 | 0 | 77579 | 46548 | 8706 | 37842 | 5530 | 14236 | 32312 | 31031 | 63343 | 40% | 82% | 8706 | 42% | 41018 | 8706 | 32312 | 0 | 8706 | 32312 | 5530 | 0 | 5530 | 0 | 0 | 0 | 0 | 0 | 13 | 27.3 | 14.8 | 12.5 | -14.3 | 0 | 24.3 | 9.1 | 0 | 0% | 799% | 19.8 | 0 | 5.8 | 9.1 | 0 | 0 | 0 |  | 34.6 | 1 | 20766 Columbus Junos Space
20770 | 20770 Etisalat Core Expansion Deployment FFP 2 MS | Bhinder, Muhammad Amir Rashid | Awarded | On Hold | Green | 2015-07-28 | 2015-08-23 | 2017-07-31 |  | 2017-06-28 | 56% | 36% | 0% | Under/Not Over budget | EMEA | MEA | UAE | Core & Edge |  |  | WESTCON ME-CUSTOMER | ETISALAT-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 57767 | 0 | 57767 | 35122 | 12906 | 22216 | 9991 | 22897 | 12225 | 22645 | 34870 | 24% | 60% | 22897 | 36% | 35122 | 12906 | 22216 | 9991 | 22897 | 12225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 20.1 | 15.9 | 0 | 0 | 7.5 | 4.5 | 0 | 0% | 26% | 0 | 0.3 | 15.6 | 4.5 | 0 | 0 | 0 |  | 20.4 | 2 | 20770 Etisalat Core Expansion Deployment FFP 2 MS
20803 | 20803 - First Data Corporation, DC Replication Project | Kouzionis, Nicholas | Awarded | Complete | Green | 2015-05-18 | 2015-06-08 | 2017-07-14 | 2017-06-25 | 2017-07-19 | 158% | -6% | -58% | Customer Issues | AMER | GLOBAL FINANCIAL SERVICES | United States of America | Core & Edge |  |  | IBM CORP-EndUser | First Data Corporation- End User | PO | Monthly in Arrears | Consulting – T & M |  | A | 90000 | 82393 | 7607 | 35400 | 44347 | -8947 | 5777 | 50124 | -14724 | 54600 | 39876 | 50% | 44% | 37124 | -6% | 22400 | 37124 | -14724 | 0 | 37124 | -14724 | 13000 | 7223 | 5777 | 0 | 0 | 0 | 0 | 0 | 28 | 28 | 44.1 | 0 | -16.125 | 28 | 28 | 20.4 | 7.6 | 0% | 174% | 13.7 | 5.3 | 23.8 | 20.4 | 0 | 0 | 0 |  | 63.1 | 1 | 20803 - First Data Corporation, DC Replication Project
20847 | 20847 ROSTELECOM WANDL PS Consultancy T&M 17 days | Tyan, Kirill | Awarded | On Hold | Green | 2015-03-31 | 2017-06-15 | 2017-12-14 |  | 2017-06-28 | 1% | 26% | 0% |  | EMEA | ENA-R-RCIS | Russia | Core & Edge |  |  | INLINE TECHNOLOGIES GROUP LLC-Customer | ROSTELECOM-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 49700 | 0 | 49700 | 2486 | 64 | 2422 | 9049 | 9113 | -6627 | 47214 | 40587 | 55% | 82% | 6763 | 26% | 136 | 64 | 72 | 6699 | 6763 | -6627 | 2350 | 0 | 2350 | 0 | 0 | 0 | 0 | 0 | 17 | 17 | 0.1 | 16.9 | 0 |  | 0 | 0 |  | 0% | 0% | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 |  | 0.1 | 1 | 20847 ROSTELECOM WANDL PS Consultancy T&M 17 days
20848 | 20848 R-Telecom Network LLD and JS Platform +CSD FFP 2MS | Tyan, Kirill | Awarded | In Progress | Green | 2016-09-27 | 2016-10-17 | 2017-09-28 |  | 2017-06-29 | 87% | 20% | 0% |  | EMEA | ENA-R-RCIS | Russia | Core & Edge | Core & Edge |  | INLINE TECHNOLOGIES-EndUser | R-Telecom | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 41498 | 0 | 41498 | 24094 | 14769 | 9325 | 5991 | 20761 | 3334 | 17404 | 20737 | 30% | 50% | 15721 | 20% | 19054 | 14769 | 4285 | 951 | 15721 | 3334 | 5040 | 0 | 5040 | 0 | 0 | 0 | 0 | 0 | 43.5 | 43.5 | 37.8 | 5.6 | 0 | 18.5 | 18.5 | 1.6 | 16.9 | 74% | 74% | 1 | 2.1 | 34.5 | 1.6 | 0 | 0 | 1.8 |  | 41 | 1 | 20848 R-Telecom Network LLD and JS Platform +CSD FFP 2MS
20974 | 20974 STC VII Security 2015 Expansion FFP 6 MS | Qasem, Waleed | Awarded | Complete | Green | 2015-08-28 | 2015-08-16 | 2017-06-29 |  | 2017-06-01 | 127% | 18% | -27% | Customer Issues | EMEA | MEA | Saudi Arabia | Security |  |  | AWALNET, INC-Customer | STC - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 885000 | 885000 | 0 | 363190 | 246685 | 116505 | 29235 | 275920 | 87270 | 521810 | 609080 | 50% | 69% | 246685 | 18% | 333955 | 246685 | 87270 | 0 | 246685 | 87270 | 29235 | 0 | 29235 | 0 | 0 | 0 | 0 | 0 | 318 | 318 | 405.1 | 0 | -87.125 | 0 | 0 | 78.3 | 0 | 0% | 24% | 0 | 0 | 314.2 | 78.3 | 0 | 0.9 | 11.8 |  | 405.1 | 1 | 20974 STC VII Security 2015 Expansion FFP 6 MS
20975 | 20975 STC 2016 North IP MPLS Network & Automation FFP 11 MS RECLASS | Abuelneel, Ahmed | Awarded | In Progress | Green | 2016-06-24 | 2016-05-29 | 2017-03-31 |  |  | 143% | 0% | -43% |  | EMEA | MEA | Saudi Arabia | Core & Edge |  |  | ARABIAN INTERNET & COMMUNICATIONS SERVICES COMPANY - Customer | STC - End User | Reclass | None | Consulting – Fixed Price Custom |  | C | 0 | 0 | 0 | 1147200 | 1377163 | -229963 | 776 | 1377939 | -230739 | -1147200 | -1377939 | 0% | 0% | 1354459 | 0% | 1123720 | 1354459 | -230739 | 0 | 1354459 | -230739 | 23480 | 22704 | 776 | 0 | 0 | 0 | 0 | 0 | 1395 | 1395 | 1993.3 | 0 | -598.3125 | 0 | 0 | 473.9 | 0 | 0% | 31% | 25.3 | 38.4 | 1519.4 | 473.9 | 0 | 0 | 0 |  | 2057.1 | 1 | 20975 STC 2016 North IP MPLS Network & Automation FFP 11 MS RECLASS
21159 | 21159 General Dynamics Security Support - T&M - PO | Wiesner, Jill | Awarded | On Hold | Green | 2015-05-15 | 2018-06-04 | 2018-06-15 | 2018-07-30 | 2017-06-12 | 6% | 0% | 0% | Under/Not Over budget | AMER | NATIONAL GOVERNMENT | United States of America | Security |  |  | GENERAL DYNAMICS CORPORATION-Customer | GENERAL DYNAMICS-EndUser | PO | Monthly in Arrears | Consulting – T & M |  | A | 26290 | 0 | 26290 | 13100 | 542 | 12558 | 12713 | 13255 | -155 | 13190 | 13035 | 50% | 50% | 7755 | 0% | 7600 | 542 | 7058 | 7213 | 7755 | -155 | 5500 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0.6 | 9.4 | 0 | 0 | 0 | 0.6 | 0 | 0% | 7% | 0.5 | 0 | 0 | 0.6 | 0 | 0 | 0 |  | 1.1 | 1 | 21159 General Dynamics Security Support - T&M - PO
21178 | 21178 MTS South HLD & LLD FFP 2MS | Tyan, Kirill | Awarded | On Hold | Green | 2015-07-02 | 2015-10-04 | 2017-07-31 |  | 2017-06-26 | 127% | 31% | -27% | Scoping Issues | EMEA | ENA-R-RCIS | Russia | Core & Edge |  |  | MARVEL COMPUTER SOLUTIONS LIMITED-Customer | MTS-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 60000 | 60000 | 0 | 35653 | 20725 | 14928 | 4095 | 24820 | 10833 | 24347 | 35180 | 28% | 59% | 20725 | 31% | 31558 | 20725 | 10833 | 0 | 20725 | 10833 | 4095 | 0 | 4095 | 0 | 0 | 0 | 0 | 0 | 55.7 | 55.7 | 70.8 | 0 | -15.1525 | 27.1 | 27.1 | 4.1 | 23.1 | 95% | 62% | 0.2 | 1.3 | 66.8 | 4.1 | 0 | 0 | 0 |  | 72.3 | 1 | 21178 MTS South HLD & LLD FFP 2MS
21184 | 21184 MTS South SDID & LLD FFP 2MS | Tyan, Kirill | Awarded | On Hold | Green | 2015-07-02 | 2016-01-14 | 2017-09-28 |  | 2017-06-26 | 50% | 47% | 0% | Customer Issues | EMEA | ENA-R-RCIS | Russia | Core & Edge |  |  | Marvel Computer Solutions - CUSTOMER | MTS-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 50000 | 50000 | 0 | 32509 | 7812 | 24697 | 7865 | 15677 | 16831 | 17491 | 34323 | 21% | 69% | 15677 | 47% | 32509 | 7812 | 24697 | 7865 | 15677 | 16831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.3 | 52.3 | 26.1 | 26.2 | 0 | 30.3 | 30.3 | 3 | 27.3 | 138% | 138% | 0.1 | 0 | 21.8 | 3 | 0 | 0 | 1.3 |  | 26.1 | 1 | 21184 MTS South SDID & LLD FFP 2MS
21253 | 21253 Bestel OSS Automation Assessment - MDF | Almanza, Henry | Awarded | On Hold | Green | 2016-06-30 | 2017-09-01 | 2017-12-22 | 2017-01-08 | 2017-07-20 | 1% | 49% | -13% | Under/Not Over budget | AMER | CALA | Mexico | Network Automation |  |  | NEC DE MEXICO-EndUser | BESTEL-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | B | 50000 | 0 | 50000 | 35096 | 0 | 35096 | 10575 | 10575 | 24521 | 14904 | 39425 | 30% | 79% | 10575 | 49% | 35096 | 0 | 35096 | 10575 | 10575 | 24521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 34 | 0.3 | 33.8 | -3.9987 | 0 | 4 | 0.3 | 0 | 0% | 13% | 8.8 | 0 | 0 | 0.3 | 0 | 0 | 0 |  | 9.1 | 1 | 21253 Bestel OSS Automation Assessment - MDF
21342 | 21342 STC MSP 2015 - Year 2 PS | Qasem, Waleed | Awarded | On Hold | Green | 2015-06-04 | 2016-03-31 | 2017-06-30 |  | 2017-06-01 | 104% | 61% | -4% | SOW Issues | EMEA | MEA | Saudi Arabia | Core & Edge | Core & Edge |  | AWALNET, INC-Customer | STC - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 2596307 | 2596307 | 0 | 179517 | 97005 | 82513 | 19688 | 116693 | 62825 | 2416790 | 2479614 | 35% | 96% | 89603 | 61% | 152427 | 89603 | 62825 | 0 | 89603 | 62825 | 27090 | 7402 | 19688 | 0 | 0 | 0 | 0 | 0 | 131 | 131 | 136.3 | 0 | -5.3125 | 0 | 0 | 40.8 | 0 | 0% | 43% | 1.5 | 29.6 | 95.5 | 40.8 | 0 | 0 | 0 |  | 167.4 | 1 | 21342 STC MSP 2015 - Year 2 PS
21356 | 21356 STC IGW Netflow Assessment & Deployment FFP 8 MS | Bin Sabbar, Abdullah | Awarded | In Progress | Green | 2015-08-28 | 2016-05-15 | 2017-08-31 |  | 2017-07-06 | 36% | 24% | 0% | Under/Not Over budget | EMEA | MEA | Saudi Arabia | Core & Edge |  |  | AWALNET, INC-Customer | STC - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 240000 | 60676 | 179324 | 124105 | 27683 | 96422 | 65011 | 92693 | 31412 | 115895 | 147307 | 37% | 61% | 77153 | 24% | 108565 | 27683 | 80882 | 49471 | 77153 | 31412 | 15540 | 0 | 15540 | 0 | 0 | 0 | 0 | 0 | 99.5 | 99.5 | 35.8 | 63.8 | 0 | 0 | 0 | 14.9 | 0 | 0% | 18% | 0 | 0 | 20.8 | 14.9 | 0 | 0 | 0 |  | 35.8 | 1 | 21356 STC IGW Netflow Assessment & Deployment FFP 8 MS
21416 | 21416-ATT AIC Contrail Network Virtualization Phase 1 | Charleville, Vann | Awarded | In Progress | Green | 2017-04-17 | 2015-08-27 | 2017-12-29 |  | 2017-07-12 | 75% | 61% | 0% | Under/Not Over budget | AMER | AT&T | United States of America | SDN |  |  | AT&T INC.-Customer | ATT-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 24464870 | 0 | 24464870 | 4727876 | 1084280 | 3643596 | 1175669 | 2259949 | 2467927 | 19736994 | 22204921 | 30% | 91% | 854100 | 61% | 3322027 | 661687 | 2660340 | 192413 | 854100 | 2467927 | 55807 | 29260 | 26547 | 0 | 1350042 | 393333 | 956710 | 0 | 1200 | 1200 | 904.3 | 295.7 | 0 | 143.1 | 143.1 | 153.8 | 0 | 14% | 15% | 7.4 | 37 | 750.6 | 153.8 | 0 | 0 | 0 |  | 948.7 | 1 | 21416-ATT AIC Contrail Network Virtualization Phase 1
21503 | 21503 STC DDOS Kaspersky Solution FFP 7 MS | Qasem, Waleed | Awarded | On Hold | Green | 2015-08-24 | 2015-08-02 | 2016-06-30 |  |  | 76% | 36% | 0% |  | EMEA | MEA | Saudi Arabia | Core & Edge |  |  | AWALNET, INC-Customer | STC - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 120000 | 61026 | 58974 | 69518 | 28536 | 40982 | 12141 | 40677 | 28840 | 50482 | 79323 | 30% | 66% | 37790 | 36% | 66630 | 28536 | 38094 | 9254 | 37790 | 28840 | 2888 | 0 | 2888 | 0 | 0 | 0 | 0 | 0 | 61 | 61 | 46.1 | 14.9 | 0 | 0 | 0 | 13.5 | 0 | 0% | 28% | 0 | 0 | 31.6 | 13.5 | 0 | 0 | 1 |  | 46.1 | 1 | 21503 STC DDOS Kaspersky Solution FFP 7 MS
21553 | 21553 Comcast-Central Division CRAN Modernization | Smith, Ronald | Awarded | In Progress | Green | 2017-06-14 | 2015-12-01 | 2017-08-31 | 2017-07-31 | 2017-07-21 | 102% | -21% | -2% | Scoping Issues | AMER | CABLES | United States of America | Core & Edge |  |  | COMCAST CORPORATION-Customer | COMCAST-EndUser | PO | Milestone Payments | Install Custom |  | C | 8999399 | 9207123 | -207724 | 10919596 | 8765151 | 2154445 | 3554964 | 12320115 | -1400519 | -1920197 | -3320716 | -16% | -37% | 2900519 | -21% | 1500000 | 2900519 | -1400519 | 0 | 2900519 | -1400519 | 50000 | 7939 | 42061 | 0 | 9369596 | 5856693 | 3512903 | 0 | 2625.3 | 2625.3 | 2673.6 | 0 | -48.325 | 0 | 0 | 874.6 | 0 | 0% | 49% | 24.3 | 17.1 | 1796.7 | 874.6 | 2.4 | 0 | 0 |  | 2715 | 1 | 21553 Comcast-Central Division CRAN Modernization
21579 | 21579 London School of Economics PRO-JS-DC-QS Package | Foster, David | Awarded | On Hold | Amber | 2015-07-17 | 2015-08-17 | 2017-12-31 |  | 2017-07-14 | 50% | 52% | 0% | Under/Not Over budget | EMEA | UK-I | United Kingdom | Network Automation |  |  | AXIANS | London School of Economics-End User | PO | Upon Completion | Consulting – Packaged |  | A | 35100 | 0 | 35100 | 23697 | 3804 | 19893 | 7512 | 11316 | 12381 | 11403 | 23784 | 16% | 68% | 7536 | 52% | 19917 | 3804 | 16113 | 3732 | 7536 | 12381 | 3780 | 0 | 3780 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 6.6 | 6.4 | 0 | 0 | 0 | 3 | 0 | 0% | 30% | 0 | 0 | 3 | 3 | 0 | 0.6 | 0 |  | 6.6 | 1 | 21579 London School of Economics PRO-JS-DC-QS Package
21583 | 21583 FFP Verizon Wireless MRFP integration in Rochester and Syracuse | Stroud, Charlie | Awarded | In Progress | Green | 2016-02-18 | 2015-07-13 | 2016-12-30 |  |  | 36% | 14% | 0% |  | AMER | VERIZON | United States of America | Core & Edge |  |  | VERIZON WIRELESS-EndUser | VERIZON WIRELESS-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | B | 25800 | 0 | 25800 | 15400 | 4317 | 11083 | 7597 | 11914 | 3486 | 10400 | 13886 | 40% | 54% | 11914 | 14% | 15400 | 4317 | 11083 | 7597 | 11914 | 3486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 3.6 | 6.4 | 0 | 0 | 0 | 0.4 | 0 | 0% | 4% | 0 | 0 | 3.3 | 0.4 | 0 | 0 | 0 |  | 3.6 | 1 | 21583 FFP Verizon Wireless MRFP integration in Rochester and Syracuse
21623 | 21623 TEF FUSION HL3-HL4 Start Up FFP | Gil, Jose | Awarded | In Progress | Green |  | 2015-07-06 | 2018-12-14 |  |  | 31% | 0% | 0% |  | EMEA | Spain | Spain | Core & Edge |  |  | TELEFONICA - Customer | TELEFONICA - Customer | None | None | Consulting – Fixed Price Custom |  | B | 0 | 0 | 0 | 0 | 819974 | -819974 | 1815101 | 2635074 | -2635074 | 0 | -2635074 | 0% | 0% | 2634589 | 0% | 0 | 819489 | -819489 | 1815101 | 2634589 | -2634589 | 0 | 485 | 0 | -485 | 0 | 0 | 0 | 0 | 5645 | 5645 | 1749.9 | 3895.1 | 0 | 0 | 0 | 629.3 | 0 | 0% | 13% | 4.9 | 0 | 1120.7 | 629.3 | 0 | 0 | 0 |  | 1754.8 | 1 | 21623 TEF FUSION HL3-HL4 Start Up FFP
21641 | 21641 STC Network Consulting 170 Days (Reclass) | Shaat, Asaad | Awarded | In Progress | Green | 2015-09-04 | 2016-02-09 | 2017-04-01 |  |  | 19% | -37% | 0% |  | EMEA | MEA | Saudi Arabia | Core & Edge |  |  | AWALNET, INC-Customer | STC - End User | Reclass | Fully in Advance | Consulting – T & M |  | A | 0 | 0 | 0 | 55000 | 25373 | 29627 | 129010 | 154383 | -99383 | -55000 | -154383 | 37% | 0% | 99383 | -37% | 0 | 25373 | -25373 | 74010 | 99383 | -99383 | 55000 | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 170 | 170 | 33.1 | 136.9 | 0 | 0 | 0 | 13.6 | 0 | 0% | 9% | 41.7 | 6.1 | 9.5 | 13.6 | 0 | 0 | 10 |  | 80.9 | 1 | 21641 STC Network Consulting 170 Days (Reclass)
21661 | 21661 Talk Talk Q3 top up T&M CONSULTING 20 Days | Stirling, Alan | Awarded | In Progress | Green | 2015-08-06 | 2016-01-25 | 2017-07-28 |  | 2017-07-21 | 90% | 28% | 0% | Customer Issues | EMEA | UK-I | United Kingdom | Core & Edge |  |  | AXIANS | TALK TALK TECHNOLOGIES-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 62250 | 62250 | 0 | 37350 | 14845 | 22505 | 5312 | 20157 | 17193 | 24900 | 42093 | 40% | 68% | 13157 | 28% | 30350 | 13157 | 17193 | 0 | 13157 | 17193 | 7000 | 1688 | 5312 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 18.1 | 1.9 | 0 | 0 | 0 | 1.2 | 0 | 0% | 6% | 0 | 3.3 | 16.9 | 1.2 | 0 | 0 | 0 |  | 21.3 | 1 | 21661 Talk Talk Q3 top up T&M CONSULTING 20 Days
21722 | 21722 Bloomberg CCL | Cicatello, James | Awarded | In Progress | Green |  | 2015-10-01 | 2018-10-14 |  | 2017-07-19 | 94% | 65% | 0% | Under/Not Over budget | AMER | GLOBAL FINANCIAL SERVICES | United States of America | Juniper Strategic Delivery |  |  | BLOOMBERG/NEW YORK-EndUser | BLOOMBERG-EndUser | Cost Transfer | Quarterly in Arrears | Consulting – Fixed Price Custom |  | A | 4200000 | 0 | 4200000 | 3044629 | 806572 | 2238057 | 11563 | 818135 | 2226494 | 1155371 | 3381865 | 16% | 81% | 818135 | 65% | 3044629 | 806572 | 2238057 | 11563 | 818135 | 2226494 | 0 | 0 | 0 | 0 | 0 | 165416 | 0 | -165416 | 1095 | 1095 | 1025.4 | 69.7 | 0.0025 | 0 | 0 | 23.1 | 0 | 0% | 2% | 42.5 | 0.8 | 1002.3 | 23.1 | 0 | 0 | 0 |  | 1068.7 | 1 | 21722 Bloomberg CCL
21825 | 21825 OSP Simplicity L2 Giganet FFP 14 MS | Oliver, Juan | Awarded | In Progress | Green | 2016-11-03 | 2017-01-03 | 2018-04-30 |  |  | 134% | 30% | 0% | Customer Issues | EMEA | Spain | Spain | Core & Edge |  |  | ORANGE SPAIN | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 430259 | 339054 | 91205 | 130422 | 299390 | -168968 | 0 | 299390 | -168968 | 299837 | 130869 | 0% | 30% | 67871 | 30% | 130422 | 67871 | 62551 | 0 | 67871 | 62551 | 0 | 0 | 0 | 0 | 0 | 231520 | 0 | -231520 | 0 | 81.3 | 109.3 | 0 | -109.25 | 0 | 30.2 | 33 | 0 | 0% | 43% | 33.3 | 0 | 76.3 | 33 | 0 | 0 | 0 |  | 142.5 |  | 25676 OSP Pedrosa MX960 Design & InC FFP 2 MS | 21825 OSP Simplicity L2 Giganet FFP 14 MS
21826 | 21826 OSP Simplicity Stream2 FFP X MS | Oliver, Juan | Awarded | Booked | Green | 2017-05-30 | 2017-07-03 |  |  |  | 4% | 55% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | ORANGE SPAIN | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 466312 | 0 | 466312 | 0 | 3548 | -3548 | 69944 | 73492 | -73492 | 466312 | 392820 | 30% | 84% | 73492 | 55% | 0 | 3548 | -3548 | 69944 | 73492 | -73492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159.6 | 159.6 | 6.4 | 153.2 | 0 | 111.3 | 111.3 | 6.4 | 104.9 | 230% | 230% | 5.9 | 0 | 0 | 6.4 | 0 | 0 | 0 |  | 12.3 | 1 | 21826 OSP Simplicity Stream2 FFP X MS
21868 | 21868 TEF FUSION Migration HL3 HL4 Jaen | Gil, Jose | Awarded | In Progress | Green | 2016-03-30 | 2016-04-04 | 2017-12-22 |  |  | 55% | 19% | 0% |  | EMEA | Spain | Spain | Core & Edge |  |  | TELEFONICA - Customer | TELEFONICA - Customer | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 301753 | 221476 | 80277 | 205000 | 172795 | 32205 | 60718 | 233513 | -28513 | 96753 | 68240 | 4% | 23% | 28513 | 19% | 0 | 17780 | -17780 | 10733 | 28513 | -28513 | 0 | 0 | 0 | 0 | 205000 | 155016 | 49984 | 0 | 90 | 90 | 49.4 | 40.6 | 0 | 0 | 0 | 28.2 | 0 | 0% | 46% | 0 | 10.8 | 21.2 | 28.2 | 0 | 0 | 0 |  | 60.2 | 1 | 21868 TEF FUSION Migration HL3 HL4 Jaen
21869 | 21869 TEF FUSION Migration HL3 HL4 Cordoba | Gil, Jose | Awarded | In Progress | Green | 2016-03-30 | 2016-04-01 | 2017-12-29 |  |  | 60% | 12% | 0% |  | EMEA | Spain | Spain | Core & Edge |  |  | TELEFONICA - Customer | TELEFONICA - Customer | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 507754 | 372674 | 135080 | 386200 | 367652 | 18548 | 59445 | 427097 | -40897 | 121554 | 80657 | 4% | 16% | 40897 | 12% | 0 | 26687 | -26687 | 14210 | 40897 | -40897 | 1200 | 0 | 1200 | 0 | 385000 | 340966 | 44034 | 0 | 120 | 120 | 71.4 | 48.6 | 0 | 0 | 0 | 42.6 | 0 | 0% | 55% | 0 | 10.4 | 28.8 | 42.6 | 0 | 0 | 0 |  | 81.8 | 1 | 21869 TEF FUSION Migration HL3 HL4 Cordoba
21927 | 21927 VHA - EOL Migration CR0001 - FFP | Jacobs, Christo | Awarded | In Progress | Green | 2015-09-30 | 2015-09-30 | 2017-08-11 |  | 2017-07-21 | 100% | -228% | -352% | Scoping Issues | APAC | ANZ | Australia | Core & Edge |  |  | VODAFONE NETWORKS PTY LTD-EndUser | VODAFONE NETWORKS PTY LTD-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 128800 | 128800 | 0 | 97600 | 391646 | -294046 | 0 | 391646 | -294046 | 31200 | -262847 | 24% | -204% | 389849 | -228% | 97600 | 389849 | -292249 | 0 | 389849 | -292249 | 0 | 0 | 0 | 0 | 0 | 1798 | 0 | -1798 | 116 | 524.1 | 524.9 | 0 | -408.875 | 40.7 | 226.3 | 113.9 | 0 | 54% | 76% | 0 | 0 | 347.3 | 113.9 | 0 | 36.4 | 27.4 |  | 524.9 | 2 | 21927 VHA - EOL Migration CR0001 - FFP
21930 | 21930 Repsol Campus 802.1x Scripts implementation FFP 1 MS | M, Rahimunnisa | Awarded | In Progress | Green | 2017-04-24 | 2017-04-18 | 2017-06-30 |  | 2017-07-20 | 202% | 2% | -102% | Scoping Issues | EMEA | Spain | Spain | Network Automation |  |  | INDRA SISTEMAS S.A.-Customer | REPSOL-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 17954 | 0 | 17954 | 11870 | 14060 | -2190 | 0 | 14060 | -2190 | 6084 | 3894 | 20% | 22% | 14060 | 2% | 11870 | 14060 | -2190 | 0 | 14060 | -2190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 | 9.1 | 18.4 | 0 | -9.3125 | 4 | 4 | 1.1 | 3 | 80% | 28% | 2.5 | 0 | 17 | 1.1 | 0 | 0 | 0.4 |  | 20.9 | 1 | 21930 Repsol Campus 802.1x Scripts implementation FFP 1 MS
22014 | 22014 DT General Program Management (Volker) INTERNAL | Kraemer, Volker | Awarded | In Progress | Green |  | 2015-08-01 | 2015-12-31 |  |  |  | 0% | 0% |  | EMEA | Germany | Germany | Core & Edge |  |  | Juniper | Juniper | None | None |  |  | A | 0 | 0 | 0 | 0 | 88535 | -88535 | 0 | 88535 | -88535 | 0 | -88535 | 0% | 0% | 85595 | 0% | 0 | 85595 | -85595 | 0 | 85595 | -85595 | 0 | 2940 | 0 | -2940 | 0 | 0 | 0 | 0 | 0 | 0 | 170.8 | 0 | -170.75 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 170.8 | 0 | 0 | 0 | 0 |  | 170.8 |  | 22014 DT General Program Management (Volker) INTERNAL
22023 | 22023 Commonwealth of Kentucky NG-KIH | Hassan, Saqib | Awarded | In Progress | Green | 2017-04-04 | 2017-04-24 | 2017-09-30 | 2017-12-31 | 2017-07-21 | 40% | 0% | 0% | Under/Not Over budget | AMER | US TERRITORIES | United States of America | Core & Edge |  |  | Fujitsu-Customer | The Commonwealth of Kentucky-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 212956 | 0 | 212956 | 90854 | 35276 | 55578 | 55858 | 91134 | -280 | 122102 | 121822 | 57% | 57% | 78334 | 0% | 78054 | 35276 | 42778 | 43058 | 78334 | -280 | 12800 | 0 | 12800 | 0 | 0 | 0 | 0 | 0 | 79.3 | 79.3 | 31.8 | 47.4 | 0 | 21.6 | 21.6 | 13.4 | 8.2 | 38% | 38% | 4.7 | 2 | 18.4 | 13.4 | 0 | 0 | 0 |  | 38.5 | 1 | 22023 Commonwealth of Kentucky NG-KIH
22234 | 22234 - University of Virginia Core/Edge Audit | Gregory, Mina | Awarded | On Hold | Green |  | 2016-07-25 | 2017-09-30 | 2016-09-23 |  | 2% | 13% | 0% |  | AMER | US TERRITORIES | United States of America | Core & Edge |  |  | SLAIT CONSULTING-Customer | University of Virginia-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 64264 | 0 | 64264 | 34780 | 475 | 34305 | 24593 | 25068 | 9712 | 29484 | 39196 | 48% | 61% | 19588 | 13% | 29300 | 475 | 28825 | 19113 | 19588 | 9712 | 5480 | 0 | 5480 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 0.4 | 28.6 | 0.00125 | 0 | 0 | 0 | 0 | 0% | 0% | 2.5 | 0.3 | 0 | 0 | 0.4 | 0 | 0 |  | 3.3 | 1 | 22234 - University of Virginia Core/Edge Audit
22241 | 22241 AON UK LAN refresh "ED" | Foster, David | Awarded | In Progress | Green | 2016-10-28 | 2016-10-31 | 2017-12-31 |  | 2017-07-14 | 190% | 5% | 94% | Under/Not Over budget | EMEA | UK-I | United Kingdom | Cloud |  |  | DIMENSION DATA HOLDINGS LTD-Customer | AON CORPORATION-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 353800 | 353800 | 0 | 365241 | 150090 | 215151 | 44131 | 194221 | 171020 | -11441 | 159579 | 40% | 45% | 12955 | 5% | 183975 | 12955 | 171020 | 0 | 12955 | 171020 | 6000 | 110 | 5890 | 0 | 175266 | 137025 | 38241 | 0 | 480 | 15 | 28.6 | 0 | 451.4375 | 0 | 0 | 5.3 | 0 | 0% | 23% | 14.2 | 3.1 | 23.3 | 5.3 | 0 | 0 | 0 |  | 45.9 | 2 | 22241 AON UK LAN refresh "ED"
22254 | 22254 GACA KKIA Terminal Network Design FFP 1 MS | Al Aswad, Waseem | Awarded | On Hold | Green | 2015-11-09 | 2015-11-16 | 2017-10-31 |  | 2017-06-01 | 91% | 37% | 0% | Under/Not Over budget | EMEA | MEA | Saudi Arabia | Cloud |  |  | MINDWARE S.A.-Customer | GACA | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 134901 | 0 | 134901 | 83616 | 38866 | 44750 | 13039 | 51905 | 31711 | 51285 | 82996 | 25% | 62% | 36120 | 37% | 67831 | 36120 | 31711 | 0 | 36120 | 31711 | 15785 | 2746 | 13039 | 0 | 0 | 0 | 0 | 0 | 53 | 53 | 48.4 | 4.6 | 0 | 0 | 0 | 15.4 | 0 | 0% | 41% | 0.1 | 5.6 | 33 | 15.4 | 0 | 0 | 0 |  | 54.2 | 1 | 22254 GACA KKIA Terminal Network Design FFP 1 MS
22278 | 22278 SUnet CREDIT BOOKING SALES | Skorski, Pawel | Awarded | Booked | Green | 2015-12-30 | 2015-12-31 | 2016-12-30 |  |  |  | 68% | 0% |  | EMEA | ENA-R-NORTH | Sweden | Core & Edge |  |  | IPNETT AS-Customer | SUNET-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 55000 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 55000 | 32% | 100% | 0 | 68% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.4 |  | 22278 SUnet CREDIT BOOKING SALES
22302 | 22302 Etisalat GVPN Network Review FFP 1 MS | Bhinder, Muhammad Amir Rashid | Awarded | In Progress | Green | 2016-02-04 | 2016-02-11 | 2017-07-31 |  | 2017-07-06 | 143% | 11% | -43% | Scoping Issues | EMEA | MEA | UAE | Core & Edge |  |  | ALPHA DATA PROCESSING LLC-Customer | ETISALAT-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 52613 | 52613 | 0 | 28263 | 28247 | 16 | 0 | 28247 | 16 | 24350 | 24366 | 35% | 46% | 28247 | 11% | 28263 | 28247 | 16 | 0 | 28247 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 22 | 31.4 | 0 | -9.4375 | 0 | 0 | 5.4 | 0 | 0% | 21% | 0.1 | 2.4 | 26 | 5.4 | 0 | 0 | 0 |  | 34 | 1 | 22302 Etisalat GVPN Network Review FFP 1 MS
22362 | 22362 - AON Campus & Branch Assessment | Kouzionis, Nicholas | Awarded | On Hold | Green | 2015-12-31 | 2016-05-25 | 2017-09-30 | 2016-07-15 | 2017-06-20 | 9% | 33% | 0% |  | AMER | GLOBAL FINANCIAL SERVICES | United States of America | Cloud |  |  | DIMENSION DATA HOLDINGS LTD-Customer | AON-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 140101 | 0 | 140101 | 32000 | 4623 | 27377 | 18123 | 22746 | 9254 | 108101 | 117355 | 51% | 84% | 22746 | 33% | 32000 | 4623 | 27377 | 18123 | 22746 | 9254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 4.2 | 43.8 | 0.0025 | 48 | 48 | 1.8 | 46.2 | 768300% | 960350% | 19.2 | 1.1 | 2.4 | 1.8 | 0 | 0 | 0 |  | 24.4 | 1 | 22362 - AON Campus & Branch Assessment
22394 | 22394 Telefonica P1 Cases Support - Peru, Chile, Ecuador, Colombia, Argentina | Barbieri De Sousa, Alexandre | Awarded | In Progress | Green | 2016-08-18 | 2016-04-01 | 2017-08-23 |  |  | 80% | -18% | 0% |  | AMER | CALA | Peru | Core & Edge |  |  | NEC CORPORATION-Customer | TELEFONICA - Customer | PO | Monthly in Advance | Consulting – Fixed Price Custom |  | B | 406000 | 0 | 406000 | 0 | 355864 | -355864 | 0 | 355864 | -355864 | 406000 | 50136 | 30% | 12% | 11099 | -18% | 0 | 11099 | -11099 | 0 | 11099 | -11099 | 0 | 0 | 0 | 0 | 0 | 344765 | 0 | -344765 | 127.1 | 127.1 | 102.2 | 24.9 | 0 | 0 | 0 | 9.5 | 0 | 0% | 8% | 46 | 0 | 92.7 | 9.5 | 0 | 0 | 0 |  | 148.2 | 1 | 22394 Telefonica P1 Cases Support - Peru, Chile, Ecuador, Colombia, Argentina
22439 | 22439 Djezzy Design Services FFP 2 MS T&M 37 days | Chouaieb, Mejda | Awarded | In Progress | Green | 2015-12-10 | 2015-11-26 | 2017-08-31 |  | 2017-06-30 | 111% | 30% | -71% | SOW Issues | EMEA | ENA-R-SOUTH | Algeria | Core & Edge | Core & Edge | Core & Edge | NOKIA CORPORATION-Customer | Djezzy | PO | Milestone Payments | Consulting – Fixed Price Custom | Consulting – T & M | C | 189999 | 189999 | 0 | 69003 | 75252 | -6249 | 1266 | 76518 | -7515 | 120996 | 113481 | 30% | 60% | 72768 | 30% | 65253 | 72768 | -7515 | 0 | 72768 | -7515 | 3750 | 2484 | 1266 | 0 | 0 | 0 | 0 | 0 | 84 | 130 | 143.9 | 0 | -59.875 | 0 | 0 | 42.5 | 0 | 0% | 42% | 4.9 | 6.3 | 93.9 | 42.5 | 0 | 7 | 0.5 |  | 155 | 1 | 22439 Djezzy Design Services FFP 2 MS T&M 37 days
22450 | 22450 Etisalat GVPN Junos Space PS Consultancy T&M 28 Days | Bhinder, Muhammad Amir Rashid | Awarded | In Progress | Green | 2016-03-14 | 2016-03-02 | 2017-07-31 |  | 2017-07-06 | 177% | -5% | -77% | Product Issues | EMEA | MEA | UAE | Network Automation |  |  | ALPHA DATA PROCESSING LLC-Customer | ETISALAT-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 78100 | 78100 | 0 | 31080 | 33227 | -2147 | 3500 | 36727 | -5647 | 47020 | 41373 | 58% | 53% | 33227 | -5% | 27580 | 33227 | -5647 | 0 | 33227 | -5647 | 3500 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 28 | 28 | 49.7 | 0 | -21.6875 | 0 | 0 | 14.5 | 0 | 0% | 41% | 2.1 | 8.6 | 26.2 | 14.5 | 0 | 0 | 9 |  | 60.4 | 1 | 22450 Etisalat GVPN Junos Space PS Consultancy T&M 28 Days
22451 | 22451 TIM POC and Risk Analysis | Barbieri De Sousa, Alexandre | Awarded | In Progress | Green | 2016-06-30 | 2016-09-05 | 2017-07-31 |  |  | 72% | 45% | 0% |  | AMER | CALA | Brazil | Core & Edge |  |  | NEC CORPORATION-Customer | TELECOM ITALIA-EndUser | PO |  | Consulting – Fixed Price Custom |  | B | 176000 | 0 | 176000 | 0 | 40631 | -40631 | 0 | 40631 | -40631 | 176000 | 135369 | 32% | 77% | 38510 | 45% | 0 | 38510 | -38510 | 0 | 38510 | -38510 | 0 | 2121 | 0 | -2121 | 0 | 0 | 0 | 0 | 60 | 60 | 43.3 | 16.8 | 0 | 0 | 0 | 16.8 | 0 | 0% | 39% | 37.1 | 0 | 26.5 | 16.8 | 0 | 0 | 0 |  | 80.4 | 1 | 22451 TIM POC and Risk Analysis
22453 | 22453 TEF FUSION MAN 14 - Phase 2 (19 I&C) | Gil, Jose | Awarded | In Progress | Green | 2015-12-22 | 2015-12-29 | 2017-07-28 |  |  | 74% | 12% | 0% |  | EMEA | Spain | Spain | Core & Edge |  |  | TELEFONICA - Customer | TELEFONICA - Customer | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 447596 | 415431 | 32165 | 626782 | 272294 | 354488 | 104651 | 376944 | 249838 | -179186 | 70652 | 4% | 16% | 50083 | 12% | 299921 | 38954 | 260967 | 11130 | 50083 | 249838 | 5940 | 726 | 5214 | 0 | 320921 | 232614 | 88307 | 0 | 95 | 95 | 70 | 25 | 0 | 0 | 0 | 70 | 0 | 0% | 280% | 5 | 0 | 0 | 70 | 0 | 0 | 0 |  | 75 | 1 | 22453 TEF FUSION MAN 14 - Phase 2 (19 I&C)
22466 | 22466-ATT uCPE PS Consulting Support | Charleville, Vann | Awarded | In Progress | Green |  | 2015-11-30 | 2017-12-29 | 2017-12-29 | 2017-07-12 | 65% | 14% | 0% | Under/Not Over budget | AMER | AT&T | United States of America | Security | SDN |  | AT&T-EndUser | AT&T-EndUser | Token/Credit | Milestone Payments | Consulting – Fixed Price Custom |  | B | 1184816 | 906352 | 278464 | 824134 | 388528 | 435606 | 287875 | 676403 | 147731 | 360682 | 508413 | 29% | 43% | 484403 | 14% | 632134 | 348023 | 284111 | 136379 | 484403 | 147731 | 192000 | 40505 | 151495 | 0 | 0 | 0 | 0 | 0 | 587.5 | 587.5 | 382.4 | 205.1 | 0 | 408.3 | 408.3 | 22.8 | 385.6 | 228% | 228% | 1.3 | 51.6 | 359.5 | 22.8 | 0.2 | 0 | 0 |  | 435.3 | 1 | 22466-ATT uCPE PS Consulting Support
22504 | 22504 DT ''Lightweight 4 over 6'' LW4o6 RFQ FFP 8 MS | Chouaieb, Mejda | Awarded | On Hold | Green | 2017-03-31 | 2017-04-04 | 2017-10-31 |  | 2017-06-30 | 2% | -32% | -227% | Under/Not Over budget | EMEA | DACH | Greece | Core & Edge | Network Automation |  | DEUTSCHE TELEKOM-Customer | DEUTSCHE TELEKOM-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 112983 | 0 | 112983 | 67246 | 1755 | 65491 | 114174 | 115929 | -48683 | 45737 | -2946 | 29% | -3% | 101779 | -32% | 53096 | 1755 | 51341 | 100024 | 101779 | -48683 | 14150 | 0 | 14150 | 0 | 0 | 0 | 0 | 0 | 52 | 170 | 3 | 167 | -118 | 0 | 118 | 2.8 | 0 | 0% | 227% | 0.4 | 0 | 0.3 | 2.8 | 0 | 0 | 0 |  | 3.4 | 1 | 22504 DT ''Lightweight 4 over 6'' LW4o6 RFQ FFP 8 MS
22549 | 22549 STC JSD FFP 1 MS RECLASS | Bin Sabbar, Abdullah | Awarded | On Hold | Green | 2015-12-26 | 2016-01-01 | 2017-12-31 |  |  | 101% | -44812229% | -1% |  | EMEA | MEA | Saudi Arabia | Core & Edge | Juniper Strategic Delivery |  | AWALNET, INC-Customer | STC - End User | Reclass | Milestone Payments | Consulting – Fixed Price Custom |  | B | 1 | 0 | 1 | 215000 | 233123 | -18123 | 215000 | 448123 | -233123 | -214999 | -448122 | 10% | -44812219% | 233123 | -44812229% | 0 | 233123 | -233123 | 0 | 233123 | -233123 | 0 | 0 | 0 | 0 | 215000 | 0 | 215000 | 0 | 240 | 240 | 242 | 0 | -2 | 0 | 0 | 136 | 0 | 0% | 128% | 0.6 | 0 | 106 | 136 | 0 | 0 | 0 |  | 242.6 | 1 | 22549 STC JSD FFP 1 MS RECLASS
22559 | 22559 BT21CN Harlequin IPv6 change request | Foster, David | Awarded | In Progress | Green | 2016-02-10 | 2016-02-01 | 2017-09-29 |  | 2017-07-14 | 97% | 31% | 0% | Customer Issues | EMEA | UK-I | United Kingdom | Core & Edge |  |  | BRITISH TELECOM - Customer | BT 21CN-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 61193 | 61193 | 0 | 40590 | 25546 | 15044 | 369 | 25915 | 14675 | 20603 | 35278 | 27% | 58% | 25495 | 31% | 40170 | 25495 | 14675 | 0 | 25495 | 14675 | 420 | 51 | 369 | 0 | 0 | 0 | 0 | 0 | 41 | 41 | 39.7 | 1.3 | 0 | 0 | 0 | 4.4 | 0 | 0% | 12% | 2.6 | 0 | 32.8 | 4.4 | 0 | 0 | 2.5 |  | 42.3 | 1 | 22559 BT21CN Harlequin IPv6 change request
22595 | 22595 US Navy PMRF MPLS Implementation - Phase 2 | Wiesner, Jill | Awarded | In Progress | Green | 2016-11-01 | 2016-10-31 | 2017-09-01 | 2017-09-30 | 2017-06-23 | 94% | -1% | 0% | Under/Not Over budget | AMER | NATIONAL GOVERNMENT | United States of America | Core & Edge |  |  | US DEPT. OF NAVY SPAWAR SYSTEMS-EndUser | UNITED STATES NAVY-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 133343 | 0 | 133343 | 94546 | 81212 | 13334 | 14495 | 95708 | -1162 | 38797 | 37635 | 29% | 28% | 76958 | -1% | 75796 | 76958 | -1162 | 0 | 76958 | -1162 | 18750 | 4255 | 14495 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 56.6 | 3.4 | 0 | 26.7 | 26.7 | 8.8 | 17.9 | 80% | 80% | 3.6 | 2.5 | 47.9 | 8.8 | 0 | 0 | 0 |  | 62.7 | 1 | 22595 US Navy PMRF MPLS Implementation - Phase 2
22637 | 22637 FASTWEB 2016 Projects - PS CREDIT BOOKING 160 CREDITS | Masci, Fabio | Awarded | In Progress | Green | 2015-12-31 | 2016-01-01 | 2016-12-31 |  |  |  | 100% | 0% |  | EMEA | ENA-R-SOUTH | Italy | Core & Edge |  |  | FASTWEB-Customer | FASTWEB-EndUser | PO | Fully in Advance |  |  | A | 320000 | 320000 | 0 | 0 | 884 | -884 | 0 | 884 | -884 | 320000 | 319116 | 0% | 100% | 884 | 100% | 0 | 884 | -884 | 0 | 884 | -884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | -1.1875 | 0 | 0 | 1.2 | 0 | 0% | 0% | 0 | 0 | 0 | 1.2 | 0 | 0 | 0 |  | 1.2 |  | 22637 FASTWEB 2016 Projects - PS CREDIT BOOKING 160 CREDITS
22672 | 22672 Interoute CREDITS BOOKING 35 PS CREDITS | Foster, David | Awarded | Booked | Green | 2015-12-23 | 2015-12-25 | 2016-12-24 |  |  | 0% | -13% | 0% | Under/Not Over budget | EMEA | UK-I | United Kingdom | Core & Edge |  |  | TELENT COMMUNICATIONS HOLDINGS LTD-Customer | INTEROUTE-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 73150 | 73150 | 0 | 105091 | 0 | 105091 | 59368 | 59368 | 45723 | -31941 | 13782 | 32% | 19% | 59368 | -13% | 105091 | 0 | 105091 | 59368 | 59368 | 45723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 82 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2 | 1 | 22672 Interoute CREDITS BOOKING 35 PS CREDITS
22703 | 22703 SGIX - ACI Project - FFP | Jacobs, Christo | Awarded | In Progress | Amber | 2017-01-10 | 2017-01-20 | 2017-08-11 |  | 2017-07-21 | 93% | -27% | -27% | Product Issues | APAC | ASEAN | Singapore | Cloud |  |  | DIMENSION DATA HOLDINGS LTD-Customer | SINGAPORE INTERNET EXCHANGE LTD - EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 19740 | 14390 | 5350 | 18400 | 22117 | -3717 | 1554 | 23671 | -5271 | 1340 | -3931 | 7% | -20% | 23671 | -27% | 18400 | 22117 | -3717 | 1554 | 23671 | -5271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 26.7 | 24.9 | 1.8 | -5.6562 | 4.7 | 7 | 7.9 | 0 | 29% | 42% | 0 | 0 | 16.3 | 7.9 | 0 | 0 | 0.8 |  | 24.9 | 1 | 22703 SGIX - ACI Project - FFP
22745 | 22745 OneNet DCI Implementation | Hassan, Saqib | Awarded | On Hold | Green | 2016-08-12 | 2016-08-29 | 2017-09-29 | 2017-08-31 | 2017-07-21 | 99% | 13% | 0% | Under/Not Over budget | AMER | US TERRITORIES | United States of America | Core & Edge |  |  | ONENET-EndUser | ONENET-EndUser | PO/Reclass | Milestone Payments | Consulting – Fixed Price Custom |  | B | 145000 | 145000 | 0 | 91885 | 58070 | 33815 | 10692 | 68762 | 23123 | 53115 | 76238 | 40% | 53% | 57342 | 13% | 80465 | 57342 | 23123 | 0 | 57342 | 23123 | 11420 | 728 | 10692 | 0 | 0 | 0 | 0 | 0 | 60.9 | 60.9 | 60.3 | 0.7 | -0.00125 | 0 | 0 | 16.8 | 0 | 0% | 38% | 2.1 | 2.4 | 43.5 | 16.8 | 0 | 0 | 0 |  | 64.8 | 1 | 22745 OneNet DCI Implementation
22753 | 22753 VF IT Multi-network capacity planning, modelling & CFA WANDL FFP 2MS | Moreno, Carlos | Awarded | In Progress | Amber | 2016-02-10 | 2016-02-15 | 2017-06-30 |  | 2017-07-12 | 89% | 40% | 0% |  | EMEA | UK-I | Italy | Core & Edge |  |  | VODAFONE | VODAFONE ITALY-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 60828 | 0 | 60828 | 36195 | 11964 | 24231 | 7340 | 19304 | 16891 | 24633 | 41524 | 28% | 68% | 13460 | 40% | 30351 | 11964 | 18387 | 1496 | 13460 | 16891 | 5844 | 0 | 5844 | 0 | 0 | 0 | 0 | 0 | 23.6 | 23.6 | 20.9 | 2.7 | 0 | 0 | 0 | 10.9 | 0 | 0% | 85% | 0.1 | 0 | 9.4 | 10.9 | 0 | 0.6 | 0 |  | 21.1 | 1 | 22753 VF IT Multi-network capacity planning, modelling & CFA WANDL FFP 2MS
22793 | 22793 Moscow Metro DC for Intellect Video Monitoring FFP 2 MS | Tyan, Kirill | Awarded | In Progress | Green | 2016-06-01 | 2016-06-01 | 2017-08-31 |  | 2017-05-30 | 57% | 41% | 0% |  | EMEA | ENA-R-RCIS | Russia | Cloud |  |  | ISOLIN TRADE & INVEST | Moscow Metro | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 55163 | 35889 | 19274 | 31913 | 9627 | 22285 | 6538 | 16165 | 15747 | 23250 | 38998 | 30% | 71% | 16165 | 41% | 31913 | 9627 | 22285 | 6538 | 16165 | 15747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52.9 | 52.9 | 30.3 | 22.5 | 0 | 21.2 | 21.2 | 1.6 | 19.6 | 67% | 67% | 1.7 | 0 | 28 | 1.6 | 0 | 0.8 | 0 |  | 32.1 | 1 | 22793 Moscow Metro DC for Intellect Video Monitoring FFP 2 MS
22830 | 22830 FASTWEB T&M (NET and SEC) T&M CONSULTING 15 Days | Masci, Fabio | Awarded | In Progress | Green | 2015-12-31 | 2016-02-29 | 2017-12-31 | 2016-12-31 | 2017-06-30 | 146% | 21% | -46% |  | EMEA | ENA-R-SOUTH | Italy | Core & Edge |  |  | FASTWEB-Customer | FASTWEB-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 40450 | 40450 | 0 | 25813 | 14426 | 11387 | 3050 | 17476 | 8337 | 14637 | 22974 | 36% | 57% | 14426 | 21% | 22763 | 14426 | 8337 | 0 | 14426 | 8337 | 3050 | 0 | 3050 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 21.9 | 0 | -6.875 | 0 | 0 | 4.9 | 0 | 0% | 29% | 0 | 6.9 | 17 | 4.9 | 0 | 0 | 0 |  | 28.8 | 1 | 22830 FASTWEB T&M (NET and SEC) T&M CONSULTING 15 Days
22856 | 22856 REPSOL 2016 T&M CONSULTING 6 Days | M, Rahimunnisa | Awarded | Booked | Green | 2015-12-26 |  | 2017-08-31 |  | 2017-06-19 | 15% | 25% | 0% |  | EMEA | Spain | Spain | Security |  |  | INGRAM MICRO INC-Customer | REPSOL-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 19000 | 0 | 19000 | 8328 | 369 | 7959 | 3283 | 3653 | 4675 | 10672 | 15347 | 56% | 81% | 2203 | 25% | 6878 | 369 | 6509 | 1833 | 2203 | 4675 | 1450 | 0 | 1450 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0.9 | 5.1 | 0 | 0 | 0 | 0.9 | 0 | 0% | 17% | 0.3 | 0 | 0 | 0.9 | 0 | 0 | 0 |  | 1.2 | 1 | 22856 REPSOL 2016 T&M CONSULTING 6 Days
22868 | 22868 VF Southern Hub PM Performance Management FFP 3 MS (FOC) | Moreno, Carlos | Awarded | In Progress | Amber |  | 2016-03-02 | 2017-12-29 |  | 2017-07-12 | 257% | -16% | -157% | Customer Issues | EMEA | UK-I | Italy | Network Automation |  |  | VODAFONE | VODAFONE SOUTHERN HUB | Free of Charge | None | Consulting – Fixed Price Custom |  | B | 56796 | 0 | 56796 | 55008 | 33746 | 21262 | 32255 | 66001 | -10993 | 1788 | -9205 | 0% | -16% | 32036 | -16% | 21043 | 32036 | -10993 | 0 | 32036 | -10993 | 9830 | 1710 | 8120 | 0 | 24135 | 0 | 24135 | 0 | 21 | 21 | 53.9 | 0 | -32.875 | 0 | 0 | 12.1 | 0 | 0% | 29% | 0.8 | 2.4 | 33.3 | 12.1 | 0 | 1.9 | 6.6 |  | 57 | 1 | 22868 VF Southern Hub PM Performance Management FFP 3 MS (FOC)
22890 | 22890 DT BNG Q1'16 (Actuals) Ph1a MX960 Installs (SA tracking only) | López Moreno, Claudia | Awarded | In Progress | Green | [6 empty] | 0% | 0% |  | EMEA | Germany | Germany | Core & Edge |  |  | DEUTSCHE TELEKOM-Customer | DEUTSCHE TELEKOM-EndUser | None | None | Consulting – Fixed Price Custom |  | A | 0 | 0 | 0 | 0 | 15193 | -15193 | 0 | 15193 | -15193 | 0 | -15193 | 0% | 0% | 15193 | 0% | 0 | 15193 | -15193 | 0 | 15193 | -15193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.5 | 0 | -27.5 | 0 | 0 | 27.5 | 0 | 0% | 0% | 0 | 0 | 0 | 27.5 | 0 | 0 | 0 |  | 27.5 |  | 22890 DT BNG Q1'16 (Actuals) Ph1a MX960 Installs (SA tracking only)
22939 | 22939 TE FUSION HL1-HL2 (CORE) | Gil, Jose | Awarded | In Progress | Green |  | 2016-03-13 | 2019-12-20 |  |  | 28% | 0% | 0% |  | EMEA | Spain | Spain | Core & Edge |  |  | TELEFONICA - Customer | TELEFONICA - Customer | None | None | Consulting – Fixed Price Custom |  | B | 0 | 0 | 0 | 0 | 218702 | -218702 | 555543 | 774245 | -774245 | 0 | -774245 | 0% | 0% | 773464 | 0% | 0 | 217921 | -217921 | 555543 | 773464 | -773464 | 0 | 781 | 0 | -781 | 0 | 0 | 0 | 0 | 1379 | 1379 | 386.4 | 992.6 | 0 | 0 | 0 | 2.4 | 0 | 0% | 0% | 14.6 | 0 | 383.8 | 2.4 | 0 | 0 | 0.3 |  | 401 | 1 | 22939 TE FUSION HL1-HL2 (CORE)
23005 | 23005 POST Luxemburg VCPE via COE FFP 3 MS (FOC) | Moreno, Carlos | Awarded | On Hold | Green |  | 2016-01-29 | 2017-10-27 |  | 2017-07-12 | 184% | -32% | -84% |  | EMEA | ENA-R-NORTH | Luxembourg | SDN |  |  | INFRADATA B.V.-Customer | POST Luxembourg-EndUser | Free of Charge | Milestone Payments | Consulting – Fixed Price Custom |  | A | 0 | 0 | 0 | 22011 | 14301 | 7710 | 0 | 14301 | 7710 | -22011 | -14301 | 32% | 0% | 11417 | -32% | 22011 | 11417 | 10594 | 0 | 11417 | 10594 | 0 | 2884 | 0 | -2884 | 0 | 0 | 0 | 0 | 11 | 11 | 20.3 | 0 | -9.25 | 0 | 0 | 3 | 0 | 0% | 17% | 1.6 | 3.1 | 13.5 | 3 | 0 | 0 | 3.8 |  | 24.9 | 1 | 23005 POST Luxemburg VCPE via COE FFP 3 MS (FOC)
23058 | 23058 BT Web Filtering - Part 1 FFP 2MS | Foster, David | Awarded | In Progress | Green | 2017-03-25 | 2017-04-07 | 2017-08-25 |  | 2017-07-07 | 49% | 5% | -5% | Under/Not Over budget | EMEA | UK-I | United Kingdom | Core & Edge |  |  | BRITISH TELECOM - Customer | BT GLOBAL SERVICES (DIRECT)-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 147146 | 0 | 147146 | 98553 | 52404 | 46149 | 50558 | 102962 | -4410 | 48593 | 44184 | 25% | 30% | 97682 | 5% | 93273 | 52376 | 40897 | 45306 | 97682 | -4410 | 5280 | 28 | 5252 | 0 | 0 | 0 | 0 | 0 | 98.9 | 104.2 | 50.9 | 53.3 | -5.25 | 57.7 | 63 | 4.4 | 53.3 | 140% | 153% | 7.1 | 0 | 40.8 | 4.4 | 0 | 0 | 5.8 |  | 58 | 1 | 23058 BT Web Filtering - Part 1 FFP 2MS
23121 | 23121 Beyond DC Transformation FFP 1MS | Moreno, Carlos | Awarded | On Hold | Red |  | 2016-07-04 | 2017-07-31 |  | 2017-07-12 | 177% | -52% | -77% | Product Issues | EMEA | ENA-R-CEE | Poland | Cloud |  |  | CLICO SP Z O O-Customer | BEYOND.PL SP. Z O.O.-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 30002 | 0 | 30002 | 25212 | 40455 | -15244 | 0 | 40455 | -15244 | 4790 | -10453 | 17% | -35% | 39496 | -52% | 25212 | 39496 | -14285 | 0 | 39496 | -14285 | 0 | 959 | 0 | -959 | 0 | 0 | 0 | 0 | 36.7 | 36.7 | 65.1 | 0 | -28.405 | 0 | 0 | 11.9 | 0 | 0% | 22% | 0 | 1.4 | 20 | 11.9 | 0 | 14 | 19.3 |  | 66.5 | 1 | 23121 Beyond DC Transformation FFP 1MS
23129 | 23129 Beyond DVT and 3w on-site assistance T&M Consulting 27 days | Moreno, Carlos | Awarded | On Hold | Red |  | 2016-02-11 | 2017-12-28 |  | 2017-07-12 | 3% | 0% | 0% |  | EMEA | ENA-R-CEE | Poland | Cloud |  |  | Juniper | BEYOND.PL SP. Z O.O.-EndUser | Free of Charge | None | Consulting – T & M |  | A | 0 | 0 | 0 | 11000 | 393 | 10607 | 20728 | 21120 | -10120 | -11000 | -21120 | 0% | 0% | 10120 | 0% | 0 | 393 | -393 | 9728 | 10120 | -10120 | 11000 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 27 | 27 | 0.8 | 26.3 | 0 | 0 | 0 | 0.8 | 0 | 0% | 3% | 0 | 9.5 | 0 | 0.8 | 0 | 0 | 0 |  | 10.3 | 1 | 23129 Beyond DVT and 3w on-site assistance T&M Consulting 27 days
23132 | 23132 FASTWEB 6PE - IPV6 evolution - CREDITS REDEMPTION - 69 CREDITS | Masci, Fabio | Awarded | In Progress | Amber |  | 2016-04-18 | 2017-07-31 |  | 2017-06-30 | 121% | 24% | -21% | Customer Issues | EMEA | ENA-R-SOUTH | Italy | Core & Edge |  |  | FASTWEB-Customer | FASTWEB-EndUser | Token/Credit | Milestone Payments | Consulting – Fixed Price Custom |  | B | 138148 | 0 | 138148 | 83301 | 50706 | 32595 | 12760 | 63466 | 19835 | 54847 | 74682 | 30% | 54% | 50706 | 24% | 70541 | 50706 | 19835 | 0 | 50706 | 19835 | 12760 | 0 | 12760 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 48.3 | 0 | -8.25 | 0 | 0 | 14.1 | 0 | 0% | 41% | 0 | 1.4 | 34.1 | 14.1 | 0 | 0 | 0 |  | 49.6 | 1 | 23132 FASTWEB 6PE - IPV6 evolution - CREDITS REDEMPTION - 69 CREDITS
23139 | 23139 Kauai Island Utility Cooperative | Akiyama, Mauricio | Awarded | Booked | Green | 2017-06-29 | 2017-07-24 | 2017-09-30 |  | 2017-07-05 | 0% | 53% | 0% |  | AMER | US TERRITORIES | United States of America | Core & Edge | Security |  | SOS-Hawaii | Kauai Island Utility Cooperative - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 260496 | 0 | 260496 | 162246 | 0 | 162246 | 18200 | 18200 | 144046 | 98250 | 242296 | 40% | 93% | 0 | 53% | 144046 | 0 | 144046 | 0 | 0 | 144046 | 18200 | 0 | 18200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.03125 | 0 | 0 | 0 | 0 | 0% | 133% | 4.3 | 0.1 | 0 | 0 | 0 | 0 | 0 |  | 4.4 |  | 23139 Kauai Island Utility Cooperative
23175 | 23175 TEF FUSION HL3-HL4 qualification (4 heads) | Gil, Jose | Awarded | In Progress | Green |  | 2016-03-01 | 2017-12-15 |  |  | 92% | 0% | 0% |  | EMEA | Spain | Spain | Core & Edge |  |  | TELEFONICA - Customer | TELEFONICA - Customer | None | None | Consulting – Fixed Price Custom |  | A | 0 | 0 | 0 | 1200 | 461141 | -459941 | 39717 | 500858 | -499658 | -1200 | -500858 | 0% | 0% | 499658 | 0% | 0 | 460573 | -460573 | 39085 | 499658 | -499658 | 1200 | 568 | 632 | 0 | 0 | 0 | 0 | 0 | 1080 | 1080 | 995.9 | 84.1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 995.9 | 0 | 0 | 0 | 0 |  | 995.9 | 1 | 23175 TEF FUSION HL3-HL4 qualification (4 heads)
23240 | 23240 FW BNG 2.0 HLD update & DVT for 88 PS CREDITS REDEMPTION | Masci, Fabio | Awarded | In Progress | Green |  | 2017-01-12 | 2017-07-31 |  | 2017-06-30 | 71% | 0% | 0% |  | EMEA | ENA-R-SOUTH | Italy | Core & Edge |  |  | FASTWEB-Customer | FASTWEB-EndUser | PO/Tokens | None |  |  | A | 0 | 0 | 0 | 0 | 60959 | -60959 | 15921 | 76881 | -76881 | 0 | -76881 | 0% | 0% | 71067 | 0% | 0 | 55145 | -55145 | 15921 | 71067 | -71067 | 0 | 5814 | 0 | -5814 | 0 | 0 | 0 | 0 | 87 | 87 | 61.8 | 25.3 | 0 | 0 | 0 | 4.7 | 0 | 0% | 6% | 0 | 7.2 | 49.6 | 4.7 | 0 | 0.5 | 7 |  | 68.9 | 1 | 23240 FW BNG 2.0 HLD update & DVT for 88 PS CREDITS REDEMPTION
23241 | 23241 DT 2016/2017 General Program Management (Volker) INTERNAL | Sauter, Thorsten | Awarded | In Progress | Green |  | 2016-01-01 | 2017-12-31 |  |  |  | 0% | 0% |  | EMEA | DACH | Germany | Core & Edge |  |  | Juniper | DT-EndUser | None | None |  |  | A | 0 | 0 | 0 | 0 | 77297 | -77297 | 0 | 77297 | -77297 | 0 | -77297 | 0% | 0% | 57397 | 0% | 0 | 57397 | -57397 | 0 | 57397 | -57397 | 0 | 19900 | 0 | -19900 | 0 | 0 | 0 | 0 | 0 | 0 | 81.6 | 0 | -81.625 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 81.6 | 0 | 0 | 0 | 0 |  | 81.6 |  | 23241 DT 2016/2017 General Program Management (Volker) INTERNAL
23246 | 23246 Cable & Wireless - Juniper Devices Recertification | Almanza, Henry | Awarded | On Hold | Green | 2015-12-30 | 2017-08-01 | 2018-02-02 | 2018-01-26 | 2017-07-21 | 0% | 35% | 0% | Under/Not Over budget | AMER | CALA | United States of America | Core & Edge |  |  | VOLOGY DATA SYSTEMS-Customer | CABLE & WIRELESS-EndUser | Reclass | Upon Completion | Consulting – Fixed Price Custom |  | B | 51660 | 0 | 51660 | 54208 | 0 | 54208 | 18000 | 18000 | 36208 | -2548 | 33660 | 30% | 65% | 0 | 35% | 36208 | 0 | 36208 | 0 | 0 | 36208 | 18000 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0.1 | -0.0875 | 0 | 0 | 0 | 0 | 0% | 4% | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.1 |  | 23246 Cable & Wireless - Juniper Devices Recertification
23257 | 23257 City of Philadelphia Data Center Move | Jeffries, Stephanie | Awarded | In Progress | Green |  | 2017-06-12 | 2017-08-04 | 2017-09-02 | 2017-07-23 | 39% | -85% | -221% | Under/Not Over budget | AMER | US TERRITORIES | United States of America | Cloud |  |  | TIG-Customer | City of Phildelphia - End User | PO | Monthly in Arrears | Consulting – T & M |  | A | 42713 | 0 | 42713 | 37636 | 23320 | 14316 | 39565 | 62885 | -25249 | 5077 | -20172 | 38% | -47% | 55385 | -85% | 30136 | 23320 | 6816 | 32065 | 55385 | -25249 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 16 | 51.5 | 20.1 | 31.5 | -35.4975 | 0 | 21.8 | 1.8 | 0 | 0% | 74% | 2.4 | 0.8 | 11.8 | 1.8 | 0 | 0 | 6.5 |  | 23.3 | 2 | 23257 City of Philadelphia Data Center Move
23282 | 23282 Sempra Space Automation | Akiyama, Mauricio | Awarded | Booked | Green | 2016-09-23 | 2016-12-05 | 2017-09-30 |  |  | 0% | 38% | 0% |  | AMER | US TERRITORIES | United States of America | Network Automation |  |  | INTEGRATED ARCHIVE SYSTEMS-Customer | SEMPRA ENERGY-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 191700 | 0 | 191700 | 128640 | 0 | 128640 | 55916 | 55916 | 72724 | 63060 | 135784 | 33% | 71% | 45596 | 38% | 118320 | 0 | 118320 | 45596 | 45596 | 72724 | 10320 | 0 | 10320 | 0 | 0 | 0 | 0 | 0 | 63 | 63 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 5.2 | 1.1 | 0 | 0 | 0 | 0 | 0 |  | 6.3 | 1 | 23282 Sempra Space Automation
23300 | 23300 MOD PS Credit options | Hewitt, Mark | Awarded | In Progress | Green | 2016-05-23 | 2016-06-13 | 2016-09-30 |  |  | 22% | 48% | 0% |  | EMEA | UK-I | United Kingdom | Security |  |  | ARROW - Customer | MOD-EndUser | PO | Fully in Advance |  |  | A | 55000 | 55000 | 0 | 30909 | 2539 | 28370 | 8425 | 10964 | 19945 | 24091 | 44036 | 32% | 80% | 10964 | 48% | 30909 | 2539 | 28370 | 8425 | 10964 | 19945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 5.3 | 18.7 | 0 | 0 | 0 | 1.4 | 0 | 0% | 6% | 0.1 | 1 | 3.9 | 1.4 | 0 | 0 | 0 |  | 6.4 | 1 | 23300 MOD PS Credit options
23310 | 23310 STC 2016 IGW Expansion Consolidated FFP 6MS | Qasem, Waleed | Awarded | In Progress | Green | 2016-06-28 | 2016-06-22 | 2017-07-31 |  | 2017-06-01 | 130% | -17% | -30% | Resource Issues | EMEA | MEA | Saudi Arabia | Core & Edge |  |  | ARABIAN INTERNET & COMMUNICATIONS SERVICES COMPANY - Customer | STC - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 1400000 | 948615 | 451385 | 850458 | 400732 | 449726 | 428887 | 829619 | 20839 | 549542 | 570381 | 58% | 41% | 380227 | -17% | 401066 | 380227 | 20839 | 0 | 380227 | 20839 | 72400 | 20505 | 51895 | 0 | 376992 | 0 | 376992 | 0 | 454 | 454 | 591.8 | 0 | -137.75 | 0 | 0 | 145.3 | 0 | 0% | 33% | 4.9 | 23.1 | 446.5 | 145.3 | 0 | 0 | 0 |  | 619.8 | 1 | 23310 STC 2016 IGW Expansion Consolidated FFP 6MS
23337 | 23337 VHA - WA SA Core Redundancy JNA0029 - FFP | Wood, Russell | Awarded | In Progress | Amber | 2016-08-11 | 2016-08-15 | 2017-07-31 |  | 2017-06-28 | 368% | -129% | -268% |  | APAC | ANZ | Australia | Cloud |  |  | VODAFONE GROUP PLC-Customer | VODAFONE NETWORKS PTY LTD-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 176472 | 132612 | 43860 | 126900 | 355404 | -228504 | 0 | 355404 | -228504 | 49572 | -178932 | 28% | -101% | 180435 | -129% | 126900 | 180435 | -53535 | 0 | 180435 | -53535 | 0 | 0 | 0 | 0 | 0 | 174968 | 0 | -174968 | 80 | 80 | 294.8 | 0 | -214.7488 | 0 | 0 | 148.6 | 0 | 0% | 102% | 0 | 5.5 | 146.1 | 148.6 | 0 | 0 | 0 |  | 300.3 | 1 | 23337 VHA - WA SA Core Redundancy JNA0029 - FFP
23339 | 23339 RTA MAG6611 Health Check FFF 1MS | Bhinder, Muhammad Amir Rashid | Awarded | On Hold | Green | 2016-12-12 | 2016-12-29 | 2017-08-31 |  | 2017-07-06 | 19% | 34% | 0% | Under/Not Over budget | EMEA | MEA | UAE | Security |  |  | MINDWARE S.A.-Customer | ROAD & TRANSPORT AUTHORITY-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 6101 | 0 | 6101 | 4029 | 318 | 3711 | 2176 | 2495 | 1534 | 2072 | 3606 | 25% | 59% | 1340 | 34% | 2874 | 318 | 2556 | 1021 | 1340 | 1534 | 1155 | 0 | 1155 | 0 | 0 | 0 | 0 | 0 | 2.6 | 2.6 | 0.5 | 2.1 | 0 | 0 | 0 | 0.5 | 0 | 0% | 24% | 0.4 | 0 | 0 | 0.5 | 0 | 0 | 0 |  | 0.9 | 1 | 23339 RTA MAG6611 Health Check FFF 1MS
23355 | 23355 Bharti - Smart Packet Backbone Design Part1 - FFP | Manohar, Ravindra | Awarded | In Progress | Amber | 2016-06-29 | 2016-07-07 | 2017-06-30 |  | 2017-06-28 | 87% | 36% | -52% | Customer Issues | APAC | India | India | Core & Edge |  |  | IBM-Customer | BHARTI AIRTEL LTD-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 83472 | 53053 | 30419 | 54200 | 21359 | 32841 | 2458 | 23817 | 30383 | 29272 | 59656 | 35% | 71% | 19748 | 36% | 54200 | 17290 | 36910 | 2458 | 19748 | 34452 | 0 | 0 | 0 | 0 | 0 | 4069 | 0 | -4069 | 86 | 131 | 113.9 | 17.1 | -44.9875 | 0 | 12.5 | 45.4 | 0 | 0% | 53% | 0 | 1 | 68.5 | 45.4 | 0 | 0 | 0 |  | 114.9 | 1 | 23355 Bharti - Smart Packet Backbone Design Part1 - FFP
23388 | 23388 Djezzy CR 10 Days Expenses (FOC) | Chouaieb, Mejda | Awarded | In Progress | Green |  | 2016-03-24 | 2017-07-31 |  | 2017-06-30 | 0% | -62% | 0% | Under/Not Over budget | EMEA | ENA-R-SOUTH | Algeria | Core & Edge |  |  | NOKIA CORPORATION-Customer | DJEZZY GSM (ORASCOM TELECOM ALGERIE)-EndUser | Free of Charge | None | Consulting – T & M |  | A | 5500 | 0 | 5500 | 5500 | 2038 | 3462 | 6863 | 8901 | -3401 | 0 | -3401 | 0% | -62% | 3401 | -62% | 0 | 0 | 0 | 3401 | 3401 | -3401 | 5500 | 2038 | 3462 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.6 | 1 | 22439 Djezzy Design Services FFP 2 MS T&M 37 days | 23388 Djezzy CR 10 Days Expenses (FOC)
23424 | 23424 VF PS Architect 2016/2017 - Lorenzo Venturato | Galli, Giuliano | Awarded | In Progress | Green |  | 2016-03-11 | 2017-12-31 |  |  |  | 0% | 0% |  | EMEA | ENA-R-SOUTH | Italy | Core & Edge | Cloud | Security | VODAFONE | VODAFONE-EndUser | None | None | Consulting – T & M |  | A | 0 | 0 | 0 | 0 | 33934 | -33934 | 0 | 33934 | -33934 | 0 | -33934 | 0% | 0% | 33934 | 0% | 0 | 33934 | -33934 | 0 | 33934 | -33934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | -54 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 8.1 | 54 | 0 | 0 | 0 | 0 |  | 62.1 |  | 23424 VF PS Architect 2016/2017 - Lorenzo Venturato
23428 | 23428 MAMPU - 1GOV Managed Gateway Design - FFP | Ang, Soon Aun | Awarded | In Progress | Green | 2017-03-29 | 2017-04-03 | 2017-09-22 |  | 2017-07-21 | 113% | -4% | -13% | Under/Not Over budget | APAC | ASEAN | Malaysia | Security |  |  | ECS HOLDING COMPANY-Customer | MALAYSIAN ADMINISTRATION MODERNISATION AND MANAGEMENT PLANNING UNIT (MAMPU). - EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 86775 | 3709 | 83066 | 67020 | 56604 | 10416 | 14070 | 70674 | -3654 | 19755 | 16101 | 23% | 19% | 55321 | -4% | 52950 | 55321 | -2371 | 0 | 55321 | -2371 | 14070 | 0 | 14070 | 0 | 0 | 1283 | 0 | -1283 | 71 | 71 | 80.1 | 0 | -9.125 | 18.3 | 18.3 | 12.6 | 5.7 | 35% | 30% | 0 | 6 | 63.5 | 12.6 | 0 | 0 | 4 |  | 86.1 | 1 | 23428 MAMPU - 1GOV Managed Gateway Design - FFP
23434 | 23434 STC MSP 2016 Growth (2xTIMs+CSIM+Third Party Vendor) FFP 4MS | Haidarah, Khalil | Awarded | On Hold | Green | 2016-06-22 | 2015-09-01 | 2017-04-30 |  |  |  | 79% | 0% |  | EMEA | MEA | Saudi Arabia | Core & Edge | Juniper Strategic Delivery |  | SAUDI TELECOM COMPANY (STC)-Customer | STC - End User | PO | Monthly in Arrears | Consulting – Fixed Price Custom |  | C | 1474000 | 1252900 | 221100 | 0 | 313820 | -313820 | 0 | 313820 | -313820 | 1474000 | 1160180 | 0% | 79% | 313820 | 79% | 0 | 313820 | -313820 | 0 | 313820 | -313820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 517.8 | 0 | -517.75 | 0 | 0 | 517.8 | 0 | 0% | 0% | 0 | 0 | 0 | 517.8 | 0 | 0 | 0 |  | 517.8 |  | 23434 STC MSP 2016 Growth (2xTIMs+CSIM+Third Party Vendor) FFP 4MS
23437 | 23437 - TD Ameritrade Security Support T&M | Kouzionis, Nicholas | Awarded | On Hold | Green | 2016-05-04 | 2016-05-16 | 2017-09-30 | 2016-11-30 | 2017-07-21 | 62% | 45% | 0% |  | AMER | GLOBAL FINANCIAL SERVICES | United States of America | Security |  |  | FORSYTHE TECHNOLOGY INC-Customer | TD AMERITRADE-EndUser | PO |  | Consulting – T & M |  | A | 61650 | 32625 | 29025 | 39665 | 12804 | 26861 | 901 | 13705 | 25960 | 21985 | 47945 | 33% | 78% | 13705 | 45% | 39665 | 12804 | 26861 | 901 | 13705 | 25960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 16.2 | 9.8 | 0.00125 | 24 | 24 | 5.1 | 19 | 1193% | 1194% | 8.7 | 0 | 11.1 | 5.1 | 0 | 0 | 0 |  | 24.9 | 1 | 23437 - TD Ameritrade Security Support T&M
23445 | 23445 Equinix OSS Automation | Henning, Mark | Awarded | In Progress | Green | 2016-04-22 | 2016-07-25 | 2017-07-21 | 2017-07-26 | 2017-07-14 | 87% | 79% | 0% | Under/Not Over budget | AMER | CLOUD PROVIDERS | United States of America | Network Automation |  |  | EQUINIX, INC.-Customer | EQUINIX-EndUser | PO | Fully in Advance | Consulting – Packaged |  | B | 356400 | 356400 | 0 | 260000 | 3672 | 256328 | 795 | 4467 | 255533 | 96400 | 351933 | 20% | 99% | 4467 | 79% | 260000 | 3672 | 256328 | 795 | 4467 | 255533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 280 | 242.9 | 37.1 | 0.0025 | 0 | 0 | 3.9 | 0 | 0% | 1% | 3 | 0.2 | 239 | 3.9 | 0 | 0 | 0 |  | 246.1 | 1 | 23445 Equinix OSS Automation
23520 | 23520 Orange Poland MD5 implementation plan FFP 1 MS | Subramaniam, Ragunath | Awarded | In Progress | Green | 2016-06-28 | 2016-06-03 | 2017-06-30 |  | 2017-06-19 | 157% | 37% | -57% | Under/Not Over budget | EMEA | France | Poland | Core & Edge |  |  | Orange Poland | Orange Poland-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 33771 | 33771 | 0 | 11022 | 10249 | 773 | 833 | 11082 | -60 | 22749 | 22689 | 30% | 67% | 8442 | 37% | 8382 | 8442 | -60 | 0 | 8442 | -60 | 2640 | 1807 | 833 | 0 | 0 | 0 | 0 | 0 | 8.3 | 8.3 | 13 | 0 | -4.7188 | 0 | 0 | 5.7 | 0 | 0% | 79% | 0.1 | 3.9 | 7.3 | 5.7 | 0 | 0 | 0 |  | 17 | 1 | 23520 Orange Poland MD5 implementation plan FFP 1 MS
23531 | 23531 VZ FFP Northstar Integration and testing | Martin, David | Awarded | In Progress | Amber | 2016-12-07 | 2017-01-02 | 2017-07-28 |  | 2017-07-18 | 147% | -7% | -47% | Resource Issues | AMER | VERIZON | United States of America | Core & Edge |  |  | VERIZON-EndUser | VERIZON-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | B | 320000 | 0 | 320000 | 238000 | 242274 | -4274 | 13168 | 255442 | -17442 | 82000 | 64558 | 27% | 20% | 237442 | -7% | 220000 | 237442 | -17442 | 0 | 237442 | -17442 | 18000 | 4832 | 13168 | 0 | 0 | 0 | 0 | 0 | 147 | 147 | 215.9 | 0 | -68.8512 | 0 | 0 | 0 | 0 | 0% | 0% | 11.7 | 2.9 | 215.9 | 0 | 0 | 0 | 0 |  | 230.4 | 1 | 23531 VZ FFP Northstar Integration and testing
23532 | 23532 Verizon SBR Upgrades V6 to V7 | Stroud, Charlie | Awarded | In Progress | Green | 2016-11-18 | 2017-01-09 | 2017-07-28 |  | 2017-06-29 | 130% | -60% | -30% |  | AMER | VERIZON |  | Core & Edge |  |  | VERIZON COMMUNICATIONS-EndUser | VERIZON COMMUNICATIONS-EndUser | PO |  | Consulting – Fixed Price Custom |  | B | 41920 | 0 | 41920 | 0 | 50294 | -50294 | 0 | 50294 | -50294 | 41920 | -8374 | 40% | -20% | 50294 | -60% | 0 | 50294 | -50294 | 0 | 50294 | -50294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 38.9 | 0 | -8.9288 | 0 | 0 | 12.8 | 0 | 0% | 49% | 0 | 0 | 26.2 | 12.8 | 0 | 0 | 0 |  | 38.9 | 1 | 23532 Verizon SBR Upgrades V6 to V7
23537 | 23537 PT XL - ITDS-Credits 1 - T&M | Henning, Riana | Awarded | In Progress | Green | 2016-04-07 | 2016-04-01 | 2017-10-27 |  | 2017-06-26 | 117% | -58% | -17% | Under/Not Over budget | APAC | ASEAN | Remote | Core & Edge |  |  | PT LINTAS TEKNOLOGI INDONESIA-Customer | PT EXCELCOMINDO PRATAMA-EndUser | PO | Upon Completion | Consulting – T & M |  | A | 31500 | 0 | 31500 | 16800 | 35077 | -18277 | 0 | 35077 | -18277 | 14700 | -3577 | 47% | -11% | 2880 | -58% | 16800 | 2880 | 13920 | 0 | 2880 | 13920 | 0 | 0 | 0 | 0 | 0 | 32196 | 0 | -32196 | 21 | 21 | 24.6 | 0 | -3.625 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 8.5 | 24.6 | 0 | 0 | 0 | 0 |  | 33.1 | 1 | 23537 PT XL - ITDS-Credits 1 - T&M
23557 | 23557 ATOS MPLS Assistance T&M Consulting 4 days (Remote) | M, Rahimunnisa | Awarded | Booked | Green | 2017-06-30 | 2017-07-24 | 2017-07-27 |  | 2017-07-20 |  | 45% | 0% |  | EMEA | ENA-R-SOUTH | France | Core & Edge |  |  | TECHACCESS - Customer | ATOS INTERNATIONAL-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 11700 | 0 | 11700 | 6070 | 960 | 5110 | 0 | 960 | 5110 | 5630 | 10740 | 47% | 92% | 960 | 45% | 6070 | 960 | 5110 | 0 | 960 | 5110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | -1.125 | 0 | 0 | 0.1 | 0 | 0% | 13% | 0 | 0 | 1 | 0.1 | 0 | 0 | 0 |  | 1.1 |  | 23557 ATOS MPLS Assistance T&M Consulting 4 days (Remote)
23613 | 23613 VZW FFP vJSA for 76 sites | Stroud, Charlie | Awarded | In Progress | Green | 2016-12-16 | 2016-10-17 | 2017-07-28 |  |  | 234% | -51% | -134% |  | AMER | VERIZON | United States of America | Cloud |  |  | VERIZON WIRELESS-EndUser | VERIZON WIRELESS-EndUser | PO |  | Install Custom |  | B | 145700 | 0 | 145700 | 119016 | 187518 | -68502 | 3892 | 191409 | -72393 | 26684 | -45709 | 20% | -31% | 183109 | -51% | 110716 | 183109 | -72393 | 0 | 183109 | -72393 | 8300 | 4408 | 3892 | 0 | 0 | 0 | 0 | 0 | 72 | 72 | 168.3 | 0 | -96.2138 | 0 | 0 | 43.4 | 0 | 0% | 35% | 9.7 | 0 | 124.9 | 43.4 | 0 | 0 | 0 |  | 177.9 | 1 | 23613 VZW FFP vJSA for 76 sites
23614 | 23614 PTCL IP Core Resiliency & Ufone Synergy FFP 3MS | Bhinder, Muhammad Amir Rashid | Awarded | In Progress | Green | 2016-12-16 | 2016-12-28 | 2017-08-31 |  | 2017-07-06 | 90% | 22% | 0% | Under/Not Over budget | EMEA | MEA | Pakistan | Core & Edge |  |  | PREMIER SYSTEMS-Customer | PTCL-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 85000 | 59457 | 25543 | 55188 | 35100 | 20088 | 10210 | 45310 | 9878 | 29812 | 39690 | 25% | 47% | 35181 | 22% | 45059 | 35100 | 9959 | 81 | 35181 | 9878 | 10129 | 0 | 10129 | 0 | 0 | 0 | 0 | 0 | 41.2 | 41.2 | 36.9 | 4.3 | 0 | 0 | 0 | 5.7 | 0 | 0% | 16% | 2.6 | 1.6 | 31.2 | 5.7 | 0 | 0 | 0 |  | 41.1 | 1 | 23614 PTCL IP Core Resiliency & Ufone Synergy FFP 3MS
23616 | 23616 DT SecGW refresh FFP 22 MS | Chouaieb, Mejda | Awarded | In Progress | Green | 2016-09-28 | 2016-10-03 | 2017-12-29 |  | 2017-06-30 | 100% | 19% | 0% | Product Issues | EMEA | DACH | Germany | Security |  |  | DEUTSCHE TELEKOM-Customer | DT-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 493761 | 487317 | 6444 | 125304 | 190951 | -65647 | 36089 | 227040 | -101736 | 368457 | 266721 | 35% | 54% | 184295 | 19% | 82559 | 184295 | -101736 | 0 | 184295 | -101736 | 21285 | 6656 | 14629 | 0 | 21460 | 0 | 21460 | 0 | 224 | 224 | 224.7 | 0 | -0.6875 | 0 | 0 | 77.1 | 0 | 0% | 52% | 12 | 10.1 | 131.9 | 77.1 | 0 | 0 | 15.8 |  | 246.8 | 1 | 23616 DT SecGW refresh FFP 22 MS
23629 | 23629 BSNL - M to MX Migration - FFP | Manohar, Ravindra | Awarded | In Progress | Green | 2017-06-26 | 2017-07-03 | 2017-12-30 |  | 2017-06-27 |  | -31% | 0% |  | APAC | India | India | Core & Edge |  |  | INSPIRA ENTERPRISE INDIA PVT. LTD.-Customer | MINISTRY OF COMMUNICATION AND INFORMATION TECHNOLOGY - Enduser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 106000 | 0 | 106000 | 73560 | 18161 | 55399 |  |  |  | 32440 |  | 31% | 0% |  | -31% | 73560 | 0 | 73560 |  |  |  | 0 | 0 | 0 | 0 | 0 | 18161 | 0 | -18161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 23629 BSNL - M to MX Migration - FFP
23642 | 23642 Telefonica Soluciones Security Director FFP 2 MS | Moreno, Carlos | Awarded | On Hold | Amber | 2017-01-23 | 2017-01-23 | 2017-06-30 |  | 2017-07-12 | 127% | 3% | -27% | Customer Issues | EMEA | Spain | Spain | Security |  |  | TELEFONICA SOLUCIONES DE INF Y COM DE E-EndUser | Junta Extremadura-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 17739 | 0 | 17739 | 11678 | 10133 | 1545 | 2708 | 12842 | -1164 | 6061 | 4897 | 25% | 28% | 9722 | 3% | 8558 | 9722 | -1164 | 0 | 9722 | -1164 | 3120 | 412 | 2708 | 0 | 0 | 0 | 0 | 0 | 10.2 | 10.2 | 13 | 0 | -2.8 | 0 | 0 | 4.9 | 0 | 0% | 60% | 1.4 | 1.3 | 8.1 | 4.9 | 0 | 0 | 0 |  | 15.6 | 1 | 23642 Telefonica Soluciones Security Director FFP 2 MS
23651 | 23651 DHL Security Audit Project FFP 2MS | Foster, David | Awarded | On Hold | Green | 2016-08-23 | 2016-08-25 | 2017-08-31 |  | 2017-06-30 | 26% | 48% | 0% | Under/Not Over budget | EMEA | ENA-R-CEE | Czech Republic | Security |  |  | ARROW - Customer | DHL-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 41018 | 32572 | 8446 | 26056 | 5131 | 20925 | 5369 | 10500 | 15556 | 14962 | 30518 | 26% | 74% | 7060 | 48% | 22616 | 2473 | 20143 | 4587 | 7060 | 15556 | 3440 | 2658 | 782 | 0 | 0 | 0 | 0 | 0 | 22 | 22 | 5.8 | 16.3 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 1.6 | 4.4 | 5.8 | 0 | 0 | 0 | 0 |  | 11.7 | 1 | 23651 DHL Security Audit Project FFP 2MS
23701 | 23701 SFO 100 PS Credits | Jeffries, Stephanie | Awarded | In Progress | Green | 2016-10-19 | 2016-11-22 | 2017-10-17 |  | 2017-05-22 | 156% | 38% | -238% | Scoping Issues | AMER | US TERRITORIES | United States of America | Security |  |  | INTERVISION SYSTEMS TECHNOLOGIES, INC.-Customer | SAN FRANCISCO INTERNATIONAL AIRPORT-EndUser | Token/Credit | Milestone Payments | Consulting – Fixed Price Custom |  | A | 187000 | 187000 | 0 | 74800 | 41192 | 33609 | 0 | 41192 | 33609 | 112200 | 145809 | 40% | 78% | 41192 | 38% | 74800 | 41192 | 33609 | 0 | 41192 | 33609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 24 | 37.4 | 0 | -26.3325 | 0 | 5 | 7 | 0 | 0% | 23% | 6.2 | 0.6 | 30.4 | 7 | 0 | 0 | 0 |  | 44.1 | 1 | 23701 SFO 100 PS Credits
23728 | 23728 Telefonica ISG to SRX migration FFP 2 MS | Moreno, Carlos | Awarded | On Hold | Amber | 2017-01-23 | 2017-01-25 | 2017-06-30 |  | 2017-07-12 | 44% | 31% | 0% | Resource Issues | EMEA | Spain | Spain | Security |  |  | TELEFONICA SOLUCIONES DE INF Y COM DE E-EndUser | JUNTA DE EXTREMADURA - END USER | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 16904 | 0 | 16904 | 10611 | 1982 | 8629 | 4867 | 6849 | 3762 | 6293 | 10055 | 28% | 59% | 4449 | 31% | 8211 | 1982 | 6229 | 2467 | 4449 | 3762 | 2400 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 8.1 | 8.1 | 3.6 | 4.5 | 0 | 0 | 0 | 3.6 | 0 | 0% | 79% | 0.3 | 0 | 0 | 3.6 | 0 | 0 | 0 |  | 3.8 | 1 | 23728 Telefonica ISG to SRX migration FFP 2 MS
23734 | 23734 Orange CIT T&M 5 Days | Ferrari, Lenora | Awarded | On Hold | Green | 2016-09-27 |  |  |  | 2017-06-29 |  | 99% | 0% |  | EMEA | ENA-R-SOUTH | Cote D'Ivoire | Core & Edge |  |  | WESTCON GROUP EUROPEAN OPERATIONS | ORANGE-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 18850 | 0 | 18850 | 0 | 106 | -106 | 0 | 106 | -106 | 18850 | 18744 | 0% | 99% | 106 | 99% | 0 | 106 | -106 | 0 | 106 | -106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | -0.25 | 0 | 0 | 0.3 | 0 | 0% | 0% | 0.2 | 0 | 0 | 0.3 | 0 | 0 | 0 |  | 0.4 |  | 23734 Orange CIT T&M 5 Days
23739 | 23739 MGM - Cotai DNI Solution - FFP | Jacobs, Christo | Awarded | In Progress | Amber | 2016-05-19 | 2016-05-01 | 2017-12-29 |  | 2017-07-21 | 64% | -48% | -40% | Scoping Issues | APAC | Greater China | Macau | Cloud |  |  | VODATEL HOLDINGS LTD-Customer | MGM GRAND PARADISE LIMITED-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 238269 | 100349 | 137920 | 182529 | 228049 | -45520 | 68432 | 296481 | -113953 | 55740 | -58213 | 23% | -24% | 89516 | -48% | 144900 | 58712 | 86188 | 30804 | 89516 | 55384 | 37629 | 0 | 37629 | 0 | 0 | 169337 | 0 | -169337 | 161 | 225 | 144.3 | 80.8 | -64 | 17.6 | 44.5 | 36 | 0 | 12% | 25% | 0 | 4 | 77 | 36 | 0 | 1.3 | 30 |  | 148.3 | 2 | 23739 MGM - Cotai DNI Solution - FFP
23740 | 23740 Oracle CCL | Cicatello, James | Awarded | In Progress | Green | 2016-07-15 | 2016-07-15 | 2017-07-14 | 2017-07-19 | 2017-07-19 | 66% | 40% | 0% | Under/Not Over budget | AMER | CLOUD PROVIDERS | United States of America | Juniper Strategic Delivery |  |  | DIMENSION DATA NORTH AMERICA INC.-EndUser | ORACLE CORP-EndUser | PO/Reclass | Fully in Advance | Consulting – Fixed Price Custom |  | B | 423353 | 423353 | 0 | 304651 | 101768 | 202883 | 63840 | 165607 | 139043 | 118703 | 257746 | 21% | 61% | 153301 | 40% | 292344 | 101768 | 190576 | 51533 | 153301 | 139043 | 0 | 0 | 0 | 0 | 12307 | 12307 | 12307 | -12307 | 365 | 365 | 241.6 | 123.4 | 0.0025 | 0 | 0 | 11.8 | 0 | 0% | 3% | 0.5 | 0.4 | 229.9 | 11.8 | 0 | 0 | 0 |  | 242.5 | 2 | 23740 Oracle CCL
23744 | 23744 ORANGE SENEGAL Sonatel BNG SBR FFP 7MS | Ferrari, Lenora | Awarded | In Progress | Red | 2016-09-08 | 2016-08-29 | 2017-06-30 |  | 2017-06-21 | 68% | 9% | -43% | Customer Issues | EMEA | ENA-R-SOUTH | Senegal | Core & Edge |  |  | INTERDATA - Customer | SONATEL-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 194510 | 48929 | 145581 | 150683 | 92054 | 58629 | 40397 | 132451 | 18232 | 43827 | 62059 | 23% | 32% | 103125 | 9% | 121357 | 72907 | 48450 | 30218 | 103125 | 18232 | 21780 | 12277 | 9503 | 0 | 7546 | 6870 | 676 | 0 | 100.4 | 143.3 | 96.9 | 46.4 | -42.85 | 0 | 0 | 25.9 | 0 | 0% | 22% | 0.4 | 6.4 | 63.6 | 25.9 | 0 | 6.9 | 0.5 |  | 103.6 | 1 | 23744 ORANGE SENEGAL Sonatel BNG SBR FFP 7MS
23791 | 23791 Telecom Slovenia T&M Consulting 5 Days Onsite | M, Rahimunnisa | Awarded | On Hold | Green | 2016-11-18 | 2017-06-07 | 2017-08-31 | 2017-12-07 | 2017-06-21 | 66% | 25% | 0% | Customer Issues | EMEA | ENA-R-CEE | Slovenia | Security |  |  | DSC d.o.o. | TELECOM SLOVENIA - ENDUSER | PO | Fully in Advance | Consulting – T & M |  | A | 17050 | 17050 | 0 | 10338 | 2947 | 7391 | 3108 | 6055 | 4283 | 6712 | 10995 | 39% | 64% | 3305 | 25% | 7588 | 2247 | 5341 | 1058 | 3305 | 4283 | 2750 | 700 | 2050 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 3.3 | 1.7 | 0 | 0 | 0 | 1.6 | 0 | 0% | 45% | 0.1 | 0 | 1.8 | 1.6 | 0 | 0 | 0 |  | 3.4 | 1 | 23791 Telecom Slovenia T&M Consulting 5 Days Onsite
23797 | 23797 Zalando SRX Migration T&M 11 days | Subramaniam, Ragunath | Awarded | In Progress | Green | 2016-12-14 | 2016-12-15 | 2017-06-15 |  | 2017-06-19 | 67% | 30% | 0% |  | EMEA | DACH | Germany | Security |  |  | WESTCON-Customer | Zalando-End User | PO | Fully in Advance | Consulting – T & M |  | B | 29475 | 29475 | 0 | 18943 | 7387 | 11556 | 2744 | 10131 | 8812 | 10532 | 19344 | 36% | 66% | 7881 | 30% | 16693 | 6042 | 10651 | 1839 | 7881 | 8812 | 2250 | 1344 | 906 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 7.4 | 3.6 | 0 | 0 | 0 | 1.7 | 0 | 0% | 18% | 0 | 1.4 | 5.8 | 1.7 | 0 | 0 | 0 |  | 8.8 | 1 | 23797 Zalando SRX Migration T&M 11 days
23828 | 23828 Orange SB ACX Scenario 20 Barcelona FFP 1 MS | Oliver, Juan | Awarded | Complete | Green | 2016-05-30 | 2016-06-30 | 2016-11-30 |  |  | 71% | 12% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 8036 | 8036 | 0 | 0 | 5110 | -5110 | 354 | 5465 | -5465 | 8036 | 2572 | 20% | 32% | 1358 | 12% | 0 | 1004 | -1004 | 354 | 1358 | -1358 | 0 | 0 | 0 | 0 | 0 | 4107 | 0 | -4107 | 3 | 3 | 2.1 | 0.9 | 0 | 0 | 0 | 2.1 | 0 | 0% | 243% | 0.1 | 0 | 0 | 2.1 | 0 | 0 | 0 |  | 2.3 | 1 | 23828 Orange SB ACX Scenario 20 Barcelona FFP 1 MS
23829 | 23829 Orange SB ACX Scenario 31 Viladecans FFP 1 MS | Oliver, Juan | Awarded | Complete | Green | 2016-06-14 | 2016-07-18 | 2016-10-31 |  |  | 33% | 17% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 9110 | 0 | 9110 | 20 | 5346 | -5326 | 433 | 5780 | -5760 | 9090 | 3330 | 20% | 37% | 886 | 17% | 0 | 472 | -472 | 413 | 886 | -886 | 20 | 0 | 20 | 0 | 0 | 4874 | 0 | -4874 | 3 | 3 | 1 | 2 | 0 | 0 | 0 | 0.8 | 0 | 0% | 33% | 1.1 | 0 | 0.3 | 0.8 | 0 | 0 | 0 |  | 2.1 | 1 | 23829 Orange SB ACX Scenario 31 Viladecans FFP 1 MS
23831 | 23831 Telefonica Peru 1 Year PS Consultant | Barbieri De Sousa, Alexandre | Awarded | In Progress | Green | 2016-09-09 | 2016-09-12 | 2017-09-12 |  |  | 7% | -9% | 0% |  | AMER | CALA | Peru | Core & Edge |  |  | NEC CORPORATION-Customer | TELEFONICA PERU-EndUser | PO |  | Consulting – Fixed Price Custom |  | B | 120000 | 0 | 120000 | 0 | 94669 | -94669 | 0 | 94669 | -94669 | 120000 | 25331 | 30% | 21% | 0 | -9% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94669 | 0 | -94669 | 365.1 | 365 | 24.6 | 340.4 | 0.085 | 0 | 0 | 0.9 | 0 | 0% | 0% | 0.9 | 0 | 23.8 | 0.9 | 0 | 0 | 0 |  | 25.5 | 1 | 23831 Telefonica Peru 1 Year PS Consultant
23836 | 23836 STC KSA PS Consultancy (STC NCDI Security) T&M 170 Days RECLASS | Bin Sabbar, Abdullah | Awarded | In Progress | Green | 2016-06-24 | 2017-01-01 | 2017-12-31 |  |  | 99% | 0% | 0% |  | EMEA | MEA | Saudi Arabia | Core & Edge |  |  | ARABIAN INTERNET & COMMUNICATIONS SERVICES COMPANY - Customer | STC - End User | Reclass | None | Consulting – T & M |  | A | 0 | 0 | 0 | 202450 | 116725 | 85725 | 35000 | 151725 | 50725 | -202450 | -151725 | 0% | 0% | 116725 | 0% | 167450 | 116725 | 50725 | 0 | 116725 | 50725 | 35000 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 170 | 170 | 168 | 2 | 0 | 0 | 0 | 40.9 | 0 | 0% | 32% | 0 | 3 | 127.1 | 40.9 | 0 | 0 | 0 |  | 171 | 1 | 23836 STC KSA PS Consultancy (STC NCDI Security) T&M 170 Days RECLASS
23886 | 23886 Orange SB ACX Scenario 8 EVERIS Sede Diagonal 561 BCN FFP 1 MS | Oliver, Juan | Awarded | Complete | Green | 2016-06-23 | 2016-07-10 | 2016-09-30 |  |  | 42% | 23% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 3262 | 0 | 3262 | 0 | 1223 | -1223 | 648 | 1871 | -1871 | 3262 | 1391 | 20% | 43% | 1111 | 23% | 0 | 463 | -463 | 648 | 1111 | -1111 | 0 | 0 | 0 | 0 | 0 | 760 | 0 | -760 | 3 | 3 | 1.3 | 1.8 | 0 | 0 | 0 | 0.5 | 0 | 0% | 20% | 0 | 0 | 0.8 | 0.5 | 0 | 0 | 0 |  | 1.3 | 1 | 23886 Orange SB ACX Scenario 8 EVERIS Sede Diagonal 561 BCN FFP 1 MS
23887 | 23887 Orange SB ACX Scenario 8 EVERIS Sede Entença 319 BCN FFP 1 MS | Oliver, Juan | Awarded | Complete | Green | 2016-06-13 | 2016-07-10 | 2016-09-30 |  |  | 63% | 13% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 3262 | 0 | 3262 | 0 | 1646 | -1646 | 531 | 2177 | -2177 | 3262 | 1084 | 20% | 33% | 1417 | 13% | 0 | 886 | -886 | 531 | 1417 | -1417 | 0 | 0 | 0 | 0 | 0 | 760 | 0 | -760 | 3 | 3 | 1.9 | 1.1 | 0 | 0 | 0 | 1.9 | 0 | 0% | 167% | 0 | 0 | 0 | 1.9 | 0 | 0 | 0 |  | 1.9 | 1 | 23887 Orange SB ACX Scenario 8 EVERIS Sede Entença 319 BCN FFP 1 MS
23888 | 23888 Orange SB ACX Scenario 8 EVERIS Sede Nicaragua 48 BCN FFP 1 MS | Oliver, Juan | Awarded | Complete | Green | 2016-06-13 | 2016-07-10 | 2016-09-30 |  |  | 58% | -16% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 3262 | 0 | 3262 | 0 | 2545 | -2545 | 591 | 3136 | -3136 | 3262 | 126 | 20% | 4% | 1417 | -16% | 0 | 827 | -827 | 591 | 1417 | -1417 | 0 | 0 | 0 | 0 | 0 | 1718 | 0 | -1718 | 3 | 3 | 1.8 | 1.3 | 0 | 0 | 0 | 1.8 | 0 | 0% | 140% | 0 | 0 | 0 | 1.8 | 0 | 0 | 0 |  | 1.8 | 1 | 23888 Orange SB ACX Scenario 8 EVERIS Sede Nicaragua 48 BCN FFP 1 MS
23912 | 23912 RTA additional Nwk Implementation Review Reports/Audits FFP 2MS | Bhinder, Muhammad Amir Rashid | Awarded | In Progress | Green | 2016-12-31 | 2016-06-02 | 2017-07-31 |  | 2017-07-06 | 85% | 33% | 0% | Under/Not Over budget | EMEA | MEA | UAE | Security |  |  | MINDWARE S.A.-Customer | RTA-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 41184 | 20592 | 20592 | 26607 | 11483 | 15124 | 5855 | 17338 | 9269 | 14577 | 23846 | 25% | 58% | 13266 | 33% | 22535 | 11483 | 11052 | 1783 | 13266 | 9269 | 4072 | 0 | 4072 | 0 | 0 | 0 | 0 | 0 | 21 | 21 | 17.8 | 3.2 | 0 | 0 | 0 | 4.4 | 0 | 0% | 27% | 0.3 | 0.2 | 13.4 | 4.4 | 0 | 0 | 0 |  | 18.3 | 1 | 23912 RTA additional Nwk Implementation Review Reports/Audits FFP 2MS
23913 | 23913 FASTWEB SMDF RFQ FFP 4 MS | Masci, Fabio | Awarded | In Progress | Green | 2017-03-14 | 2017-02-01 | 2017-08-31 |  | 2017-06-30 | 36% | 29% | 0% |  | EMEA | ENA-R-SOUTH | Italy | Core & Edge |  |  | SIRTI - Customer | FASTWEB S.P.A.-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 186470 | 89380 | 97090 | 114120 | 23853 | 90267 | 52737 | 76590 | 37530 | 72350 | 109880 | 30% | 59% | 48830 | 29% | 86360 | 21149 | 65211 | 27681 | 48830 | 37530 | 27760 | 2704 | 25056 | 0 | 0 | 0 | 0 | 0 | 67 | 67 | 23.9 | 43.1 | 0 | 0 | 0 | 2.9 | 0 | 0% | 4% | 4.7 | 6.4 | 18.5 | 2.9 | 0 | 0 | 2.6 |  | 35 | 1 | 23913 FASTWEB SMDF RFQ FFP 4 MS
23935 | 23935 UKRTELECOM Core Network Wandl Assessment and HLD FFP 2MS | Bakhmutov, Alexey Vladimirovich | Awarded | On Hold | Green | 2016-08-02 | 2016-12-05 | 2017-09-29 |  |  | 2% | 32% | 0% | Under/Not Over budget | EMEA | ENA-R-RCIS | Ukraine | Core & Edge |  |  | TECHNOSERV | UKRAINE TELECOM-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 59789 | 0 | 59789 | 36505 | 445 | 36060 | 22298 | 22743 | 13762 | 23284 | 37046 | 30% | 62% | 14383 | 32% | 28145 | 445 | 27700 | 13938 | 14383 | 13762 | 8360 | 0 | 8360 | 0 | 0 | 0 | 0 | 0 | 47.5 | 47.5 | 1.2 | 46.3 | 0 | 0 | 0 | 0.4 | 0 | 0% | 1% | 3 | 0 | 0.8 | 0.4 | 0 | 0 | 0 |  | 4.2 | 1 | 23935 UKRTELECOM Core Network Wandl Assessment and HLD FFP 2MS
23936 | 23936 OBS Contrail T&M 5 Days | M, Rahimunnisa | Awarded | On Hold | Green | 2016-09-09 | 2016-10-03 | 2017-08-31 | 2017-07-31 | 2017-06-21 | 86% | 13% | 0% | Customer Issues | EMEA | France | France | SDN |  |  | WESTCON GROUP EUROPEAN OPERATIONS | ORANGE BUSINESS SERVICES-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 14500 | 14500 | 0 | 8544 | 3473 | 5071 | 3185 | 6658 | 1886 | 5956 | 7842 | 41% | 54% | 3845 | 13% | 5731 | 3473 | 2258 | 372 | 3845 | 1886 | 2813 | 0 | 2813 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 4.3 | 0.7 | 0 | 0 | 0 | 1.1 | 0 | 0% | 27% | 0.2 | 0 | 3.3 | 1.1 | 0 | 0 | 0 |  | 4.5 | 1 | 23936 OBS Contrail T&M 5 Days
23941 | 23941 Orange Poland T&M 26 Days (5 by JNPR 21 by COMP) | M, Rahimunnisa | Awarded | On Hold | Green | 2016-08-31 |  | 2017-08-31 |  | 2017-06-23 | 6% | -15% | 0% |  | EMEA | ENA-R-SOUTH | Poland | Network Automation |  |  | Orange Poland | Orange Poland-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 16200 | 0 | 16200 | 11855 | 660 | 11195 | 13759 | 14419 | -2564 | 4345 | 1781 | 26% | 11% | 11669 | -15% | 9105 | 660 | 8445 | 11009 | 11669 | -2564 | 2750 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 1.6 | 24.4 | 0 | 0 | 0 | 1.6 | 0 | 0% | 6% | 0.2 | 0 | 0 | 1.6 | 0 | 0 | 0 |  | 1.8 | 1 | 23941 Orange Poland T&M 26 Days (5 by JNPR 21 by COMP)
23944 | 23944 STC KSA PS Consultancy (STC NCDI Security 2) T&M 170 Days RECLASS | Bin Sabbar, Abdullah | Awarded | In Progress | Amber | 2016-06-24 | 2016-10-01 | 2017-09-30 |  | 2017-07-06 | 33% | 0% | 0% |  | EMEA | MEA | Saudi Arabia | Security |  |  | ARABIAN INTERNET & COMMUNICATIONS SERVICES COMPANY - Customer | STC - End User | Reclass | None | Consulting – T & M |  | A | 0 | 0 | 0 | 0 | 43984 | -43984 | 88317 | 132300 | -132300 | 0 | -132300 | 0% | 0% | 132300 | 0% | 0 | 43984 | -43984 | 88317 | 132300 | -132300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 170 | 56.7 | 113.3 | 0 | 0 | 0 | 21.1 | 0 | 0% | 14% | 0 | 0 | 35.6 | 21.1 | 0 | 0 | 0 |  | 56.7 | 1 | 23944 STC KSA PS Consultancy (STC NCDI Security 2) T&M 170 Days RECLASS
23963 | 23963 Telefonica Germany Atos DC EVPN FFP 4MS - Q3 16 offer | Ferrari, Lenora | Awarded | In Progress | Amber | 2016-10-19 | 2016-10-19 | 2017-06-30 |  | 2017-06-29 | 90% | 29% | 0% | Customer Issues | EMEA | Spain | Germany | Cloud |  |  | ATOS Origin-Customer | TELEFONICA GERMANY GMBH & CO. OHG-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 108178 | 108178 | 0 | 71454 | 42369 | 29085 | 12736 | 55105 | 16349 | 36724 | 53073 | 20% | 49% | 41685 | 29% | 58034 | 41685 | 16349 | 0 | 41685 | 16349 | 13420 | 684 | 12736 | 0 | 0 | 0 | 0 | 0 | 66 | 66 | 59.5 | 6.5 | 0 | 0 | 0 | 15.8 | 0 | 0% | 31% | 0.8 | 5.8 | 43.8 | 15.8 | 0 | 0 | 0 |  | 66.1 | 1 | 23744 ORANGE SENEGAL Sonatel BNG SBR FFP 7MS | 24172 Meditel FUN2 SRX RFQ FFP 7 MS + T&M 30 days | 23963 Telefonica Germany Atos DC EVPN FFP 4MS - Q3 16 offer
23965 | 23965 Swisscom MX Testing T&M 58 days | Subramaniam, Ragunath | Awarded | In Progress | Green | 2016-06-21 | 2016-08-02 | 2017-08-02 |  | 2017-06-19 | 55% | -18% | 0% |  | EMEA | ENA-R-CEE | Switzerland | Core & Edge |  |  | Swisscom-Customer | SWISSCOM AG-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 141375 | 141375 | 0 | 67886 | 39204 | 28682 | 42877 | 82082 | -14196 | 73489 | 59293 | 60% | 42% | 70768 | -18% | 56572 | 39204 | 17368 | 31563 | 70768 | -14196 | 11314 | 0 | 11314 | 0 | 0 | 0 | 0 | 0 | 58 | 58 | 32.1 | 25.9 | 0 | 0 | 0 | 3.3 | 0 | 0% | 6% | 0 | 0 | 28.8 | 3.3 | 0 | 0 | 0 |  | 32.1 | 1 | 23965 Swisscom MX Testing T&M 58 days
23991 | 23991 OSP TM 5 D | Oliver, Juan | Awarded | In Progress | Green | 2017-03-09 | 2016-12-08 | 2017-06-30 |  |  | 20% | 10% | -100% |  | EMEA | France | Spain | Core & Edge |  |  | ORANGE SPAIN | ORANGE-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 11580 | 11580 | 0 | 7588 | 1113 | 6475 | 4452 | 5565 | 2023 | 3992 | 6015 | 42% | 52% | 5565 | 10% | 7588 | 1113 | 6475 | 4452 | 5565 | 2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 2 | 8 | -5 | 0 | 0.5 | 2 | 0 | 0% | 25% | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 2 | 1 | 23991 OSP TM 5 D
23994 | 23994 Orange SB ACX Scenario 31 Alcobendas FFP 2 MS | Oliver, Juan | Awarded | Complete | Green | 2016-06-06 | 2016-06-30 | 2016-07-31 |  |  | 88% | 43% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 16696 | 16696 | 0 | 0 | 6050 | -6050 | 173 | 6223 | -6223 | 16696 | 10474 | 20% | 63% | 1385 | 43% | 0 | 1212 | -1212 | 173 | 1385 | -1385 | 0 | 0 | 0 | 0 | 0 | 4838 | 0 | -4838 | 3 | 3 | 2.6 | 0.4 | 0 | 0 | 0 | 2.6 | 0 | 0% | 700% | 0 | 0 | 0 | 2.6 | 0 | 0 | 0 |  | 2.6 | 1 | 23994 Orange SB ACX Scenario 31 Alcobendas FFP 2 MS
24002 | 24002 Telefonica Brazil Core Multicast | Barbieri De Sousa, Alexandre | Awarded | In Progress | Green | 2016-10-01 | 2016-10-10 | 2017-09-29 |  |  | 1228% | -41% | -13% |  | AMER | CALA | Brazil | Core & Edge |  |  | NEC CORPORATION-Customer | TELEFONICA BRAZIL-EndUser | PO |  | Consulting – Fixed Price Custom |  | B | 75000 | 0 | 75000 | 0 | 83597 | -83597 | 0 | 83597 | -83597 | 75000 | -8597 | 30% | -11% | 83597 | -41% | 0 | 83597 | -83597 | 0 | 83597 | -83597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.1 | 6 | 73.8 | 0 | -8.6587 | 0 | 1 | 25.8 | 0 | 0% | 54% | 15 | 0 | 48 | 25.8 | 0 | 0 | 0 |  | 88.8 | 1 | 24002 Telefonica Brazil Core Multicast
24003 | 24003 STC JSD Network Planning Serv (Renewal 22549) FFP 1MS RECLASS | Bin Sabbar, Abdullah | Awarded | Booked | Green | 2016-06-24 | 2017-01-01 | 2017-12-31 |  | 2017-06-22 |  | -35% | 0% | Under/Not Over budget | EMEA | MEA | Saudi Arabia | Juniper Strategic Delivery |  |  | ARABIAN INTERNET & COMMUNICATIONS SERVICES COMPANY - Customer | STC - End User | Reclass | None | Consulting – Fixed Price Custom |  | C | 0 | 0 | 0 | 250000 | 16117 | 233883 | 250000 | 266117 | -16117 | -250000 | -266117 | 35% | 0% | 16117 | -35% | 0 | 16117 | -16117 | 0 | 16117 | -16117 | 0 | 0 | 0 | 0 | 250000 | 0 | 250000 | 0 | 0 | 0 | 20 | 0 | -20 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 20 | 0 | 0 | 0 | 0 |  | 20 |  | 24003 STC JSD Network Planning Serv (Renewal 22549) FFP 1MS RECLASS
24005 | 24005 LA Poste T&M 10 Days | M, Rahimunnisa | Awarded | On Hold | Green | 2016-07-15 | 2016-11-01 | 2017-06-30 | 2017-08-31 | 2017-06-23 | 54% | -15% | 0% |  | EMEA | France | France | Security |  |  | BT GROUP PLC-Customer | LA POSTE-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 40000 | 40000 | 0 | 0 | 3324 | -3324 | 2770 | 6094 | -6094 | 40000 | 33906 | 100% | 85% | 6094 | -15% | 0 | 3324 | -3324 | 2770 | 6094 | -6094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 5.4 | 4.6 | 0 | 0 | 0 | 3.3 | 0 | 0% | 48% | 0.1 | 0 | 2.1 | 3.3 | 0 | 0 | 0 |  | 5.5 | 1 | 24005 LA Poste T&M 10 Days
24007 | 24007 SNCF T&M 35 Days | Subramaniam, Ragunath | Awarded | In Progress | Green | 2016-06-30 | 2016-09-15 | 2017-07-16 |  | 2017-06-19 | 89% | 14% | 0% |  | EMEA | France | France | Core & Edge |  |  | OBS-Partner | SNCF | PO | Fully in Advance | Consulting – T & M |  | A | 120896 | 120896 | 0 | 64328 | 21490 | 42838 | 26319 | 47809 | 16519 | 56568 | 73087 | 47% | 60% | 23600 | 14% | 40119 | 21490 | 18629 | 2110 | 23600 | 16519 | 24209 | 0 | 24209 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 31.2 | 3.8 | 0 | 0 | 0 | 4.2 | 0 | 0% | 14% | 0 | 0.8 | 27 | 4.2 | 0 | 0 | 0 |  | 31.9 | 1 | 24007 SNCF T&M 35 Days
24020 | 24020 DT One Stop Shop Rack Solution FFP 2 MS | Sauter, Thorsten | Awarded | Booked | Green | 2016-10-28 |  |  |  |  | 0% | 8% | 0% |  | EMEA | DACH | Germany | Core & Edge |  |  | DEUTSCHE TELEKOM-Customer | DEUTSCHE TELEKOM-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 97701 | 86760 | 10941 | 69512 | 0 | 69512 | 68726 | 68726 | 786 | 28189 | 28975 | 22% | 30% | 738 | 8% | 1524 | 0 | 1524 | 738 | 738 | 786 | 0 | 0 | 0 | 0 | 67988 | 0 | 67988 | 0 | 1.5 | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.6 | 1 | 24020 DT One Stop Shop Rack Solution FFP 2 MS
24044 | 24044 Mobily KSA (Iftikhar Ahmed) TIM 3-MTH Renewable COST TRSF to AS | Elsherif, Tarek | Awarded | In Progress | Green |  | 2016-08-01 | 2016-10-31 |  |  | 180% | 0% | -80% |  | EMEA | MEA | Saudi Arabia | Core & Edge |  |  | BMC-Customer | MOBILY-EndUser | Cost Transfer | None | Consulting – T & M |  | A | 0 | 0 | 0 | 37061 | 78199 | -41138 | 37061 | 115260 | -78199 | -37061 | -115260 | 0% | 0% | 78199 | 0% | 0 | 78199 | -78199 | 0 | 78199 | -78199 | 0 | 0 | 0 | 0 | 37061 | 0 | 37061 | 0 | 60 | 60 | 108 | 0 | -48 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 108 | 0 | 0 | 0 | 0 |  | 108 | 1 | 24044 Mobily KSA (Iftikhar Ahmed) TIM 3-MTH Renewable COST TRSF to AS
24058 | 24058 DCA UAE AMIA Upgrade Passenger Terminal Building SP 726 FFP 3MS | Bhinder, Muhammad Amir Rashid | Awarded | In Progress | Green | 2016-10-17 | 2016-10-13 | 2017-08-31 |  | 2017-07-06 | 115% | 23% | -15% | Scoping Issues | EMEA | MEA | UAE | Core & Edge |  |  | MINDWARE S.A.-Customer | DCA-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 155000 | 102717 | 52283 | 94145 | 54605 | 39541 | 18847 | 73452 | 20694 | 60855 | 81549 | 30% | 53% | 54493 | 23% | 75186 | 54493 | 20694 | 0 | 54493 | 20694 | 18959 | 112 | 18847 | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 86.2 | 0 | -11.1875 | 0 | 0 | 12.6 | 0 | 0% | 17% | 1.3 | 4.9 | 69.5 | 12.6 | 0 | 0 | 4.1 |  | 92.4 | 1 | 24058 DCA UAE AMIA Upgrade Passenger Terminal Building SP 726 FFP 3MS
24059 | 24059 OSP Mobile BH ICX SB IOT FFP 1 MS | Oliver, Juan | Awarded | In Progress | Green | 2017-02-17 | 2017-03-01 | 2017-08-31 |  |  | 38% | 25% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | Orange-Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  |  | 25662 | 0 | 25662 | 12983 | 3797 | 9186 | 5248 | 9045 | 3938 | 12679 | 16617 | 40% | 65% | 9045 | 25% | 12983 | 3797 | 9186 | 5248 | 9045 | 3938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 5.8 | 9.3 | 0 | 0 | 0 | 3.3 | 0 | 0% | 28% | 0.8 | 0 | 2.5 | 3.3 | 0 | 0 | 0 |  | 6.5 | 1 | 24059 OSP Mobile BH ICX SB IOT FFP 1 MS
24070 | 24070 TEF FUSION I&C GRANADA-ALMERIA HL3-HL4 | Gil, Jose | Awarded | In Progress | Green | 2016-06-24 | 2016-06-27 | 2017-07-28 |  |  | 84% | 7% | 0% |  | EMEA | Spain | Spain | Core & Edge |  |  | TELEFONICA - Customer | TELEFONICA ESPANA-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 823902 | 823902 | 0 | 686500 | 620009 | 66491 | 111047 | 731056 | -44556 | 137402 | 92846 | 4% | 11% | 44556 | 7% | 0 | 37725 | -37725 | 6831 | 44556 | -44556 | 3000 | 0 | 3000 | 0 | 683500 | 582283 | 101217 | 0 | 120 | 120 | 100.8 | 19.3 | 0 | 0 | 0 | 77.1 | 0 | 0% | 180% | 0 | 1 | 23.6 | 77.1 | 0 | 0 | 0 |  | 101.8 | 1 | 24070 TEF FUSION I&C GRANADA-ALMERIA HL3-HL4
24081 | 24081 TEF FUSION I&C HL1-HL2 (10 Nodes - 2016/2017) | Gil, Jose | Awarded | In Progress | Green | 2016-06-28 | 2016-06-28 | 2017-09-29 |  |  | 48% | 26% | 0% |  | EMEA | Spain | Spain | Core & Edge |  |  | TELEFONICA DE ESPANA (FUSION)-EndUser | TELEFONICA DE ESPANA-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 343906 | 204758 | 139148 | 257500 | 165547 | 91953 | 124769 | 290316 | -32816 | 86406 | 53590 | -10% | 16% | 32816 | 26% | 0 | 15907 | -15907 | 16909 | 32816 | -32816 | 2500 | 855 | 1645 | 0 | 255000 | 148785 | 106215 | 0 | 90 | 90 | 43.6 | 46.4 | 0 | 0 | 0 | 39.5 | 0 | 0% | 78% | 0 | 0 | 3.8 | 39.5 | 0 | 0.4 | 0 |  | 43.6 | 1 | 24081 TEF FUSION I&C HL1-HL2 (10 Nodes - 2016/2017)
24120 | 24120 Cox Communication SDN Trial & Buy - FOC | Henning, Mark | Awarded | Complete | Green | 2017-07-12 | 2017-02-13 | 2017-06-23 |  | 2017-07-14 | 293% | 0% | -193% | SOW Issues | AMER | CABLES | United States of America | SDN |  |  | COX COMMUNICATIONS, INC.-EndUser | COX COMMUNICATIONS, INC.-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | B | 148806 | 148806 | 0 | 33500 | 118898 | -85398 | 0 | 118898 | -85398 | 115306 | 29908 | 20% | 20% | 101904 | 0% | 25000 | 101904 | -76904 | 0 | 101904 | -76904 | 8500 | 16994 | 0 | -8494 | 0 | 0 | 0 | 0 | 30.1 | 30.1 | 88.2 | 0 | -58.1362 | 0 | 0 | 11.6 | 0 | 0% | 15% | 15.7 | 5.8 | 76.6 | 11.6 | 0 | 0 | 0 |  | 109.6 | 1 | 24120 Cox Communication SDN Trial & Buy - FOC
24154 | 24154 Bharti - 75 days Support - T&M | Pathak, Nishant | Awarded | On Hold | Green | 2016-06-29 | 2016-07-15 | 2017-08-31 |  | 2017-04-06 | 55% | -26% | 0% |  | APAC | India | India | Core & Edge |  |  | IBM-Customer | BHARTI AIRTEL LIMITED-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 70000 | 70000 | 0 | 37200 | 46932 | -9732 | 8131 | 55063 | -17863 | 32800 | 14937 | 47% | 21% | 19380 | -26% | 37200 | 11249 | 25951 | 8131 | 19380 | 17820 | 0 | 0 | 0 | 0 | 0 | 35684 | 0 | -35684 | 83 | 83 | 45.5 | 37.5 | 0 | 79 | 79 | 7 | 72 | 1975% | 1975% | 0 | 5.1 | 38.5 | 7 | 0 | 0 | 0 |  | 50.6 | 1 | 24154 Bharti - 75 days Support - T&M
24172 | 24172 Meditel FUN2 SRX RFQ FFP 7 MS + T&M 30 days | Ferrari, Lenora | Awarded | In Progress | Amber | 2017-01-03 | 2017-04-03 | 2017-12-31 |  | 2017-05-25 | 69% | 16% | 0% | Internal Issues | EMEA | ENA-R-SOUTH | Morocco/Western Sahara | Security |  |  | WESTCON GROUP EUROPEAN OPERATIONS | MEDITEL-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 215267 | 0 | 215267 | 147371 | 69903 | 77468 | 55970 | 125873 | 21498 | 67896 | 89395 | 26% | 42% | 78916 | 16% | 100414 | 60608 | 39806 | 18308 | 78916 | 21498 | 22381 | 4291 | 18090 | 0 | 24576 | 5004 | 19572 | 0 | 88 | 88 | 61.1 | 26.9 | 0 | 0 | 0 | 32.3 | 0 | 0% | 58% | 0.8 | 7.4 | 28.9 | 32.3 | 0 | 0 | 0 |  | 69.3 | 1 | 23744 ORANGE SENEGAL Sonatel BNG SBR FFP 7MS | 24172 Meditel FUN2 SRX RFQ FFP 7 MS + T&M 30 days
24188 | 24188 SEC NGRID Network Architecture Assessment FOC | Bin Sabbar, Abdullah | Awarded | Complete | Green |  | 2016-10-05 | 2017-01-31 |  | 2017-06-16 |  | 0% | 0% |  | EMEA | MEA | Saudi Arabia | Core & Edge | Security |  | Juniper | Saudi Electricity Company (SEC) - End User | Free of Charge | None | Consulting – Packaged |  | A | 0 | 0 | 0 | 3000 | 25295 | -22295 | 0 | 25295 | -22295 | -3000 | -25295 | 0% | 0% | 18295 | 0% | 0 | 18295 | -18295 | 0 | 18295 | -18295 | 3000 | 7000 | 0 | -4000 | 0 | 0 | 0 | 0 | 0 | 0 | 26.4 | 0 | -26.4375 | 0 | 0 | 10.1 | 0 | 0% | 61% | 0 | 4.6 | 16.4 | 10.1 | 0 | 0 | 0 |  | 31.1 | 1 | 24188 SEC NGRID Network Architecture Assessment FOC
24210 | 24210 TELEFONICA SPAIN Network Planning (NP) | Saccucci, Fabio | Awarded | In Progress | Green | [6 empty] | 0% | 0% |  | EMEA | Spain | Spain | Juniper Strategic Delivery |  |  | TELEFONICA DE ESPANA-EndUser | TELEFONICA ESPANA-EndUser |  |  |  |  | A | 0 | 0 | 0 | 0 | 32672 | -32672 | 0 | 32672 | -32672 | 0 | -32672 | 0% | 0% | 32672 | 0% | 0 | 32672 | -32672 | 0 | 32672 | -32672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.7 | 0 | -53.6875 | 0 | 0 | 53.7 | 0 | 0% | 0% | 0 | 0 | 0 | 53.7 | 0 | 0 | 0 |  | 53.7 |  | 24210 TELEFONICA SPAIN Network Planning (NP)
24225 | 24225 SEAT DC design FFP 2 MS (FOC) | Moreno, Carlos | Awarded | On Hold | Amber |  | 2016-06-28 | 2017-07-28 |  | 2017-07-12 | 88% | 0% | 0% |  | EMEA | Spain | Spain | Core & Edge |  |  | Seat | SEAT-EndUser | Free of Charge | None | Consulting – Fixed Price Custom |  | B | 0 | 0 | 0 | 0 | 16118 | -16118 | 1890 | 18008 | -18008 | 0 | -18008 | 0% | 0% | 17623 | 0% | 0 | 15733 | -15733 | 1890 | 17623 | -17623 | 0 | 385 | 0 | -385 | 0 | 0 | 0 | 0 | 38 | 38 | 33.4 | 4.6 | 0 | 0 | 0 | 10.5 | 0 | 0% | 38% | 0.1 | 0.5 | 22.9 | 10.5 | 0 | 0 | 0 |  | 34 | 1 | 24225 SEAT DC design FFP 2 MS (FOC)
24231 | 24231 Telefonica Data Center Miami | Almanza, Henry | Awarded | Complete | Green | 2016-12-08 | 2017-01-02 | 2017-06-30 | 2017-07-26 | 2017-07-21 | 140% | -29% | -70% | Product Issues | AMER | CALA | United States of America | Cloud | Network Automation |  | VOLOGY DATA SYSTEMS-Customer | TELEFONICA - Customer | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 123916 | 123916 | 0 | 107000 | 132482 | -25482 | 0 | 132482 | -25482 | 16916 | -8566 | 22% | -7% | 115978 | -29% | 93500 | 115978 | -22478 | 0 | 115978 | -22478 | 13500 | 16504 | 0 | -3004 | 0 | 0 | 0 | 0 | 60.1 | 73.1 | 102.1 | 0 | -42.0688 | 0 | 3.8 | 18.8 | 0 | 0% | 22% | 10.9 | 23 | 77 | 18.8 | 0 | 0 | 6.4 |  | 136 | 1 | 24231 Telefonica Data Center Miami
24244 | 24244 OSP SB Elecnor sede 1 ACX Scenario 20 Bilbao FFP 1 MS | Oliver, Juan | Awarded | Complete | Green | 2016-08-04 | 2016-08-28 | 2016-09-15 |  |  | 0% | 40% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 8721 | 8721 | 0 | 0 | 4808 | -4808 | 448 | 5256 | -5256 | 8721 | 3465 | 0% | 40% | 448 | 40% | 0 | 0 | 0 | 448 | 448 | -448 | 0 | 0 | 0 | 0 | 0 | 4808 | 0 | -4808 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.8 | 1 | 24244 OSP SB Elecnor sede 1 ACX Scenario 20 Bilbao FFP 1 MS
24248 | 24248 Mobinil (Orange) EGP DC FW migration Cisco ASA to SRX5400 FFP 2MS | Al Aswad, Waseem | Awarded | In Progress | Green | 2017-01-10 | 2017-01-25 | 2017-06-30 |  | 2017-06-22 | 273% | -57% | -173% | Resource Issues | EMEA | MEA | Egypt | Security |  |  | NOKIA CORPORATION-Customer | MOBINIL-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 51263 | 0 | 51263 | 29432 | 53813 | -24381 | 8960 | 62773 | -33341 | 21831 | -11510 | 35% | -22% | 53813 | -57% | 20472 | 53813 | -33341 | 0 | 53813 | -33341 | 8960 | 0 | 8960 | 0 | 0 | 0 | 0 | 0 | 22 | 22 | 60.1 | 0 | -38.125 | 0 | 0 | 12.4 | 0 | 0% | 26% | 1.6 | 0 | 47.8 | 12.4 | 0 | 0 | 0 |  | 61.8 | 1 | 24248 Mobinil (Orange) EGP DC FW migration Cisco ASA to SRX5400 FFP 2MS
24252 | 24252 Bharti - Smart Packet Backbone Design Part2 - FFP | Manohar, Ravindra | Awarded | In Progress | Amber | 2016-06-29 | 2016-08-29 | 2017-06-30 |  | 2017-06-28 | 215% | 4% | -115% | Customer Issues | APAC | India | India | Core & Edge |  |  | IBM-Customer | BHARTI AIRTEL LTD-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 83333 | 23175 | 60158 | 55960 | 49571 | 6389 | 2860 | 52431 | 3529 | 27373 | 30902 | 33% | 37% | 41438 | 4% | 53100 | 41438 | 11662 | 0 | 41438 | 11662 | 2860 | 0 | 2860 | 0 | 0 | 8133 | 0 | -8133 | 80 | 80 | 172.3 | 0 | -92.2313 | 0 | 0 | 41.5 | 0 | 0% | 32% | 0 | 6.5 | 126.4 | 41.5 | 0 | 3.1 | 1.3 |  | 178.8 | 1 | 24252 Bharti - Smart Packet Backbone Design Part2 - FFP
24256 | 24256 Orange SB ACX Scenario 18 Bilbao Elecnor2 FFP 1 MS | Oliver, Juan | Awarded | Complete | Green | 2016-07-13 | 2016-08-21 | 2016-09-15 |  |  | 0% | 20% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 6881 | 6881 | 0 | 0 | 3050 | -3050 | 1068 | 4117 | -4117 | 6881 | 2764 | 20% | 40% | 1068 | 20% | 0 | 0 | 0 | 1068 | 1068 | -1068 | 0 | 0 | 0 | 0 | 0 | 3050 | 0 | -3050 | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.6 | 1 | 24256 Orange SB ACX Scenario 18 Bilbao Elecnor2 FFP 1 MS
24278 | 24278 THALES T&M 9 Days | M, Rahimunnisa | Awarded | On Hold | Green | 2016-06-30 |  | 2017-08-31 |  | 2017-06-23 | 32% | 41% | 0% |  | EMEA | France | France | Security |  |  | NOMIOS - Customer | THALES-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 25000 | 0 | 25000 | 15408 | 1449 | 13959 | 4779 | 6229 | 9179 | 9592 | 18771 | 34% | 75% | 4479 | 41% | 13658 | 1449 | 12209 | 3029 | 4479 | 9179 | 1750 | 0 | 1750 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 2.9 | 6.1 | 0 | 0 | 0 | 2.9 | 0 | 0% | 48% | 0 | 0 | 0 | 2.9 | 0 | 0 | 0 |  | 2.9 | 1 | 24278 THALES T&M 9 Days
24294 | 24294-ATTM NP&E OAM SRX Conversion Engineering Audit 2016 | Charleville, Vann | Awarded | In Progress | Green |  | 2016-10-03 | 2017-08-11 |  | 2017-07-17 | 82% | -7% | 0% | Under/Not Over budget | AMER | AT&T | United States of America | Security |  |  | AT&T MOBILITY, LLC.-EndUser | AT&T MOBILITY, LLC.-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 137484 | 0 | 137484 | 81634 | 76868 | 4766 | 14319 | 91187 | -9553 | 55850 | 46297 | 41% | 34% | 91187 | -7% | 81634 | 76868 | 4766 | 14319 | 91187 | -9553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68.8 | 68.8 | 56.5 | 12.3 | 0 | 38.8 | 38.8 | 7.5 | 31.3 | 129% | 129% | 1.6 | 0 | 49 | 7.5 | 0 | 0 | 0 |  | 58.1 | 1 | 24294-ATTM NP&E OAM SRX Conversion Engineering Audit 2016
24298 | 24298 Singtel - PS Credits - June 2016 - T&M | Pathak, Nishant | Awarded | In Progress | Green | 2016-07-27 | 2016-05-02 | 2017-09-29 |  |  | 2% | 27% | 0% |  | APAC | ASEAN | Singapore | Core & Edge |  |  | NERA TELECOMMUNICATIONS LTD-Customer | SINGAPORE TELECOMMUNICATIONS LIMITED-EndUser | PO | Upon Completion | Consulting – T & M |  | A | 46501 | 0 | 46501 | 27900 | 14535 | 13365 | 595 | 15130 | 12770 | 18601 | 31371 | 40% | 67% | 730 | 27% | 27900 | 135 | 27765 | 595 | 730 | 27170 | 0 | 0 | 0 | 0 | 0 | 14400 | 0 | -14400 | 31 | 31 | 0.6 | 30.4 | 0 | 31 | 31 | 0.6 | 30.4 | 0% | 0% | 0 | 0 | 0 | 0.6 | 0 | 0 | 0 |  | 0.6 | 1 | 26895 Singtel - PS Credits Container Project | 24298 Singtel - PS Credits - June 2016 - T&M
24318 | 24318 Stadt Frankfurt QoS Concept review FFP 2 MS | Subramaniam, Ragunath | Awarded | Booked | Green | 2017-01-31 | 2017-06-05 | 2017-06-21 |  | 2017-06-19 | 51% | -7% | -76% |  | EMEA | DACH | Germany | Core & Edge |  |  | WESTCON GROUP EUROPEAN OPERATIONS | Stadt (Germany) - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 22154 | 22154 | 0 | 14236 | 9409 | 4827 | 9835 | 19244 | -5008 | 7918 | 2910 | 20% | 13% | 18419 | -7% | 13411 | 9409 | 4002 | 9010 | 18419 | -5008 | 825 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 13.2 | 23.2 | 11.8 | 11.4 | -10 | 0 | 3.5 | 1.5 | 0 | 0% | 18% | 0.1 | 0 | 10.3 | 1.5 | 0 | 0 | 0 |  | 11.9 | 1 | 24318 Stadt Frankfurt QoS Concept review FFP 2 MS
24321 | 24321 Orange SB ACX Scenario 14 ALIBERICO 16 FFP 1 MS | Oliver, Juan | Awarded | Complete | Green | 2016-08-11 | 2016-09-15 | 2016-10-31 |  |  | 42% | 17% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT ORANGE-EndUser | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 8176 | 8176 | 0 | 4268 | 4555 | -287 | 628 | 5183 | -915 | 3908 | 2994 | 20% | 37% | 1076 | 17% | 4268 | 448 | 3820 | 628 | 1076 | 3192 | 0 | 0 | 0 | 0 | 0 | 4107 | 0 | -4107 | 3 | 3 | 1.3 | 1.8 | 0 | 0 | 0 | 1.3 | 0 | 0% | 71% | 0 | 0 | 0 | 1.3 | 0 | 0 | 0 |  | 1.3 | 1 | 24321 Orange SB ACX Scenario 14 ALIBERICO 16 FFP 1 MS
24322 | 24322 Orange SB ACX Scenario 25 EVERIS Manoteras 52 FFP 1 MS | Oliver, Juan | Awarded | Complete | Green | 2016-08-12 | 2016-09-01 | 2016-11-30 |  |  | 42% | 19% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT ORANGE-EndUser | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 6171 | 6171 | 0 | 4859 | 3106 | 1753 | 648 | 3753 | 1106 | 1312 | 2418 | 20% | 39% | 1110 | 19% | 4859 | 463 | 4396 | 648 | 1110 | 3749 | 0 | 0 | 0 | 0 | 0 | 2643 | 0 | -2643 | 3 | 3 | 1.3 | 1.8 | 0 | 0 | 0 | 1.3 | 0 | 0% | 71% | 0 | 0 | 0 | 1.3 | 0 | 0 | 0 |  | 1.3 | 1 | 24322 Orange SB ACX Scenario 25 EVERIS Manoteras 52 FFP 1 MS
24323 | 24323 Orange SB ACX Scenario 25 TRANSCOM San Fernando FFP 1 MS | Oliver, Juan | Awarded | Complete | Green | 2016-08-11 | 2016-09-01 | 2016-12-01 |  |  | 58% | 18% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT ORANGE-EndUser | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 6073 | 6073 | 0 | 4859 | 3285 | 1574 | 458 | 3743 | 1116 | 1214 | 2330 | 20% | 38% | 1100 | 18% | 4859 | 642 | 4217 | 458 | 1100 | 3759 | 0 | 0 | 0 | 0 | 0 | 2643 | 0 | -2643 | 3 | 3 | 1.8 | 1.3 | 0 | 0 | 0 | 1.8 | 0 | 0% | 140% | 0 | 0 | 0 | 1.8 | 0 | 0 | 0 |  | 1.8 | 1 | 24323 Orange SB ACX Scenario 25 TRANSCOM San Fernando FFP 1 MS
24324 | 24324 Orange SB ACX Scenario 25 EVERIS Miguelturra FFP 1 MS | Oliver, Juan | Awarded | Complete | Green | 2016-08-09 | 2016-09-01 | 2016-12-29 |  |  | 42% | 37% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT ORANGE-EndUser | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 8203 | 8203 | 0 | 5457 | 4524 | 933 | 628 | 5152 | 305 | 2746 | 3051 | 0% | 37% | 1076 | 37% | 5457 | 448 | 5009 | 628 | 1076 | 4381 | 0 | 0 | 0 | 0 | 0 | 4076 | 0 | -4076 | 3 | 3 | 1.3 | 1.8 | 0 | 0 | 0 | 1.3 | 0 | 0% | 71% | 0 | 0 | 0 | 1.3 | 0 | 0 | 0 |  | 1.3 | 1 | 24324 Orange SB ACX Scenario 25 EVERIS Miguelturra FFP 1 MS
24331 | 24331 Megafon DC SPB DC Fabrics FFP 2 MS | Tyan, Kirill | Awarded | Booked | Green | 2017-03-28 | 2017-05-15 | 2017-08-31 |  | 2017-06-15 | 70% | 17% | -4% |  | EMEA | ENA-R-RCIS | Russia | Cloud |  |  | INLINE TECHNOLOGIES GROUP LLC-Customer | MEGAFON MOSCOW-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 50948 | 24102 | 26846 | 30219 | 14971 | 15248 | 11925 | 26896 | 3323 | 20729 | 24052 | 30% | 47% | 17616 | 17% | 20939 | 13737 | 7203 | 3880 | 17616 | 3323 | 9280 | 1234 | 8046 | 0 | 0 | 0 | 0 | 0 | 45 | 47 | 32.8 | 14.2 | -2 | 27 | 28 | 0.3 | 26.7 | 150% | 147% | 4.6 | 0 | 32.5 | 0.3 | 0 | 0 | 0 |  | 37.4 | 2 | 24331 Megafon DC SPB DC Fabrics FFP 2 MS
24332 | 24332 VF IT Power Supply Swap BO02 FFP xMS | Moreno, Carlos | Awarded | On Hold | Green | 2016-10-13 | 2016-11-02 | 2017-08-31 |  | 2017-07-12 | 113% | 11% | -13% |  | EMEA | UK-I | Italy | Security |  |  | VODAFONE | VODAFONE ITALY-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 14584 | 0 | 14584 | 12910 | 626 | 12284 | 12101 | 12727 | 183 | 1674 | 1857 | 2% | 13% | 626 | 11% | 809 | 626 | 183 | 0 | 626 | 183 | 0 | 0 | 0 | 0 | 12101 | 0 | 12101 | 0 | 1 | 1 | 1.1 | 0 | -0.125 | 0 | 0 | 1.1 | 0 | 0% | 0% | 0 | 0 | 0 | 1.1 | 0 | 0 | 0 |  | 1.1 | 1 | 24332 VF IT Power Supply Swap BO02 FFP xMS
24335 | 24335 CAP GEMINI Junos Space Install T&M 13 Days | M, Rahimunnisa | Awarded | On Hold | Green | 2016-12-15 | 2016-12-19 | 2017-08-31 | 2017-08-31 | 2017-06-23 | 107% | 20% | -7% |  | EMEA | France | France | Network Automation |  |  | ORANGE BUSINESS SERVICES-Customer | Capgemini | PO | Fully in Advance | Consulting – T & M |  | A | 40000 | 40000 | 0 | 27553 | 11642 | 15911 | 7825 | 19467 | 8086 | 12447 | 20533 | 31% | 51% | 11642 | 20% | 19728 | 11642 | 8086 | 0 | 11642 | 8086 | 7825 | 0 | 7825 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 13.9 | 0 | -0.875 | 0 | 0 | 2.4 | 0 | 0% | 21% | 0 | 0 | 11.5 | 2.4 | 0 | 0 | 0 |  | 13.9 | 1 | 24335 CAP GEMINI Junos Space Install T&M 13 Days
24336 | 24336 VF IT Corporate Mobile LAN FFP 3 MS | Moreno, Carlos | Awarded | In Progress | Green | 2017-02-10 | 2017-02-13 | 2017-06-30 |  | 2017-07-12 | 142% | 3% | -42% |  | EMEA | UK-I | Italy | Security |  |  | VODAFONE | VODAFONE ITALY-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 33914 | 0 | 33914 | 21504 | 23054 | -1550 | 1663 | 24717 | -3213 | 12410 | 9197 | 24% | 27% | 22957 | 3% | 19744 | 22957 | -3213 | 0 | 22957 | -3213 | 1760 | 97 | 1663 | 0 | 0 | 0 | 0 | 0 | 20.6 | 20.6 | 29.3 | 0 | -8.65 | 0 | 0 | 4.3 | 0 | 0% | 17% | 0 | 0 | 25 | 4.3 | 0 | 0 | 0 |  | 29.3 | 1 | 24336 VF IT Corporate Mobile LAN FFP 3 MS
24344 | 24344 Orange SB ACX Scenario 2 Quotes FFP 1 MS | Oliver, Juan | Awarded | Complete | Green | 2016-08-10 | 2016-10-03 | 2017-03-31 |  |  | 50% | 38% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT ORANGE-EndUser | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 14506 | 14506 | 0 | 10316 | 4872 | 5444 | 1211 | 6083 | 4233 | 4190 | 8422 | 20% | 58% | 1224 | 38% | 5457 | 612 | 4845 | 612 | 1224 | 4233 | 0 | 0 | 0 | 0 | 4859 | 4260 | 599 | 0 | 3 | 3 | 1.5 | 1.5 | 0 | 0 | 0 | 1.5 | 0 | 0% | 100% | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 |  | 1.5 | 1 | 24344 Orange SB ACX Scenario 2 Quotes FFP 1 MS
24345 | 24345 Orange SB ACX Install 5 Quotes | Oliver, Juan | Awarded | Complete | Green | 2016-08-09 | 2016-08-29 | 2017-01-12 |  |  | 33% | 46% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT ORANGE-EndUser | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 41197 | 41197 | 0 | 5457 | 12618 | -7161 | 1210 | 13829 | -8372 | 35740 | 27369 | 20% | 66% | 1793 | 46% | 5457 | 583 | 4874 | 1210 | 1793 | 3664 | 0 | 0 | 0 | 0 | 0 | 12036 | 0 | -12036 | 5 | 5 | 1.6 | 3.4 | 0 | 0 | 0 | 1.6 | 0 | 0% | 48% | 0 | 0 | 0 | 1.6 | 0 | 0 | 0 |  | 1.6 | 1 | 24345 Orange SB ACX Install 5 Quotes
24371 | 24371 Orange SB ACX Scenario 31 UPF Barcelona | Oliver, Juan | Awarded | Complete | Green | 2016-08-05 | 2016-10-03 | 2016-12-29 |  |  | 0% | 18% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer-EndUser | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 8203 | 0 | 8203 | 0 | 4107 | -4107 | 968 | 5074 | -5074 | 8203 | 3129 | 20% | 38% | 968 | 18% | 0 | 0 | 0 | 968 | 968 | -968 | 0 | 0 | 0 | 0 | 0 | 4107 | 0 | -4107 | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.5 | 1 | 24371 Orange SB ACX Scenario 31 UPF Barcelona
24372 | 24372 Orange SB ACX Scenario 25 Planeta Madrid | Oliver, Juan | Awarded | Complete | Green | 2016-08-10 | 2016-10-01 | 2016-11-30 |  |  | 54% | 18% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer-EndUser | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 6073 | 6073 | 0 | 0 | 3240 | -3240 | 505 | 3745 | -3745 | 6073 | 2328 | 20% | 38% | 1102 | 18% | 0 | 597 | -597 | 505 | 1102 | -1102 | 0 | 0 | 0 | 0 | 0 | 2643 | 0 | -2643 | 3 | 3 | 1.6 | 1.4 | 0 | 0 | 0 | 1.6 | 0 | 0% | 118% | 0 | 0 | 0 | 1.6 | 0 | 0 | 0 |  | 1.6 | 1 | 24372 Orange SB ACX Scenario 25 Planeta Madrid
24377 | 24377 FFP VZ JUNOS upgrade automation | Martin, David | Awarded | In Progress | Amber | 2016-12-07 | 2016-11-14 | 2017-06-30 |  | 2017-07-18 | 186% | -20% | -86% | Internal Issues | AMER | VERIZON | United States of America | Core & Edge |  |  | VERIZON COMMUNICATIONS-EndUser | VERIZON COMMUNICATIONS-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | B | 98000 | 0 | 98000 | 64700 | 83344 | -18644 | 0 | 83344 | -18644 | 33300 | 14656 | 35% | 15% | 82525 | -20% | 64700 | 82525 | -17825 | 0 | 82525 | -17825 | 0 | 819 | 0 | -819 | 0 | 0 | 0 | 0 | 59.4 | 59.4 | 110.6 | 0 | -51.2325 | 59.4 | 59.4 | 0 | 59.4 | 431845% | 116% | 4.4 | 0 | 110.6 | 0 | 0 | 0 | 0 |  | 115 | 1 | 24377 FFP VZ JUNOS upgrade automation
24384 | 24384 DCA AMIA new DC segment Fabric Bring Up Packaged Services Q316 Offer | Bhinder, Muhammad Amir Rashid | Awarded | In Progress | Green | 2016-11-16 | 2016-11-21 | 2017-08-31 |  | 2017-07-06 | 90% | 0% | 0% | Under/Not Over budget | EMEA | MEA | UAE | Cloud |  |  | ALPHA DATA PROCESSING LLC-Customer | DCA-EndUser | PO | Milestone Payments | Consulting – Packaged |  | C | 39231 | 31519 | 7712 | 48862 | 17614 | 31248 | 11795 | 29409 | 19453 | -9631 | 9822 | 25% | 25% | 17614 | 0% | 37067 | 17614 | 19453 | 0 | 17614 | 19453 | 11795 | 0 | 11795 | 0 | 0 | 0 | 0 | 0 | 27 | 27 | 24.4 | 2.6 | 0 | 0 | 0 | 4.8 | 0 | 0% | 21% | 0 | 2.7 | 19.6 | 4.8 | 0 | 0 | 0 |  | 27.1 | 1 | 24384 DCA AMIA new DC segment Fabric Bring Up Packaged Services Q316 Offer
24415 | 24415 IBM Portsmouth UK CMS | Akiyama, Mauricio | Awarded | In Progress | Green | 2016-09-27 | 2016-09-01 | 2017-09-01 |  |  | 0% | 1% | 0% |  | AMER | CLOUD PROVIDERS | United Kingdom | Cloud |  |  | IBM CORPORATION-EndUser | IBM CORPORATION-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 66690 | 66690 | 0 | 48326 | 48326 | 0 | 0 | 48326 | 0 | 18364 | 18364 | 27% | 28% | 0 | 1% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48326 | 48326 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 1.9 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.9 | 1 | 24415 IBM Portsmouth UK CMS
24418 | 24418 GCI SBR Project | LaSalle, Glenn | Awarded | On Hold | Green | 2016-09-29 | 2017-07-24 | 2017-08-29 |  |  | 0% | 27% | 0% |  | AMER | CANADA | United States of America | Core & Edge |  |  | STRUCTURED COMMUNICATION SYSTEMS INC-Customer | GCI-EndUser | PO | Monthly in Arrears | Consulting – T & M |  | A | 13063 | 0 | 13063 | 6125 | 0 | 6125 | 2938 | 2938 | 3187 | 6938 | 10125 | 50% | 78% | 2938 | 27% | 6125 | 0 | 6125 | 2938 | 2938 | 3187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 5 | 0.0025 | 0 | 0 | 0 | 0 | 0% | 0% | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2 | 1 | 24418 GCI SBR Project
24423 | 24423 ORANGE Project Mosiac T&M 10 Days | Ferrari, Lenora | Awarded | On Hold | Green | 2016-10-19 |  |  |  | 2017-06-29 |  | 41% | 0% |  | EMEA | France | Cote D'Ivoire | Core & Edge |  |  | WESTCON GROUP EUROPEAN OPERATIONS | ORANGE COTE D'IVOIRE-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 26000 | 0 | 26000 | 11463 | 686 | 10777 | 0 | 686 | 10777 | 14537 | 25314 | 56% | 97% | 686 | 41% | 11463 | 686 | 10777 | 0 | 686 | 10777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | -1.625 | 0 | 0 | 1.6 | 0 | 0% | 0% | 0 | 0 | 0 | 1.6 | 0 | 0 | 0 |  | 1.7 |  | 24423 ORANGE Project Mosiac T&M 10 Days
24425 | 24425 Orange SB ACX Scenario 31 OSP Madrid FFP 1 MS | Oliver, Juan | Awarded | Complete | Green | 2016-08-09 | 2016-09-15 | 2016-11-30 |  |  | 69% | -9% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 8203 | 8203 | 0 | 6563 | 4614 | 1949 | 2687 | 7301 | -738 | 1640 | 902 | 20% | 11% | 738 | -9% | 0 | 507 | -507 | 231 | 738 | -738 | 0 | 0 | 0 | 0 | 6563 | 4107 | 2456 | 0 | 2 | 2 | 1.4 | 0.6 | 0 | 0 | 0 | 1.4 | 0 | 0% | 220% | 0 | 0 | 0 | 1.4 | 0 | 0 | 0 |  | 1.4 | 1 | 24425 Orange SB ACX Scenario 31 OSP Madrid FFP 1 MS
24427 | 24427 VF OpenStack POC PS Support FOC T&M | Subramaniam, Ragunath | Awarded | In Progress | Green |  | 2016-10-10 | 2017-10-10 |  | 2017-06-19 | 70% | 0% | 0% |  | EMEA | UK-I | Italy | Network Automation |  |  | VODAFONE | VODAFONE GROUP SERVICES-EndUser | Free of Charge | None | Consulting – T & M |  | A | 0 | 0 | 0 | 0 | 33679 | -33679 | 10725 | 44405 | -44405 | 0 | -44405 | 0% | 0% | 44405 | 0% | 0 | 33679 | -33679 | 10725 | 44405 | -44405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 55.6 | 24.4 | 0 | 0 | 0 | 3.1 | 0 | 0% | 4% | 0 | 6.6 | 52.5 | 3.1 | 0 | 0 | 0 |  | 62.3 | 1 | 24427 VF OpenStack POC PS Support FOC T&M
24440 | 24440 Telstra - RDN Networks RR Migration - FFP | Davis, Joseph | Awarded | On Hold | Amber | 2016-09-21 | 2017-10-04 | 2017-07-21 |  | 2017-07-07 | 156% | -40% | -56% | Product Issues | APAC | ANZ | Australia | Core & Edge |  |  | TELSTRA CORPORATION-Customer | TELSTRA CORPORATION LIMITED-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 146247 | 108486 | 37761 | 101700 | 159712 | -58012 | 0 | 159712 | -58012 | 44547 | -13465 | 30% | -9% | 39490 | -40% | 101700 | 39490 | 62210 | 0 | 39490 | 62210 | 0 | 0 | 0 | 0 | 0 | 120222 | 0 | -120222 | 113 | 113 | 176.3 | 0 | -63.25 | 0 | 0 | 42.5 | 0 | 0% | 32% | 0 | 0 | 129.4 | 42.5 | 0 | 0 | 4.4 |  | 176.3 | 1 | 24440 Telstra - RDN Networks RR Migration - FFP
24465 | 24465 Orange SB ACX Scenario 20 Generali BCN | Oliver, Juan | Awarded | Complete | Green | 2016-08-11 | 2016-09-15 | 2016-10-31 |  |  | 75% | -9% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 7897 | 7897 | 0 | 6317 | 4659 | 1658 | 2394 | 7053 | -736 | 1580 | 844 | 20% | 11% | 736 | -9% | 0 | 552 | -552 | 184 | 736 | -736 | 0 | 0 | 0 | 0 | 6317 | 4107 | 2210 | 0 | 2 | 2 | 1.5 | 0.5 | 0 | 0 | 0 | 1.5 | 0 | 0% | 300% | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 |  | 1.5 | 1 | 24465 Orange SB ACX Scenario 20 Generali BCN
24471 | 24471 OSP SB Cordoba POP Full Routing Implementation FFP 1MS | Oliver, Juan | Awarded | Complete | Green | 2016-11-01 | 2016-11-06 | 2016-12-09 |  |  | 0% | 54% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 3113 | 0 | 3113 | 2483 | 0 | 2483 | 143 | 143 | 2340 | 630 | 2970 | 42% | 95% | 143 | 54% | 2483 | 0 | 2483 | 143 | 143 | 2340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.2 | 3.2 | 0 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2.8 | 1 | 24471 OSP SB Cordoba POP Full Routing Implementation FFP 1MS
24479 | 24479 PT XL - 26 Credits - T&M | Henning, Riana | Awarded | In Progress | Green |  | 2017-07-03 | 2017-10-23 |  |  | 58% | 72% | 23% |  | APAC | ASEAN | Indonesia | Core & Edge |  |  | PT LINTAS TEKNOLOGI INDONESIA-Customer | PT EXCELCOMINDO PRATAMA-EndUser | PO | Upon Completion | Consulting – T & M |  | A | 38999 | 0 | 38999 | 27900 | 0 | 27900 | 0 | 0 | 27900 | 11099 | 38999 | 28% | 100% | 0 | 72% | 27900 | 0 | 27900 | 0 | 0 | 27900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 20 | 11.5 | 8.5 | 6 | 0 | 20 | 0 | 0 | 0% | 0% | 0 | 0 | 11.5 | 0 | 0 | 0 | 0 |  | 11.5 | 1 | 26896 PT XL - PS Credits Container Project | 24479 PT XL - 26 Credits - T&M
24503 | 24503 Orange SB ACX Scenario 18 Generali Madrid | Oliver, Juan | Awarded | Complete | Green | 2016-09-26 | 2016-10-13 | 2017-03-31 |  |  | 22% | -38% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 6003 | 0 | 6003 | 4859 | 3130 | 1729 | 3955 | 7085 | -2226 | 1144 | -1082 | 20% | -18% | 2226 | -38% | 0 | 487 | -487 | 1739 | 2226 | -2226 | 0 | 0 | 0 | 0 | 4859 | 2643 | 2216 | 0 | 4 | 4 | 0.9 | 3.1 | 0 | 0 | 0 | 0.9 | 0 | 0% | 28% | 0 | 0 | 0 | 0.9 | 0 | 0 | 0 |  | 0.9 | 1 | 24503 Orange SB ACX Scenario 18 Generali Madrid
24533 | 24533 Orange SB ACX Scenarios 31 8 31 8 ISGF Madrid FFP 4 MS | Oliver, Juan | Awarded | Complete | Green | 2016-08-23 | 2016-09-04 | 2017-03-31 |  |  | 0% | 31% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 22552 | 22552 | 0 | 6562 | 9726 | -3164 | 1222 | 10948 | -4386 | 15990 | 11604 | 20% | 51% | 1222 | 31% | 0 | 0 | 0 | 1222 | 1222 | -1222 | 0 | 0 | 0 | 0 | 6562 | 9726 | 0 | -3164 | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.9 | 1 | 24533 Orange SB ACX Scenarios 31 8 31 8 ISGF Madrid FFP 4 MS
24534 | 24534 Gamesys Dc and Contrail 30d T&M (Infradata) | Subramaniam, Ragunath | Awarded | In Progress | Green | 2016-12-30 | 2017-04-04 | 2017-10-10 |  | 2017-06-19 | 75% | 38% | 0% |  | EMEA | UK-I | United Kingdom | SDN |  |  | WESTCON-Customer | GAMESYS | PO | Fully in Advance | Consulting – T & M |  | A | 78247 | 78247 | 0 | 58375 | 20465 | 37910 | 8049 | 28515 | 29860 | 19872 | 49732 | 25% | 64% | 24515 | 38% | 54375 | 20465 | 33910 | 4049 | 24515 | 29860 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 22.5 | 7.5 | 0 | 0 | 0 | 2.1 | 0 | 0% | 8% | 0.6 | 2.5 | 20.4 | 2.1 | 0 | 0 | 0 |  | 25.5 | 1 | 24534 Gamesys Dc and Contrail 30d T&M (Infradata)
24535 | 24535 GCI Business Cloud CPE - Phase 1 | Henning, Mark | Awarded | Complete | Green | 2016-10-24 | 2016-11-07 | 2017-07-14 | 2017-07-31 | 2017-07-14 | 132% | -25% | -79% | Product Issues | AMER | US TERRITORIES | United States of America | SDN |  |  | STRUCTURED COMMUNICATION SYSTEMS INC-Customer | GCI - MANAGED BROADBAND SVCS-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 89550 | 89550 | 0 | 62153 | 80989 | -18836 | 2580 | 83569 | -21416 | 27397 | 5981 | 32% | 7% | 80989 | -25% | 59573 | 80989 | -21416 | 0 | 80989 | -21416 | 2580 | 0 | 2580 | 0 | 0 | 0 | 0 | 0 | 50.1 | 68.1 | 89.6 | 0 | -39.5712 | 0 | 2.8 | 9.1 | 0 | 0% | 11% | 4.9 | 0 | 71.6 | 9.1 | 2.2 | 0 | 6.8 |  | 94.6 | 1 | 24535 GCI Business Cloud CPE - Phase 1
24557 | 24557 Globe - BNG Expansion - Phase 2 - T&M | Ang, Soon Aun | Awarded | On Hold | Green | 2016-09-09 | 2017-02-15 | 2017-09-30 |  | 2017-07-21 | 155% | -66% | -55% | Under/Not Over budget | APAC | ASEAN | Philippines | Core & Edge |  |  | COMMVERGE SOLUTIONS LIMITED-Customer | GLOBE TELECOM, INC.-EndUser | PO | Upon Completion | Consulting – T & M |  | A | 50000 | 8929 | 41072 | 36800 | 62509 | -25709 | 7100 | 69609 | -32809 | 13200 | -19608 | 26% | -39% | 62509 | -66% | 29700 | 62509 | -32809 | 0 | 62509 | -32809 | 7100 | 0 | 7100 | 0 | 0 | 8242 | 0 | -8242 | 33 | 33 | 51.1 | 0 | -18.125 | 0 | 0 | 0.9 | 0 | 0% | 2% | 0 | 1 | 49 | 0.9 | 0 | 0 | 1.3 |  | 52.1 | 1 | 24557 Globe - BNG Expansion - Phase 2 - T&M
24568 | 24568 Execulink Telecom E to Mx Migration | Hassan, Saqib | Awarded | On Hold | Amber | 2017-02-02 | 2017-04-03 | 2017-09-29 | 2017-10-02 | 2017-07-21 | 37% | 16% | 0% | Under/Not Over budget | AMER | CANADA | Canada | Core & Edge |  |  | CHARTER TELECOM INC-Customer | Execulink-End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 99546 | 0 | 99546 | 64639 | 16413 | 48226 | 27471 | 43884 | 20755 | 34907 | 55661 | 40% | 56% | 39464 | 16% | 60219 | 16413 | 43806 | 23051 | 39464 | 20755 | 4420 | 0 | 4420 | 0 | 0 | 0 | 0 | 0 | 41 | 41 | 15 | 26 | 0.0025 | 5.5 | 5.5 | 3.3 | 2.3 | 16% | 16% | 3.7 | 0 | 2.4 | 3.3 | 0 | 0 | 9.4 |  | 18.7 | 1 | 24568 Execulink Telecom E to Mx Migration
24582 | 24582 Orange SB ACX Scenario 22 KIKO Madrid FFP 1MS | Oliver, Juan | Awarded | Complete | Green | 2016-09-29 | 2016-10-25 | 2016-11-30 |  |  | 19% | 10% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 7957 | 0 | 7957 | 0 | 4376 | -4376 | 1166 | 5541 | -5541 | 7957 | 2416 | 20% | 30% | 1435 | 10% | 0 | 269 | -269 | 1166 | 1435 | -1435 | 0 | 0 | 0 | 0 | 0 | 4107 | 0 | -4107 | 4 | 4 | 0.8 | 3.3 | 0 | 0 | 0 | 0.8 | 0 | 0% | 23% | 0 | 0 | 0 | 0.8 | 0 | 0 | 0 |  | 0.8 | 1 | 24582 Orange SB ACX Scenario 22 KIKO Madrid FFP 1MS
24584 | 24584 Orange SB ACX Scenario 15 15 Cesca BCN FFP 2Quotes | Oliver, Juan | Awarded | In Progress | Green | 2016-09-21 | 2016-10-25 | 2017-08-31 |  |  | 0% | -20% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  |  | 4971 | 0 | 4971 | 0 | 4448 | -4448 |  |  |  | 4971 |  | 20% | 0% |  | -20% | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 4448 | 0 | -4448 | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 24584 Orange SB ACX Scenario 15 15 Cesca BCN FFP 2Quotes
24588 | 24588 Verizon Wireline (2) PTX resources Full Year 2017 | Stroud, Charlie | Awarded | In Progress | Green | 2016-12-20 | 2017-01-01 | 2017-12-29 |  |  | 8% | -197% | -98% |  | AMER | VERIZON |  | Core & Edge |  |  | VERIZON COMMUNICATIONS-EndUser | VERIZON COMMUNICATIONS-EndUser | PO | Monthly in Advance | Consulting – Fixed Price Custom |  | B | 799000 | 0 | 799000 | 1356800 | 127141 | 1229659 | 2085819 | 2212960 | -856160 | -557800 | -1413960 | 20% | -177% | 1534560 | -197% | 678400 | 125580 | 552820 | 1408980 | 1534560 | -856160 | 678400 | 1561 | 676839 | 0 | 0 | 0 | 0 | 0 | 562 | 1112 | 91 | 1021 | -550 | 0 | 550 | 0 | 0 | 0% | 98% | 0 | 0 | 91 | 0 | 0 | 0 | 0 |  | 91 | 1 | 24588 Verizon Wireline (2) PTX resources Full Year 2017
24615 | 24615 Kauai Island Utility 10d TE | Akiyama, Mauricio | Awarded | In Progress | Green | 2016-09-22 | 2016-09-26 | 2017-09-01 |  |  | 79% | 33% | 0% |  | AMER | US TERRITORIES | United States of America | Security |  |  | SOS-Hawaii | Kauai Island Utility Cooperative - End User | PO | Upon Completion | Consulting – Packaged |  | A | 24750 | 0 | 24750 | 8000 | 5968 | 2032 | 0 | 5968 | 2032 | 16750 | 18782 | 43% | 76% | 5968 | 33% | 8000 | 5968 | 2032 | 0 | 5968 | 2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 7.9 | 2.1 | 0 | 0 | 0 | 0.4 | 0 | 0% | 4% | 2.2 | 0 | 7.5 | 0.4 | 0 | 0 | 0 |  | 10.1 | 1 | 24615 Kauai Island Utility 10d TE
24617 | 24617 Orange SB ACX Scenario 31 Huawei MAD FFP 1MS | Oliver, Juan | Awarded | Complete | Green | 2016-08-23 | 2016-09-22 | 2016-10-13 |  |  | 34% | -19% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 8108 | 8108 | 0 | 6562 | 4614 | 1948 | 3424 | 8038 | -1476 | 1546 | 70 | 20% | 1% | 1476 | -19% | 0 | 507 | -507 | 969 | 1476 | -1476 | 0 | 0 | 0 | 0 | 6562 | 4107 | 2455 | 0 | 4 | 4 | 1.4 | 2.6 | 0 | 0 | 0 | 1.4 | 0 | 0% | 52% | 0 | 0 | 0 | 1.4 | 0 | 0 | 0 |  | 1.4 | 1 | 24617 Orange SB ACX Scenario 31 Huawei MAD FFP 1MS
24623 | 24623 Roy Hill - QFX Swapout - T&M | Pathak, Nishant | Awarded | On Hold | Green | 2016-09-27 | 2016-10-10 | 2017-08-31 |  | 2017-07-05 | 90% | 17% | 0% |  | APAC | ANZ | Australia | Cloud |  |  | AVNET INC.-Customer | ROY HILL HOLDINGS PTY LTD-EndUser | PO | Milestone Payments | Consulting – T & M |  | A | 20137 | 0 | 20137 | 18300 | 12629 | 5671 | 2300 | 14929 | 3371 | 1837 | 5208 | 9% | 26% | 11181 | 17% | 16000 | 11181 | 4819 | 0 | 11181 | 4819 | 2300 | 0 | 2300 | 0 | 0 | 1448 | 0 | -1448 | 20 | 20 | 18 | 2 | 0 | 0 | 20 | 2.5 | 0 | 0% | 0% | 0 | 5.8 | 15 | 2.5 | 0 | 0 | 0.5 |  | 23.8 | 1 | 24623 Roy Hill - QFX Swapout - T&M
24626 | 24626 PSBA - Network Management for PSN 1.0 - FFP | Henning, Riana | Awarded | In Progress | Green | 2016-10-18 | 2016-11-07 | 2017-07-28 |  | 2017-06-22 | 249% | -120% | -149% | Internal Issues | APAC | ANZ | Australia | Cloud |  |  | WESTCON GROUP PTE LTD - Customer | PUBLIC SAFETY BUSINESS AGENCY-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 50170 | 34913 | 15257 | 37930 | 88489 | -50559 | 9580 | 98069 | -60139 | 12240 | -47899 | 24% | -95% | 81206 | -120% | 28350 | 81206 | -52856 | 0 | 81206 | -52856 | 9580 | 0 | 9580 | 0 | 0 | 7283 | 0 | -7283 | 34.5 | 34.5 | 85.9 | 0 | -51.375 | 6.2 | 6.2 | 10.9 | 0 | 22% | 15% | 0 | 6 | 73 | 10.9 | 0 | 0 | 2 |  | 91.9 | 1 | 24626 PSBA - Network Management for PSN 1.0 - FFP
24628 | 24628 Orange OTI POP Refresh Project (Main PID) | Masci, Fabio | Awarded | In Progress | Amber |  | 2016-07-15 | 2017-07-28 |  | 2017-06-30 | 104% | 46% | -4% | Customer Issues | EMEA | France | France | Core & Edge |  |  | ORANGE SA-Customer | ORANGE-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 317549 | 317549 | 0 | 211538 | 87030 | 124507 | 60927 | 147957 | 63581 | 106012 | 169592 | 8% | 53% | 84250 | 46% | 147831 | 84250 | 63581 | 0 | 84250 | 63581 | 24640 | 2780 | 21860 | 0 | 39067 | 0 | 39067 | 0 | 145.5 | 145.5 | 151.7 | 0 | -6.1875 | 0 | 0 | 33.8 | 0 | 0% | 29% | 0.5 | 15.8 | 117.7 | 33.8 | 0 | 0 | 0.3 |  | 167.9 | 1 | 24628 Orange OTI POP Refresh Project (Main PID)
24647 | 24647 Orange SB ACX Scenario 22 Planeta BCN FFP 1 MS | Oliver, Juan | Awarded | Complete | Green | 2016-09-21 | 2016-10-18 | 2016-12-06 |  |  | 0% | 14% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 7957 | 7957 | 0 | 0 | 4107 | -4107 | 1121 | 5227 | -5227 | 7957 | 2730 | 20% | 34% | 1121 | 14% | 0 | 0 | 0 | 1121 | 1121 | -1121 | 0 | 0 | 0 | 0 | 0 | 4107 | 0 | -4107 | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.9 | 1 | 24647 Orange SB ACX Scenario 22 Planeta BCN FFP 1 MS
24648 | 24648 Orange SB ACX Scenarios 23 Malaga 23 Sevilla 23 Valencia Huawei 3Quotes | Oliver, Juan | Awarded | Complete | Green | 2016-09-20 | 2016-10-23 | 2017-03-31 |  |  | 25% | 59% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 24031 | 14064 | 9967 | 0 | 4670 | -4670 | 481 | 5151 | -5151 | 24031 | 18881 | 20% | 79% | 1037 | 59% | 0 | 556 | -556 | 481 | 1037 | -1037 | 0 | 0 | 0 | 0 | 0 | 4113 | 0 | -4113 | 4 | 4 | 1 | 3 | 0 | 0 | 0 | 1 | 0 | 0% | 33% | 1.9 | 0 | 0 | 1 | 0 | 0 | 0 |  | 2.9 | 1 | 24648 Orange SB ACX Scenarios 23 Malaga 23 Sevilla 23 Valencia Huawei 3Quotes
24651 | 24651 Orange SB ACX Scenario 14 DSI BCN FFP 1MS | Oliver, Juan | Awarded | Complete | Green | 2016-10-19 | 2016-11-08 | 2017-01-13 |  |  | 17% | 18% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  |  | 5273 | 5273 | 0 | 0 | 2424 | -2424 | 852 | 3275 | -3275 | 5273 | 1998 | 20% | 38% | 1031 | 18% | 0 | 179 | -179 | 852 | 1031 | -1031 | 0 | 0 | 0 | 0 | 0 | 2244 | 0 | -2244 | 3 | 3 | 0.5 | 2.5 | 0 | 0 | 0 | 0.5 | 0 | 0% | 20% | 0.1 | 0 | 0 | 0.5 | 0 | 0 | 0 |  | 0.6 | 1 | 24651 Orange SB ACX Scenario 14 DSI BCN FFP 1MS
24654 | 24654 Blackberry Contrail Assesment and POC | Hassan, Saqib | Awarded | In Progress | Green | 2017-04-27 | 2017-05-22 | 2017-08-31 | 2017-11-09 | 2017-07-21 | 24% | 28% | 0% | Under/Not Over budget | AMER | CANADA | Canada | SDN |  |  | Bell Canada - Customer | Blackberry- End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 70048 | 0 | 70048 | 48061 | 6252 | 41809 | 19732 | 25984 | 22077 | 21987 | 44064 | 34% | 63% | 21194 | 28% | 43271 | 5911 | 37360 | 15283 | 21194 | 22077 | 4790 | 341 | 4449 | 0 | 0 | 0 | 0 | 0 | 29 | 29 | 7.1 | 22 | 0 | 29 | 29 | 3.2 | 25.8 | 154733% | 154733% | 2.7 | 0 | 3.9 | 3.2 | 0 | 0 | 0 |  | 9.8 | 1 | 24654 Blackberry Contrail Assesment and POC
24669 | 24669 T-Systems JSA Support T&M Consulting 5 Days | M, Rahimunnisa | Awarded | On Hold | Green | 2016-09-16 |  | 2017-08-31 | 2017-08-31 | 2017-06-23 | 31% | 7% | 0% |  | EMEA | ENA-R-NORTH | Belgium | Network Automation |  |  | DEUTSCHE TELEKOM AG (T-SYSTEMS INTERNATIONAL GMBH)-EndUser | EUROPEAN COMMISSION- S TESTA-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 14438 | 0 | 14438 | 10338 | 660 | 9678 | 4209 | 4868 | 5470 | 4100 | 9569 | 59% | 66% | 2118 | 7% | 7588 | 660 | 6928 | 1459 | 2118 | 5470 | 2750 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 1.6 | 3.4 | 0 | 0 | 0 | 1.6 | 0 | 0% | 45% | 0.1 | 0 | 0 | 1.6 | 0 | 0 | 0 |  | 1.7 | 1 | 24669 T-Systems JSA Support T&M Consulting 5 Days
24672 | 24672 Djezzy Junos Space CSD + PM Reporting FFP 3 MS + 4 days T&M | Chouaieb, Mejda | Awarded | In Progress | Green | 2017-02-14 | 2017-03-16 | 2017-08-31 |  | 2017-06-30 | 42% | 42% | 0% | Under/Not Over budget | EMEA | ENA-R-SOUTH | Algeria | Network Automation |  |  | NOKIA CORPORATION-Customer | Djezzy | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 60079 | 0 | 60079 | 39050 | 10465 | 28585 | 12380 | 22845 | 16205 | 21029 | 37234 | 20% | 62% | 13605 | 42% | 29810 | 8512 | 21298 | 5093 | 13605 | 16205 | 9240 | 1953 | 7287 | 0 | 0 | 0 | 0 | 0 | 29.7 | 29.7 | 12.6 | 17.2 | 0 | 11.4 | 11.4 | 6.6 | 4.9 | 63% | 63% | 7.3 | 2.6 | 5.5 | 6.6 | 0 | 0 | 0.5 |  | 22.5 | 1 | 24672 Djezzy Junos Space CSD + PM Reporting FFP 3 MS + 4 days T&M
24683 | 24683 Telstra - FAE UAE Phase 2 SAD - T&M | Davis, Joseph | Awarded | On Hold | Amber | 2016-11-28 | 2016-11-28 | 2017-09-29 |  | 2017-07-07 | 49% | 3% | 0% | Resource Issues | APAC | ANZ | Australia | Core & Edge |  |  | TELSTRA CORPORATION-Customer | TELSTRA CORPORATION LIMITED-EndUser | PO | Milestone Payments | Consulting – T & M |  | B | 122841 | 45861 | 76980 | 99690 | 50606 | 49084 | 36087 | 86693 | 12997 | 23151 | 36148 | 26% | 29% | 7543 | 3% | 67500 | 3646 | 63854 | 3897 | 7543 | 59957 | 32190 | 0 | 32190 | 0 | 0 | 46960 | 0 | -46960 | 75 | 75 | 36.7 | 38.3 | 0 | 0 | 0 | 4.1 | 0 | 0% | 6% | 0 | 0.1 | 32.6 | 4.1 | 0 | 0 | 0 |  | 36.8 | 1 | 24683 Telstra - FAE UAE Phase 2 SAD - T&M
24698 | 24698 AON - LAN Refresh Phase 2 - FFP | Jacobs, Christo | Awarded | In Progress | Amber | 2016-12-26 | 2016-11-30 | 2017-08-31 |  | 2017-07-21 | 63% | -54% | -33% | Scoping Issues | APAC | ANZ | Australia | Cloud |  |  | WESTCON GROUP PTE LTD - Customer | AON CORPORATION AUSTRALIA LIMITED - Enduser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 83882 | 68350 | 15532 | 66120 | 89534 | -23414 | 21771 | 111306 | -45186 | 17762 | -27423 | 21% | -33% | 75276 | -54% | 50400 | 69225 | -18825 | 6051 | 75276 | -24876 | 15720 | 0 | 15720 | 0 | 0 | 20309 | 0 | -20309 | 56 | 74.6 | 47.1 | 27.5 | -18.625 | 40 | 54.7 | 18.9 | 21.1 | 250% | 274% | 0 | 21.5 | 26.6 | 18.9 | 0 | 0 | 1.6 |  | 68.6 | 1 | 24698 AON - LAN Refresh Phase 2 - FFP
24701 | 24701 Orange SB ACX Scenario 19 Ibertic Castellon | Oliver, Juan | Awarded | Complete | Green | 2016-10-30 | 2016-10-23 | 2016-11-30 |  |  | 0% | 12% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 7955 | 7955 | 0 | 0 | 4076 | -4076 | 1300 | 5376 | -5376 | 7955 | 2579 | 20% | 32% | 1300 | 12% | 0 | 0 | 0 | 1300 | 1300 | -1300 | 0 | 0 | 0 | 0 | 0 | 4076 | 0 | -4076 | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.4 | 1 | 24701 Orange SB ACX Scenario 19 Ibertic Castellon
24702 | 24702 Orange SB ACX Scenario 21 Elecnor Valencia | Oliver, Juan | Awarded | Complete | Green | 2016-09-30 | 2016-10-16 | 2016-11-30 |  |  | 25% | 7% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  |  | 7366 | 7366 | 0 | 0 | 3962 | -3962 | 1422 | 5384 | -5384 | 7366 | 1982 | 20% | 27% | 1978 | 7% | 0 | 556 | -556 | 1422 | 1978 | -1978 | 0 | 0 | 0 | 0 | 0 | 3406 | 0 | -3406 | 4 | 4 | 1 | 3 | 0 | 0 | 0 | 1 | 0 | 0% | 33% | 0.3 | 0 | 0 | 1 | 0 | 0 | 0 |  | 1.3 | 1 | 24702 Orange SB ACX Scenario 21 Elecnor Valencia
24703 | 24703 Orange SB ACX Scenario 23 Valencia Everis | Oliver, Juan | Awarded | Complete | Green | 2016-10-30 | 2016-10-16 | 2016-11-30 |  |  | 0% | 18% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  |  | 7517 | 7517 | 0 | 0 | 3406 | -3406 | 1255 | 4661 | -4661 | 7517 | 2856 | 20% | 38% | 1255 | 18% | 0 | 0 | 0 | 1255 | 1255 | -1255 | 0 | 0 | 0 | 0 | 0 | 3406 | 0 | -3406 | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.5 | 1 | 24703 Orange SB ACX Scenario 23 Valencia Everis
24704 | 24704 Orange SB ACX Scenario 19 Alicante Orange | Oliver, Juan | Awarded | Complete | Green | 2016-09-30 | 2016-11-13 | 2016-12-29 |  |  | 0% | 13% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  |  | 7955 | 7955 | 0 | 0 | 4076 | -4076 | 1255 | 5331 | -5331 | 7955 | 2623 | 20% | 33% | 1255 | 13% | 0 | 0 | 0 | 1255 | 1255 | -1255 | 0 | 0 | 0 | 0 | 0 | 4076 | 0 | -4076 | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.5 | 1 | 24704 Orange SB ACX Scenario 19 Alicante Orange
24705 | 24705 Orange SB ACX Scenario 28 Valencia Orange | Oliver, Juan | Awarded | Complete | Green | 2016-09-30 | 2016-11-20 | 2017-03-15 |  |  | 0% | -27% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  |  | 7366 | 7366 | 0 | 0 | 6502 | -6502 | 1345 | 7847 | -7847 | 7366 | -481 | 20% | -7% | 1345 | -27% | 0 | 0 | 0 | 1345 | 1345 | -1345 | 0 | 0 | 0 | 0 | 0 | 6502 | 0 | -6502 | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.3 | 1 | 24705 Orange SB ACX Scenario 28 Valencia Orange
24706 | 24706 Orange SB ACX Scenario 29 Madrid Orange | Oliver, Juan | Awarded | Complete | Green | 2016-09-22 | 2016-11-15 | 2016-12-27 |  |  | 3% | 10% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 7957 | 7957 | 0 | 0 | 4151 | -4151 | 1390 | 5541 | -5541 | 7957 | 2416 | 20% | 30% | 1435 | 10% | 0 | 45 | -45 | 1390 | 1435 | -1435 | 0 | 0 | 0 | 0 | 0 | 4107 | 0 | -4107 | 4 | 4 | 0.1 | 3.9 | 0 | 0 | 0 | 0.1 | 0 | 0% | 3% | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 |  | 0.1 | 1 | 24706 Orange SB ACX Scenario 29 Madrid Orange
24707 | 24707 Orange SB ACX Scenarios 18 22 Orange Barcelona | Oliver, Juan | Awarded | Complete | Green | 2016-09-21 | 2016-09-15 | 2016-10-31 |  |  | 34% | 21% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 13961 | 13961 | 0 | 0 | 7305 | -7305 | 941 | 8246 | -8246 | 13961 | 5715 | 20% | 41% | 1435 | 21% | 0 | 493 | -493 | 941 | 1435 | -1435 | 0 | 0 | 0 | 0 | 0 | 6812 | 0 | -6812 | 4 | 4 | 1.4 | 2.6 | 0 | 0 | 0 | 1.4 | 0 | 0% | 52% | 0 | 0 | 0 | 1.4 | 0 | 0 | 0 |  | 1.4 | 1 | 24707 Orange SB ACX Scenarios 18 22 Orange Barcelona
24708 | 24708 Orange SB ACX Scenario 28 Zaragoza Orange | Oliver, Juan | Awarded | Complete | Green | 2016-09-21 | 2016-11-09 | 2016-12-21 |  |  | 22% | 12% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 8106 | 8106 | 0 | 0 | 4390 | -4390 | 1121 | 5510 | -5510 | 8106 | 2595 | 20% | 32% | 1435 | 12% | 0 | 314 | -314 | 1121 | 1435 | -1435 | 0 | 0 | 0 | 0 | 0 | 4076 | 0 | -4076 | 4 | 4 | 0.9 | 3.1 | 0 | 0 | 0 | 0.9 | 0 | 0% | 28% | 0 | 0 | 0 | 0.9 | 0 | 0 | 0 |  | 0.9 | 1 | 24708 Orange SB ACX Scenario 28 Zaragoza Orange
24709 | 24709 ORANGE RDC Network Implementation FFP 5 MS | Masci, Fabio | Awarded | In Progress | Amber | 2016-12-07 | 2017-01-09 | 2017-07-31 |  | 2017-06-30 | 112% | 6% | -12% | Customer Issues | EMEA | France | DR of Congo | Security |  |  | INTERDATA-Customer | ORANGE-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 82432 | 73694 | 8738 | 43601 | 46782 | -3181 | 30800 | 77582 | -33981 | 38831 | 4850 | 0% | 6% | 46782 | 6% | 12801 | 46782 | -33981 | 0 | 46782 | -33981 | 0 | 0 | 0 | 0 | 30800 | 0 | 30800 | 0 | 40 | 40 | 44.8 | 0 | -4.8125 | 0 | 0 | 5.9 | 0 | 0% | 15% | 1.1 | 0 | 29.9 | 5.9 | 0 | 6 | 3 |  | 45.9 | 1 | 24709 ORANGE RDC Network Implementation FFP 5 MS
24717 | 24717 University of Washington Automation 5d TE | Wiesner, Jill | Awarded | In Progress | Green | 2017-02-14 | 2017-03-13 | 2017-09-29 | 2017-08-10 | 2017-06-23 | 65% | 18% | 0% | Under/Not Over budget | AMER | US TERRITORIES | United States of America | Network Automation |  |  | Right Systems-Customer | University of Washington- End User | PO | Invoice on Signed Timesheets | Consulting – T & M |  | A | 14375 | 0 | 14375 | 6000 | 3926 | 2074 | 2386 | 6312 | -312 | 8375 | 8063 | 38% | 56% | 4312 | 18% | 4000 | 3926 | 74 | 386 | 4312 | -312 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 3.3 | 1.8 | 0.0025 | 2.5 | 2.5 | 1.4 | 1.1 | 99% | 99% | 1.4 | 0 | 1.9 | 1.4 | 0 | 0 | 0 |  | 4.7 | 1 | 24717 University of Washington Automation 5d TE
24727 | 24727 MEDITEL Design Review and Migration Support FFP 3 MS | Chouaieb, Mejda | Awarded | In Progress | Amber | 2016-10-01 | 2016-10-04 | 2017-07-31 |  | 2017-06-30 | 311% | -63% | -211% | Scoping Issues | EMEA | ENA-R-SOUTH | Algeria | Core & Edge |  |  | ERICSSON-Customer | MEDITEL-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 17318 | 13243 | 4075 | 10995 | 24838 | -13843 | 0 | 24838 | -13843 | 6323 | -7520 | 20% | -43% | 24838 | -63% | 10995 | 24838 | -13843 | 0 | 24838 | -13843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.2 | 11.2 | 34.9 | 0 | -23.7175 | 0 | 0 | 17.7 | 0 | 0% | 103% | 0.3 | 0 | 17.3 | 17.7 | 0 | 0 | 0 |  | 35.2 | 1 | 24727 MEDITEL Design Review and Migration Support FFP 3 MS
24729 | 24729 GACA KKIA Switching PS Consultancy NET2 T&M 5days | Subramaniam, Ragunath | Awarded | In Progress | Green | 2016-12-08 | 2016-12-05 | 2017-07-31 |  | 2017-06-19 | 116% | 23% | -16% |  | EMEA | MEA | Saudi Arabia | Core & Edge |  |  | MINDWARE S.A.-Customer | GACA-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 15560 | 15560 | 0 | 8288 | 4486 | 3802 | 700 | 5186 | 3102 | 7272 | 10374 | 44% | 67% | 4486 | 23% | 7588 | 4486 | 3102 | 0 | 4486 | 3102 | 700 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5.8 | 0 | -0.78125 | 0 | 0 | 3.5 | 0 | 0% | 157% | 0 | 0 | 2.3 | 3.5 | 0 | 0 | 0 |  | 5.8 | 1 | 24729 GACA KKIA Switching PS Consultancy NET2 T&M 5days
24739 | 24739 Orange SB ACX Scenario 14-14-32 Cesca BCN Cerdanyola Castelldefels | Oliver, Juan | Awarded | Booked | Green | 2016-09-30 | 2016-10-25 | 2017-08-31 |  |  | 0% | -20% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 19696 | 0 | 19696 | 0 | 8554 | -8554 |  |  |  | 19696 |  | 20% | 0% |  | -20% | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 8554 | 0 | -8554 | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 24739 Orange SB ACX Scenario 14-14-32 Cesca BCN Cerdanyola Castelldefels
24741 | 24741 Orange SB ACX Scenario 19 Murcia ISGF | Oliver, Juan | Awarded | Complete | Green | 2016-09-30 | 2016-10-26 | 2017-01-04 |  |  | 0% | 13% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 7955 | 7955 | 0 | 0 | 4076 | -4076 | 1255 | 5331 | -5331 | 7955 | 2623 | 20% | 33% | 1255 | 13% | 0 | 0 | 0 | 1255 | 1255 | -1255 | 0 | 0 | 0 | 0 | 0 | 4076 | 0 | -4076 | 4 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.5 | 1 | 24741 Orange SB ACX Scenario 19 Murcia ISGF
24748 | 24748 MGM - DNI Firewall - FFP | Jacobs, Christo | Awarded | In Progress | Green | 2016-10-20 | 2016-10-31 | 2017-09-29 |  | 2017-07-21 | 72% | 42% | -65% | Scoping Issues | APAC | Greater China | Macau | Security |  |  | CYBERWORLD ASIA (BVI) HOLDINGS COMPANY LIMITED-Customer | MGM GRAND PARADISE LIMITED-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 74083 | 35290 | 38793 | 67600 | 12976 | 54624 | 23849 | 36826 | 30774 | 6483 | 37257 | 9% | 50% | 16190 | 42% | 48000 | 11940 | 36060 | 4249 | 16190 | 31810 | 19600 | 0 | 19600 | 0 | 0 | 1036 | 0 | -1036 | 58 | 95.8 | 68.7 | 27.1 | -37.8125 | 7.9 | 14.5 | 27.2 | 0 | 16% | 40% | 0 | 2.3 | 41.5 | 27.2 | 0 | 0 | 0 |  | 70.9 | 2 | 24748 MGM - DNI Firewall - FFP
24752 | 24752 Iowa Communications Network 100 PS Credits | Akiyama, Mauricio | Awarded | Booked | Green | 2016-12-01 | 2016-12-01 | 2017-11-30 |  | 2017-06-07 | 0% | 100% | 0% |  | AMER | US TERRITORIES | United States of America | Core & Edge |  |  | CENTURYLINK, INC.-Customer | IOWA COMMUNICATIONS NETWORK-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | B | 198000 | 198000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198000 | 198000 | 0% | 100% | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0.0025 | 0 | 0 | 0 | 0 | 1% | 1% | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2.8 | 1 | 24752 Iowa Communications Network 100 PS Credits
24767 | 24767 OSP SB Badajoz POP Full Routing Implementation FFP 1MS | Oliver, Juan | Awarded | Complete | Green | 2016-10-19 | 2016-11-06 | 2016-11-18 |  |  | 150% | 36% | -50% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  |  | 9095 | 9095 | 0 | 0 | 1985 | -1985 | 0 | 1985 | -1985 | 9095 | 7110 | 42% | 78% | 1985 | 36% | 0 | 1985 | -1985 | 0 | 1985 | -1985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 4.5 | 0 | -1.5 | 0 | 0 | 4.5 | 0 | 0% | 0% | 0 | 0 | 0 | 4.5 | 0 | 0 | 0 |  | 4.5 | 1 | 24767 OSP SB Badajoz POP Full Routing Implementation FFP 1MS
24775 | 24775 MASMOVIL MPLS Backbone T&M 23 days | Subramaniam, Ragunath | Awarded | In Progress | Green | 2016-09-16 | 2016-09-20 | 2017-05-30 |  | 2017-06-19 | 48% | 17% | -110% |  | EMEA | Spain | Spain | Core & Edge |  |  | SATEC, S. A.-Customer | Masmovil-Customer | PO | Invoice on Signed Timesheets | Consulting – T & M |  | A | 67483 | 43672 | 23811 | 37503 | 12087 | 25416 | 13902 | 25989 | 11514 | 29980 | 41494 | 44% | 61% | 23389 | 17% | 34903 | 11770 | 23133 | 11619 | 23389 | 11514 | 2600 | 316 | 2284 | 0 | 0 | 0 | 0 | 0 | 20 | 42 | 20 | 22 | -22 | 0 | 11 | 2.8 | 0 | 0% | 35% | 0 | 2 | 17.3 | 2.8 | 0 | 0 | 0 |  | 22 | 1 | 24775 MASMOVIL MPLS Backbone T&M 23 days
24777 | 24777 Orange SB ACX Scenarios 26 19 Santander Fundacion | Oliver, Juan | Awarded | In Progress | Green | 2016-09-26 | 2016-10-24 | 2017-09-29 |  |  | 44% | 21% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 16286 | 7231 | 9055 | 6438 | 8779 | -2341 | 807 | 9586 | -3148 | 9848 | 6700 | 20% | 41% | 1435 | 21% | 0 | 628 | -628 | 807 | 1435 | -1435 | 0 | 0 | 0 | 0 | 6438 | 8152 | 0 | -1714 | 4 | 4 | 1.8 | 2.3 | 0 | 0 | 0 | 1.8 | 0 | 0% | 78% | 0 | 0 | 0 | 1.8 | 0 | 0 | 0 |  | 1.8 | 1 | 24777 Orange SB ACX Scenarios 26 19 Santander Fundacion
24791 | 24791 Nyherji, Data Center Consolidated Design FFP 1 MS | Masci, Fabio | Awarded | Booked | Green | 2017-06-13 | 2017-08-21 | 2017-08-31 |  | 2017-06-30 | 0% | 25% | 0% |  | EMEA | ENA-R-NORTH | Iceland | Core & Edge | Core & Edge |  | SEC DATACOM HOLDING APS-Customer | NYHERJI Customer | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 17203 | 0 | 17203 | 11087 | 0 | 11087 | 8304 | 8304 | 2783 | 6116 | 8899 | 27% | 52% | 4944 | 25% | 7727 | 0 | 7727 | 4944 | 4944 | 2783 | 3360 | 0 | 3360 | 0 | 0 | 0 | 0 | 0 | 8.2 | 8.2 | 0 | 8.2 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.5 | 1 | 24791 Nyherji, Data Center Consolidated Design FFP 1 MS
24805 | 24805 IPC Network - BTI Project - FFP | Chin, Soon Hwa | Awarded | In Progress | Green | 2016-08-30 | 2016-10-21 | 2017-07-14 |  | 2017-07-05 | 50% | 49% | -100% | Under/Not Over budget | APAC | ASEAN | Singapore | Cloud |  |  | IPC NETWORK SERVICES ASIA LIMITED-EndUser | IPC NETWORK SERVICES ASIA LIMITED-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 14100 | 4800 | 9300 | 10000 | 1622 | 8378 | 1280 | 2902 | 7098 | 4100 | 11198 | 30% | 79% | 2560 | 49% | 10000 | 1280 | 8720 | 1280 | 2560 | 7440 | 0 | 0 | 0 | 0 | 0 | 342 | 0 | -342 | 2 | 4 | 2 | 2 | -2 | 0 | 2 | 0 | 0 | 0% | 100% | 0 | 0 | 2 | 0 | 0 | 0 | 0 |  | 2 | 1 | 24805 IPC Network - BTI Project - FFP
24808 | 24808 Starhub - BTI Project - FFP | Ang, Soon Aun | Awarded | In Progress | Green | 2016-08-30 | 2015-10-23 | 2017-09-30 |  | 2017-07-21 |  | 62% | 0% | Under/Not Over budget | APAC | ASEAN | Singapore | Cloud |  |  | STARHUB LTD-EndUser | STARHUB LTD-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | D | 433608 | 224398 | 209210 | 360000 | 16880 | 343120 | 60000 | 76880 | 283120 | 73608 | 356728 | 20% | 82% | 16880 | 62% | 300000 | 16880 | 283120 | 0 | 16880 | 283120 | 30000 | 0 | 30000 | 0 | 30000 | 0 | 30000 | 0 | 0 | 0 | 171.9 | 0 | -171.875 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 1 | 166.8 | 0 | 0 | 0.4 | 4.8 |  | 172.9 |  | 24808 Starhub - BTI Project - FFP
24818 | 24818 Singtel - PS Credits - Sep 2016 - T&M | Pathak, Nishant | Awarded | In Progress | Green | 2016-11-14 | 2017-05-01 | 2017-09-29 |  |  | 0% | -40% | 0% |  | APAC | ASEAN | Singapore | Core & Edge |  |  | NERA TELECOMMUNICATIONS LTD-Customer | SINGAPORE TELECOMMUNICATIONS LIMITED-EndUser | PO | Upon Completion | Consulting – T & M |  | A | 24000 | 0 | 24000 | 14400 | 14400 | 0 |  |  |  | 9600 |  | 40% | 0% |  | -40% | 14400 | 0 | 14400 |  |  |  | 0 | 0 | 0 | 0 | 0 | 14400 | 0 | -14400 | 13.5 | 13.5 | 0 | 13.5 | 0 | 13.5 | 13.5 | 0 | 13.5 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 26895 Singtel - PS Credits Container Project | 24818 Singtel - PS Credits - Sep 2016 - T&M
24827 | 24827 MPO HPE T&M Consulting Support | Wiesner, Jill | Awarded | On Hold | Green | 2017-03-17 | 2017-11-06 | 2017-11-10 | 2018-03-16 | 2017-06-01 | 6% | 13% | 0% | Under/Not Over budget | AMER | NATIONAL GOVERNMENT | United States of America | Cloud |  |  | MARYLAND PROCUREMENT OFFICE-EndUser | MARYLAND PROCUREMENT OFFICE-EndUser | PO | Monthly in Arrears | Consulting – T & M |  | A | 9900 | 0 | 9900 | 5950 | 394 | 5556 | 4932 | 5326 | 624 | 3950 | 4574 | 33% | 46% | 5326 | 13% | 5950 | 394 | 5556 | 4932 | 5326 | 624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0.3 | 4.7 | 0 | 0 | 0 | 0.3 | 0 | 0% | 7% | 0.3 | 0 | 0 | 0.3 | 0 | 0 | 0 |  | 0.6 | 1 | 24827 MPO HPE T&M Consulting Support
24836 | 24836 - Arkansas Department of Information Systems BTI Implementation | Meyer, James | Awarded | In Progress | Green | 2017-05-18 | 2017-06-07 | 2017-07-28 | 2017-11-24 | 2017-07-17 | 36% | 38% | 0% |  | AMER | US TERRITORIES | United States of America | Core & Edge |  |  | State of Arkansas | State of Arkansas | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 25110 | 0 | 25110 | 15850 | 300 | 15550 | 5650 | 5950 | 9900 | 9260 | 19160 | 38% | 76% | 300 | 38% | 10200 | 300 | 9900 | 0 | 300 | 9900 | 4450 | 0 | 4450 | 0 | 1200 | 0 | 1200 | 0 | 1 | 1 | 0.4 | 0.7 | 0 | 1 | 1 | 0.4 | 0.6 | 7179% | 7179% | 1.4 | 0 | 0 | 0.4 | 0 | 0 | 0 |  | 1.8 | 1 | 24836 - Arkansas Department of Information Systems BTI Implementation
24843 | 24843 Raytheon Company Campus & Branch - T&M | Wiesner, Jill | Awarded | On Hold | Green | 2016-12-19 | 2016-11-28 | 2017-07-31 | 2017-07-31 | 2017-06-06 | 42% | 27% | 0% | Under/Not Over budget | AMER | NATIONAL GOVERNMENT | United States of America | Core & Edge |  |  | RAYTHEON COMPANY-Customer | RAYTHEON COMPANY-EndUser | PO | Monthly in Arrears | Consulting – T & M |  | A | 85500 | 0 | 85500 | 64678 | 22291 | 42387 | 19081 | 41372 | 23306 | 20822 | 44128 | 25% | 52% | 21947 | 27% | 45253 | 14805 | 30448 | 7142 | 21947 | 23306 | 19425 | 7486 | 11939 | 0 | 0 | 0 | 0 | 0 | 38 | 38 | 15.9 | 22.2 | -0.00125 | 24.9 | 24.9 | 4.6 | 20.2 | 189% | 189% | 4.3 | 10.1 | 11.3 | 4.6 | 0 | 0 | 0 |  | 30.3 | 1 | 24843 Raytheon Company Campus & Branch - T&M
24863 | 24863 CBSi QFabric Replacement | Jeffries, Stephanie | Awarded | In Progress | Green | 2017-03-23 | 2017-05-22 | 2017-10-27 | 2017-10-28 | 2017-07-23 | 23% | -29% | -121% | Under/Not Over budget | AMER | US TERRITORIES | United States of America | Cloud |  |  | MYRIAD SUPPLY COMPANY, LLC | CBS INTERACTIVE-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 262416 | 0 | 262416 | 146551 | 54204 | 92347 | 169729 | 223933 | -77382 | 115865 | 38483 | 44% | 15% | 204733 | -29% | 127351 | 51108 | 76242 | 153624 | 204733 | -77382 | 19200 | 3095 | 16105 | 0 | 0 | 0 | 0 | 0 | 87 | 192.1 | 43.9 | 148.3 | -105.125 | 0 | 46.1 | 5.6 | 0 | 0% | 32% | 6.4 | 3.6 | 32.8 | 5.6 | 2.6 | 0 | 2.9 |  | 53.9 | 2 | 24863 CBSi QFabric Replacement
24865 | 24865 TWM - MBH - FFP | Jacobs, Christo | Awarded | In Progress | Amber | 2016-09-27 | 2016-09-23 | 2017-09-22 |  | 2017-07-21 | 77% | -36% | -72% | Scoping Issues | APAC | Greater China | Taiwan | Core & Edge |  |  | COMMVERGE SOLUTIONS LIMITED-Customer | TAIWAN MOBILE CO., LTD.-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 213156 | 58854 | 154302 | 142620 | 169337 | -26717 | 49406 | 218743 | -76123 | 70536 | -5587 | 33% | -3% | 189650 | -36% | 130500 | 152364 | -21864 | 37286 | 189650 | -59150 | 12120 | 0 | 12120 | 0 | 0 | 16972 | 0 | -16972 | 145 | 249.4 | 192.9 | 56.5 | -104.375 | 13.5 | 29.7 | 28 | 0 | 10% | 14% | 0 | 8.8 | 164.9 | 28 | 0 | 0 | 0 |  | 201.6 | 2 | 24865 TWM - MBH - FFP
24873 | 24873-ATTM TP&E EXN SRX Conversion Engineering Audit 2017 | Charleville, Vann | Awarded | Booked | Green | 2017-06-13 | 2017-08-14 | 2017-12-29 |  | 2017-07-12 | 0% | 21% | 0% | Under/Not Over budget | AMER | AT&T | United States of America | Security |  |  | AT&T MOBILITY, LLC.-EndUser | AT&T MOBILITY, LLC.-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 251332 | 0 | 251332 | 148457 | 0 | 148457 | 97370 | 97370 | 51087 | 102875 | 153962 | 40% | 61% | 97370 | 21% | 148457 | 0 | 148457 | 97370 | 97370 | 51087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 128 | 0 | 128 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.6 | 1 | 24873-ATTM TP&E EXN SRX Conversion Engineering Audit 2017
24879 | 24879 Telefonica Colombia Security | Almanza, Henry | Awarded | In Progress | Green | 2016-12-14 | 2017-01-02 | 2017-08-31 | 2017-04-11 | 2017-07-21 | 77% | 23% | -147% | Product Issues | AMER | CALA | Colombia | Security |  |  | IBM-Customer | TELEFONICA COLOMBIA-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | B | 40000 | 40000 | 0 | 28635 | 17681 | 10954 | 1168 | 18848 | 9787 | 11365 | 21152 | 30% | 53% | 18848 | 23% | 28635 | 17681 | 10954 | 1168 | 18848 | 9787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 42 | 32.4 | 9.6 | -24.9962 | 0 | 9.8 | 9.1 | 0 | 0% | 30% | 7.2 | 0 | 16.6 | 9.1 | 0 | 0 | 6.8 |  | 39.6 | 1 | 24879 Telefonica Colombia Security
24882 | 24882 CRITEO T&M 8 Days | M, Rahimunnisa | Awarded | Booked | Green | 2017-03-20 |  | 2017-08-31 |  | 2017-06-23 | 16% | 18% | 0% |  | EMEA | France | France | Security |  |  | AVNET INC.-Customer | CRITEO - End User | PO | Fully in Advance | Consulting – T & M |  | A | 23899 | 0 | 23899 | 9278 | 641 | 8637 | 8063 | 8704 | 574 | 14621 | 15195 | 46% | 64% | 6304 | 18% | 6878 | 641 | 6237 | 5663 | 6304 | 574 | 2400 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 1.3 | 6.7 | 0 | 0 | 0 | 1.2 | 0 | 0% | 17% | 0.1 | 0 | 0.1 | 1.2 | 0 | 0 | 0 |  | 1.4 | 1 | 24882 CRITEO T&M 8 Days
24886 | 24886 OSP SB POP Full Routing Implementation FFP 3 MS | Oliver, Juan | Awarded | Complete | Green | 2016-12-09 | 2017-01-01 | 2017-03-10 |  |  | 63% | 18% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 13882 | 13882 | 0 | 2872 | 6279 | -3407 | 0 | 6279 | -3407 | 11010 | 7603 | 36% | 55% | 1183 | 18% | 2872 | 1183 | 1689 | 0 | 1183 | 1689 | 0 | 0 | 0 | 0 | 0 | 5097 | 0 | -5097 | 3.4 | 3.4 | 2.1 | 1.3 | 0 | 0 | 0 | 2.1 | 0 | 0% | 167% | 1.6 | 0 | 0 | 2.1 | 0 | 0 | 0 |  | 3.8 | 1 | 24886 OSP SB POP Full Routing Implementation FFP 3 MS
24891 | 24891 University of Oregon Onboarding | Jeffries, Stephanie | Awarded | In Progress | Green | 2016-09-30 | 2016-12-12 | 2017-09-15 |  | 2017-07-23 | 64% | -12% | -262% | Customer Issues | AMER | US TERRITORIES | United States of America | Core & Edge |  |  | STRUCTURED COMMUNICATION SYSTEMS INC-Customer | University of Oregon - End User | PO | Upon Completion | Consulting – Packaged |  | B | 75050 | 0 | 75050 | 33600 | 40515 | -6915 | 22138 | 62653 | -29053 | 41450 | 12397 | 29% | 17% | 56953 | -12% | 27900 | 39487 | -11587 | 17466 | 56953 | -29053 | 5700 | 1028 | 4672 | 0 | 0 | 0 | 0 | 0 | 15 | 54.5 | 34.8 | 19.7 | -39.4875 | 0 | 28.8 | 11.2 | 0 | 0% | 112% | 1.6 | 1.8 | 9.9 | 11.2 | 11.8 | 0 | 2 |  | 38.2 | 1 | 24891 University of Oregon Onboarding
24892 | 24892 ORANGE LABS T&M 5 Days | M, Rahimunnisa | Awarded | Booked | Green | 2016-09-30 |  | 2017-07-31 |  | 2017-06-23 | 8% | 35% | 0% |  | EMEA | France | France | Core & Edge |  |  | Orange-Customer | ORANGE SA-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 15750 | 0 | 15750 | 0 | 158 | -158 | 2071 | 2229 | -2229 | 15750 | 13521 | 51% | 86% | 2229 | 35% | 0 | 158 | -158 | 2071 | 2229 | -2229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0.4 | 4.6 | 0 | 0 | 0 | 0.4 | 0 | 0% | 8% | 0.1 | 0 | 0 | 0.4 | 0 | 0 | 0 |  | 0.4 | 1 | 24892 ORANGE LABS T&M 5 Days
24907 | 24907 OSP SB Castellon Full Routing FFP 2MS | Oliver, Juan | Awarded | Complete | Green | 2016-10-12 | 2016-11-06 | 2016-11-18 |  |  | 88% | 35% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 9115 | 0 | 9115 | 2357 | 2540 | -183 | 166 | 2707 | -350 | 6758 | 6409 | 35% | 70% | 1330 | 35% | 2357 | 1164 | 1193 | 166 | 1330 | 1027 | 0 | 0 | 0 | 0 | 0 | 1376 | 0 | -1376 | 3 | 3 | 2.6 | 0.4 | 0 | 0 | 0 | 2.6 | 0 | 0% | 700% | 0 | 0 | 0 | 2.6 | 0 | 0 | 0 |  | 2.6 | 1 | 24907 OSP SB Castellon Full Routing FFP 2MS
24915 | 24915 VZW FFP SoVA SAEGW-SPGW-Conversion | Stroud, Charlie | Awarded | In Progress | Green | 2016-10-06 | 2016-10-17 | 2017-06-30 |  |  | 96% | 20% | 0% |  | AMER | VERIZON | United States of America | Cloud |  |  | VERIZON WIRELESS-EndUser | VERIZON WIRELESS-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | B | 1200000 | 0 | 1200000 | 510000 | 430440 | 79560 | 11500 | 441940 | 68060 | 690000 | 758060 | 43% | 63% | 441940 | 20% | 510000 | 430440 | 79560 | 11500 | 441940 | 68060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 380.1 | 380.1 | 366 | 14.1 | 0.00125 | 0 | 0 | 174.9 | 0 | 0% | 85% | 4.3 | 0 | 191.1 | 174.9 | 0 | 0 | 0 |  | 370.3 | 1 | 24915 VZW FFP SoVA SAEGW-SPGW-Conversion
24922 | 24922 Telecom Italia TIM SRX5800 SecGW upgrade and roll-out T&M 30 days (FOC) | Ferrari, Lenora | Awarded | In Progress | Green |  | 2016-10-03 | 2017-09-29 |  | 2017-05-02 | 65% | 0% | 0% |  | EMEA | ENA-R-SOUTH | Italy | Security |  |  | Juniper | Telecom Italia - EndUser | Free of Charge | None | Consulting – T & M |  | A | 0 | 0 | 0 | 7300 | 12954 | -5654 | 12514 | 25468 | -18168 | -7300 | -25468 | 0% | 0% | 18168 | 0% | 0 | 12954 | -12954 | 5214 | 18168 | -18168 | 7300 | 0 | 7300 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 19.6 | 10.4 | 0 | 0 | 0 | 4.1 | 0 | 0% | 16% | 0 | 2.9 | 15.5 | 4.1 | 0 | 0 | 0 |  | 22.5 | 1 | 24922 Telecom Italia TIM SRX5800 SecGW upgrade and roll-out T&M 30 days (FOC)
24935 | 24935 - Goldman Sachs Additional 5 FW Conversions | Kouzionis, Nicholas | Awarded | In Progress | Green | 2016-11-10 | 2016-09-30 | 2017-11-30 | 2017-03-31 | 2017-06-16 | 80% | 21% | -20% | Customer Issues | AMER | GLOBAL FINANCIAL SERVICES | United States of America | Security |  |  | DIMENSION DATA HOLDINGS LTD-Customer | GOLDMAN SACHS-EndUser | PO |  | Consulting – Fixed Price Custom |  | B | 100320 | 81761 | 18559 | 68900 | 41875 | 27025 | 6057 | 47932 | 20968 | 31420 | 52388 | 31% | 52% | 47932 | 21% | 68900 | 41875 | 27025 | 6057 | 47932 | 20968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 57.6 | 46 | 11.6 | -9.6212 | 4.1 | 6.1 | 10.6 | 0 | 9% | 23% | 4.9 | 0 | 32.4 | 10.6 | 0 | 3 | 0 |  | 50.9 | 1 | 24935 - Goldman Sachs Additional 5 FW Conversions
24946 | 24946 OSP Resiliency T&M CONSULTING 3 Days | Oliver, Juan | Awarded | Complete | Green | 2016-11-15 | 2017-03-08 | 2017-07-31 |  |  | 100% | 27% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Fully in Advance | Consulting – T & M |  | A | 6600 | 0 | 6600 | 3439 | 1669 | 1770 | 0 | 1669 | 1770 | 3161 | 4931 | 48% | 75% | 1669 | 27% | 3439 | 1669 | 1770 | 0 | 1669 | 1770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0% | 0% | 0.1 | 0 | 0 | 3 | 0 | 0 | 0 |  | 3.1 | 1 | 24946 OSP Resiliency T&M CONSULTING 3 Days
24953 | 24953 Lazada - IP Fabric - FFP | Pathak, Nishant | Awarded | In Progress | Green | 2016-09-29 | 2016-11-14 | 2017-08-17 |  | 2017-07-07 | 53% | 24% | 0% |  | APAC | Greater China | Taiwan | Cloud |  |  | COMMVERGE SOLUTIONS LIMITED-Customer | LAZADA TAIWAN-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 54668 | 0 | 54668 | 46193 | 11180 | 35013 | 21736 | 32915 | 13278 | 8475 | 21753 | 16% | 40% | 20622 | 24% | 33900 | 11180 | 22720 | 9443 | 20622 | 13278 | 12293 | 0 | 12293 | 0 | 0 | 0 | 0 | 0 | 46 | 46 | 24.5 | 21.5 | 0 | 11.8 | 11.8 | 10 | 1.8 | 35% | 35% | 0 | 0 | 14.5 | 10 | 0 | 0 | 0 |  | 24.5 | 1 | 24953 Lazada - IP Fabric - FFP
24979 | 24979 GTT 20 PS Credits | LaSalle, Glenn | Awarded | Booked | Green |  | 2017-01-11 | 2018-01-11 |  |  | 0% | 65% | 0% | Under/Not Over budget | AMER | US TERRITORIES |  | Cloud |  |  | GTT COMMUNICATIONS, INC.-Customer | GTT-EndUser | PO | Fully in Advance | Consulting – Packaged |  | A | 39600 | 39600 | 0 | 0 | 0 | 0 | 14019 | 14019 | -14019 | 39600 | 25581 | 0% | 65% | 14019 | 65% | 0 | 0 | 0 | 14019 | 14019 | -14019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 20 | 0.0025 | 0 | 0 | 0 | 0 | 0% | 0% | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.4 | 1 | 24979 GTT 20 PS Credits
24987 | 24987 Algar Risk Analysis | Barbieri De Sousa, Alexandre | Awarded | In Progress | Green | 2016-09-30 | 2017-02-20 | 2017-09-29 |  |  | 77% | 29% | 0% |  | AMER | CALA | Brazil | Core & Edge |  |  | BINARIO DISTRIBUIDORA DE EQUIP. ELETRONICOS LTDA-Customer | Algar Telecom-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 30000 | 0 | 30000 | 0 | 11277 | -11277 | 1582 | 12859 | -12859 | 30000 | 17141 | 28% | 57% | 12859 | 29% | 0 | 11277 | -11277 | 1582 | 12859 | -12859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14 | 10.8 | 3.3 | 0 | 0 | 0 | 3.1 | 0 | 0% | 29% | 1.8 | 0 | 7.6 | 3.1 | 0 | 0 | 0 |  | 12.5 | 1 | 24987 Algar Risk Analysis
24991 | 24991 Sempra RB Core Replacement | Jeffries, Stephanie | Awarded | In Progress | Amber | 2017-05-01 | 2017-04-10 | 2017-12-29 |  | 2017-07-23 | 44% | -152% | -222% | Scoping Issues | AMER | US TERRITORIES | United States of America | Core & Edge | Security |  | IBM ARGENTINA S.A.-Customer | SEMPRA ENERGY-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 119700 | 70706 | 48994 | 183417 | 138473 | 44944 | 120349 | 258822 | -75405 | -63717 | -139122 | 36% | -116% | 233212 | -152% | 157807 | 134236 | 23571 | 98976 | 233212 | -75405 | 25610 | 4237 | 21373 | 0 | 0 | 0 | 0 | 0 | 80.1 | 257.9 | 113 | 144.9 | -177.8462 | 0 | 38.6 | 18.6 | 0 | 0% | 18% | 36.8 | 13.3 | 94.4 | 18.6 | 0 | 0 | 0 |  | 163 | 2 | 24991 Sempra RB Core Replacement
24992 | 24992 Orange SB ACX Scenario 25 Madrid Tienda Sol | Oliver, Juan | Awarded | Complete | Green | 2016-10-13 | 2016-11-07 | 2017-01-10 |  |  | 56% | -14% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 6146 | 6146 | 0 | 4859 | 3218 | 1641 | 2534 | 5752 | -893 | 1287 | 394 | 20% | 6% | 893 | -14% | 0 | 502 | -502 | 391 | 893 | -893 | 0 | 0 | 0 | 0 | 4859 | 2716 | 2143 | 0 | 2 | 2 | 1.1 | 0.9 | 0 | 0 | 0 | 1.1 | 0 | 0% | 129% | 0 | 0 | 0 | 1.1 | 0 | 0 | 0 |  | 1.1 | 1 | 24992 Orange SB ACX Scenario 25 Madrid Tienda Sol
25007 | 25007 IBM Cloud RMS Boulder | Akiyama, Mauricio | Awarded | In Progress | Green | 2016-11-14 | 2016-11-16 | 2017-11-15 |  | 2017-05-31 | 0% | -11% | 0% |  | AMER | CLOUD PROVIDERS | United States of America | Network Automation |  |  | IBM CORPORATION-EndUser | IBM CORPORATION-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 171185 | 171185 | 0 | 141967 | 141967 | 0 | 130 | 142097 | -130 | 29218 | 29088 | 28% | 17% | 130 | -11% | 0 | 0 | 0 | 130 | 130 | -130 | 0 | 0 | 0 | 0 | 141967 | 141967 | 0 | 0 | 1 | 1 | 0 | 1 | 0.0025 | 0 | 0 | 0 | 0 | 1% | 1% | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.8 | 1 | 25007 IBM Cloud RMS Boulder
25008 | 25008 IBM Cloud RMS RTP | Akiyama, Mauricio | Awarded | In Progress | Green | 2016-11-10 | 2016-11-16 | 2017-11-16 |  | 2017-05-31 | 0% | -1% | 0% |  | AMER | CLOUD PROVIDERS | Remote | Network Automation |  |  | IBM CORPORATION-EndUser | IBM CORPORATION-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 213387 | 213387 | 0 | 156132 | 139427 | 16705 | 16816 | 156243 | -111 | 57255 | 57144 | 28% | 27% | 111 | -1% | 0 | 0 | 0 | 111 | 111 | -111 | 0 | 0 | 0 | 0 | 156132 | 139427 | 16705 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.8 | 1 | 25008 IBM Cloud RMS RTP
25015 | 25015 Skyline Telephone | Meyer, James | Awarded | In Progress | Green | 2017-01-28 | 2017-04-10 | 2017-08-12 |  | 2017-07-21 | 24% | 73% | 0% |  | AMER | CABLES | United States of America | Core & Edge |  |  | Skyline Telephone - End User | Skyline Telephone - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 16226 | 0 | 16226 | 9820 | 200 | 9620 | 0 | 200 | 9620 | 6406 | 16026 | 26% | 99% | 200 | 73% | 9820 | 200 | 9620 | 0 | 200 | 9620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0.3 | 0.8 | 0 | 1 | 1 | 0.3 | 0.8 | 7179% | 7179% | 2.4 | 0 | 0 | 0.3 | 0 | 0 | 0 |  | 2.7 | 1 | 25015 Skyline Telephone
25023 | 25023 DHS/NASA/NOAA/USPTO T&M Consulting Support | Wiesner, Jill | Awarded | In Progress | Green | 2016-09-30 | 2016-10-24 | 2017-06-30 | 2017-04-24 | 2017-06-23 | 43% | 18% | 0% | Under/Not Over budget | AMER | NATIONAL GOVERNMENT | United States of America | Cloud |  |  | TECHNICA CORPORATION-Customer | DHS-EndUser | PO | Monthly in Arrears | Consulting – T & M |  | A | 49482 | 11324 | 38158 | 30982 | 12453 | 18529 | 10497 | 22950 | 8032 | 18500 | 26532 | 36% | 54% | 20065 | 18% | 30982 | 9568 | 21414 | 10497 | 20065 | 10917 | 0 | 2885 | 0 | -2885 | 0 | 0 | 0 | 0 | 26 | 26 | 11.2 | 14.8 | -0.00125 | 8 | 6 | 2.2 | 5.8 | 44% | 30% | 1 | 1.5 | 9 | 2.2 | 0 | 0 | 0 |  | 13.7 | 1 | 25023 DHS/NASA/NOAA/USPTO T&M Consulting Support
25048 | 25048 VF GR Complete Migration FFP 5 MS | Moreno, Carlos | Awarded | In Progress | Amber | 2016-12-16 | 2017-01-04 | 2017-06-30 |  | 2017-07-12 | 129% | -44% | -88% | Customer Issues | EMEA | UK-I | Greece | Security |  |  | VODAFONE PANAFON S A-EndUser | VODAFONE GREECE-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 55404 | 55404 | 0 | 33917 | 64123 | -30206 | 2420 | 66543 | -32626 | 21487 | -11139 | 24% | -20% | 64123 | -44% | 31497 | 64123 | -32626 | 0 | 64123 | -32626 | 2420 | 0 | 2420 | 0 | 0 | 0 | 0 | 0 | 38.8 | 56.9 | 73.2 | 0 | -34.3575 | 3.5 | 4.2 | 10.9 | 0 | 10% | 18% | 1 | 0 | 62.3 | 10.9 | 0 | 0 | 0 |  | 74.2 | 1 | 25048 VF GR Complete Migration FFP 5 MS
25074 | 25074 Orange SB ACX I&C install scenario 27 Barcelona | Oliver, Juan | Awarded | In Progress | Green | 2016-10-21 | 2017-02-01 | 2017-04-11 |  |  | 0% | 0% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | ORANGE SA-Customer | ORANGE ESPAGNE, S.A.U.-EndUser | PO | Milestone Payments | Install Custom |  |  | 7096 | 7096 | 0 | 0 | 4144 | -4144 |  |  |  | 7096 |  | 0% | 0% |  | 0% | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 4144 | 0 | -4144 | 3 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 25074 Orange SB ACX I&C install scenario 27 Barcelona
25080 | 25080 Telefonica Colombia Core Edge - RTS | Almanza, Henry | Awarded | Complete | Green | 2017-05-31 | 2017-06-02 | 2017-06-09 | 2017-08-24 | 2017-07-21 | 54% | 17% | -40% | Under/Not Over budget | AMER | CALA | Colombia | Core & Edge |  |  | NEC CORPORATION-Customer | TELEFONICA COLOMBIA-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | B | 15000 | 15000 | 0 | 10500 | 4661 | 5839 | 3266 | 7927 | 2573 | 4500 | 7073 | 30% | 47% | 7927 | 17% | 10500 | 4661 | 5839 | 3266 | 7927 | 2573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 14 | 7.6 | 6.4 | -3.9975 | 0 | 13 | 2.6 | 0 | 0% | 1282% | 0.6 | 0 | 0.5 | 2.6 | 0 | 0 | 4.5 |  | 8.3 | 1 | 25080 Telefonica Colombia Core Edge - RTS
25087 | 25087 - CSX FW Conversion | Henning, Mark | Awarded | In Progress | Green | 2016-12-08 | 2017-03-27 | 2017-10-13 | 2017-06-16 | 2017-07-14 | 18% | 32% | 0% | Under/Not Over budget | AMER | US TERRITORIES | United States of America | Security |  |  | Mainline Information Systems-EndUser | CSX - End User | PO | Milestone Payments | Consulting – T & M |  | A | 92025 | 0 | 92025 | 33400 | 4380 | 29020 | 21331 | 25711 | 7689 | 58625 | 66314 | 40% | 72% | 18711 | 32% | 26400 | 4380 | 22020 | 14331 | 18711 | 7689 | 7000 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 26.3 | 26.3 | 4.8 | 21.5 | 0 | 2.5 | 2.5 | 3.4 | 0 | 11% | 15% | 4.6 | 0 | 1.4 | 3.4 | 0 | 0 | 0 |  | 9.4 | 1 | 25087 - CSX FW Conversion
25109 | 25109 Ooredoo ISP Peering Router Replacement (MX480) FFP 1MS | Bhinder, Muhammad Amir Rashid | Awarded | In Progress | Red | 2016-12-30 | 2017-01-18 | 2017-08-31 |  | 2017-07-06 | 243% | -120% | -477% | Internal Issues | EMEA | MEA | Qatar | Core & Edge |  |  | WESTCON ME-CUSTOMER | Ooredoo | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 35605 | 35605 | 0 | 20387 | 66007 | -45620 | 1642 | 67649 | -47262 | 15218 | -32044 | 30% | -90% | 64709 | -120% | 17447 | 64709 | -47262 | 0 | 64709 | -47262 | 2940 | 1298 | 1642 | 0 | 0 | 0 | 0 | 0 | 16 | 38 | 92.4 | 0 | -76.375 | 0 | 6.6 | 19 | 0 | 0% | 26% | 0.9 | 3.1 | 73.4 | 19 | 0 | 0 | 0 |  | 96.4 | 1 | 25109 Ooredoo ISP Peering Router Replacement (MX480) FFP 1MS
25131 | 25131 Skylogic T&M 15 Days | M, Rahimunnisa | Awarded | Booked | Green | 2017-03-06 |  | 2017-08-31 |  | 2017-06-23 | 8% | 41% | 0% |  | EMEA | ENA-R-SOUTH | Italy | Core & Edge |  |  | Juniper | SKYLOGIC S.P.A.-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 48325 | 0 | 48325 | 4450 | 475 | 3975 | 11108 | 11583 | -7133 | 43875 | 36742 | 35% | 76% | 7133 | 41% | 0 | 475 | -475 | 6658 | 7133 | -7133 | 4450 | 0 | 4450 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 1.1 | 13.9 | 0 | 0 | 0 | 1.1 | 0 | 0% | 8% | 0.3 | 0 | 0 | 1.1 | 0 | 0 | 0 |  | 1.4 | 1 | 25131 Skylogic T&M 15 Days
25135 | 25135 DJEZZY JSA Quickstart FFP 1 MS | Chouaieb, Mejda | Awarded | In Progress | Green | 2017-02-14 | 2017-03-16 | 2017-07-31 |  | 2017-06-30 | 68% | 29% | 0% | Under/Not Over budget | EMEA | ENA-R-SOUTH | Algeria | Security |  |  | NOKIA SOLUTIONS AND NETWORKS(NSN) - Customer | DJEZZY GSM (ORASCOM TELECOM ALGERIE)-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 10779 | 0 | 10779 | 6421 | 2246 | 4175 | 2124 | 4370 | 2051 | 4358 | 6409 | 30% | 59% | 2270 | 29% | 4321 | 2246 | 2075 | 24 | 2270 | 2051 | 2100 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 4.4 | 4.4 | 3 | 1.4 | 0 | 4.4 | 4.4 | 2 | 2.4 | 0% | 0% | 1.4 | 0 | 1 | 2 | 0 | 0 | 0 |  | 4.4 | 1 | 25135 DJEZZY JSA Quickstart FFP 1 MS
25137 | 25137 Oracle 50 PS Credits | Martin, David | Awarded | In Progress | Green | 2016-10-19 | 2016-10-11 | 2017-10-11 |  | 2017-06-07 | 0% | 100% | 0% |  | AMER | CLOUD PROVIDERS |  | Security |  |  | DIMENSION DATA HOLDINGS LTD-Customer | ORACLE CORP-EndUser | PO/Tokens | Fully in Advance | Consulting – Fixed Price Custom |  | Not Scoped | 100001 | 100001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100001 | 100001 | 0% | 100% | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 1 | 25137 Oracle 50 PS Credits
25155 | 25155 Algar Telecom Monet | Barbieri De Sousa, Alexandre | Awarded | Booked | Green | 2017-06-29 |  | 2017-09-30 |  | 2017-06-29 | 0% | 65% | 0% |  | AMER | CALA | Brazil | Core & Edge |  |  | BINARIO DISTRIBUIDORA DE EQUIP. ELETRONICOS LTDA-Customer | Algar Telecom-EndUser |  |  | Consulting – Fixed Price Custom |  | B | 22500 | 0 | 22500 | 0 | 0 | 0 | 0 | 0 | 0 | 22500 | 22500 | 35% | 100% | 0 | 65% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.0075 | 0 | 0 | 0 | 0 | 0% | 100% | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.9 |  | 25155 Algar Telecom Monet
25170 | 25170 Telem Group | Garzon, Jairo | Awarded | In Progress | Green | 2017-03-23 | 2017-09-15 | 2017-10-27 |  | 2017-07-18 | 0% | 70% | -25% |  | AMER | CALA | Bahamas | Core & Edge |  |  | Telem Group - End User | Telem Group - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 23866 | 0 | 23866 | 0 | 0 | 0 | 0 | 0 | 0 | 23866 | 23866 | 30% | 100% | 0 | 70% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 11.3 | 0 | 11.3 | -2.2487 | 0 | 0 | 0 | 0 | 0% | 0% | 4.6 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4.6 | 1 | 25170 Telem Group
25173 | 25173 Bharti - SRC Expansion - FFP | Manohar, Ravindra | Awarded | Booked | Green | 2016-12-30 | 2017-01-05 | 2017-08-22 |  | 2017-06-10 | 85% | 9% | 0% |  | APAC | India | India | Core & Edge |  |  | IBM-Customer | BHARTI AIRTEL LTD-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 48089 | 0 | 48089 | 36417 | 135 | 36283 | 32041 | 32175 | 4242 | 11672 | 15914 | 24% | 33% | 158 | 9% | 4400 | 135 | 4265 | 23 | 158 | 4242 | 0 | 0 | 0 | 0 | 32017 | 0 | 32017 | 0 | 50 | 50 | 42.6 | 7.4 | 0 | 0 | 0 | 42.6 | 0 | 0% | 578% | 0 | 0 | 0 | 42.6 | 0 | 0 | 0 |  | 42.6 | 1 | 25173 Bharti - SRC Expansion - FFP
25185 | 25185 Orange SB ACX Installations Q4-2016 | Oliver, Juan | Awarded | Complete | Green | 2016-10-27 | 2016-10-03 | 2017-07-21 |  |  | 75% | 28% | -2815% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  |  | 182406 | 104732 | 77674 | 0 | 94179 | -94179 | 279 | 94459 | -94459 | 182406 | 87948 | 20% | 48% | 766 | 28% | 0 | 487 | -487 | 279 | 766 | -766 | 0 | 0 | 0 | 0 | 0 | 93693 | 0 | -93693 | 2.5 | 72.9 | 54.9 | 18 | -70.375 | 0 | 70.4 | 54.9 | 0 | 0% | 2815% | 1.3 | 0 | 0 | 54.9 | 0 | 0 | 0 |  | 56.1 | 1 | 25185 Orange SB ACX Installations Q4-2016
25247 | 25247 TEL Fusion HL3-HL4 Migration Service Granada & Almeria | Gil, Jose | Awarded | In Progress | Green | 2017-03-28 | 2016-12-12 | 2017-12-22 |  |  | 96% | 7% | 0% |  | EMEA | Spain | Spain | Core & Edge |  |  | TELEFONICA ESPANA-EndUser | TELEFONICA DE ESPANA-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 1042462 | 745347 | 297115 | 857200 | 680900 | 176300 | 241843 | 922743 | -65543 | 185262 | 119719 | 4% | 11% | 65543 | 7% | 0 | 63017 | -63017 | 2526 | 65543 | -65543 | 2200 | 0 | 2200 | 0 | 855000 | 617883 | 237117 | 0 | 120 | 120 | 115.4 | 4.6 | 0 | 0 | 0 | 115.4 | 0 | 0% | 2495% | 0 | 0 | 0 | 115.4 | 0 | 0 | 0 |  | 115.4 | 1 | 25247 TEL Fusion HL3-HL4 Migration Service Granada & Almeria
25249 | 25249 IBM CMS Lab POC | Henning, Mark | Awarded | On Hold | Green |  | 2017-02-13 | 2017-10-27 | 2017-12-15 | 2017-07-14 | 59% | 64% | -46% | Product Issues | AMER | CLOUD PROVIDERS | United States of America | Core & Edge |  |  | IBM CLOUD-EndUser | IBM CLOUD-EndUser | Free of Charge | None | Consulting – Fixed Price Custom |  | B | 160650 | 0 | 160650 | 162345 | 40826 | 121519 | 17208 | 58035 | 104310 | -1695 | 102615 | 0% | 64% | 58035 | 64% | 162345 | 40826 | 121519 | 17208 | 58035 | 104310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 90.3 | 53.1 | 37.2 | -28.2475 | 9.2 | 21.7 | 14 | 0 | 17% | 32% | 8.1 | 2.5 | 39.1 | 14 | 0 | 0 | 0 |  | 63.7 | 1 | 25249 IBM CMS Lab POC
25250 | 25250 Softbank - JSD-Part 11 - FFP | Oyama, Hirofumi | Awarded | In Progress | Green | 2016-12-12 | 2017-04-01 | 2017-12-31 |  | 2017-06-29 | 38% | 1% | 0% | Under/Not Over budget | APAC | Japan | Japan | Security |  |  | ITOCHU CORPORATION-Customer | SOFTBANK - Enduser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 189430 | 189430 | 0 | 139500 | 52059 | 87441 | 85581 | 137640 | 1860 | 49930 | 51790 | 26% | 27% | 137640 | 1% | 139500 | 52059 | 87441 | 85581 | 137640 | 1860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155 | 58.6 | 96.4 | -155 | 0 | 155 | 0 | 0 | 0% | 0% | 0 | 0 | 58.6 | 0 | 0 | 0 | 0 |  | 58.6 |  | 25250 Softbank - JSD-Part 11 - FFP
25252 | 25252 Piraeus Bank MX Design Review T&M CONSULTING 7 Days | M, Rahimunnisa | Awarded | Booked | Green | 2017-06-28 | 2017-03-22 | 2017-07-31 | 2017-07-31 | 2017-06-23 | 132% | 19% | -32% | Product Issues | EMEA | ENA-R-SOUTH | Greece | Core & Edge |  |  | G.C.C Computers Ltd | PIRAEUS BANK S.A. | PO | Fully in Advance | Consulting – T & M |  | A | 24925 | 24925 | 0 | 13073 | 7783 | 5290 | 2450 | 10233 | 2840 | 11852 | 14692 | 40% | 59% | 7783 | 19% | 10623 | 7783 | 2840 | 0 | 7783 | 2840 | 2450 | 0 | 2450 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 9.3 | 0 | -2.25 | 0 | 0 | 1.3 | 0 | 0% | 16% | 0.2 | 0 | 5.5 | 1.3 | 0 | 0 | 2.5 |  | 9.4 | 1 | 25252 Piraeus Bank MX Design Review T&M CONSULTING 7 Days
25276 | 25276 Stantec Edmonton Data Center | Hassan, Saqib | Awarded | In Progress | Green | 2017-06-13 | 2017-06-12 | 2017-10-31 | 2017-12-15 | 2017-07-21 | 24% | 6% | 0% | Under/Not Over budget | AMER | CANADA | Canada | Cloud |  |  | TELUS CORPORATION-Customer | STANTEC CONSULTING-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 230820 | 0 | 230820 | 151182 | 42306 | 108876 | 105489 | 147795 | 3387 | 79638 | 83025 | 30% | 36% | 125295 | 6% | 128682 | 41354 | 87328 | 83942 | 125295 | 3387 | 22500 | 952 | 21548 | 0 | 0 | 0 | 0 | 0 | 111.3 | 111.3 | 26.8 | 84.5 | 0 | 36.4 | 36.4 | 4.3 | 32.2 | 49% | 49% | 12.1 | 4.3 | 16.5 | 4.3 | 6 | 0 | 0 |  | 43.1 | 1 | 25276 Stantec Edmonton Data Center
25287 | 25287 DVZ ISG200 to SRX5800 T&M 60 days | Subramaniam, Ragunath | Awarded | In Progress | Green | 2016-12-28 | 2016-04-04 | 2017-10-10 |  | 2017-06-19 | 57% | 40% | 0% |  | EMEA | DACH | Germany | Security |  |  | DIMENSION DATA-EndUser | DVZ DATENVERARBEITUNGSZENTRUM M-V GMBH-End User | PO | Fully in Advance | Consulting – T & M |  | A | 124260 | 124260 | 0 | 115050 | 32154 | 82896 | 31579 | 63733 | 51317 | 9210 | 60527 | 9% | 49% | 39733 | 40% | 91050 | 26709 | 64341 | 13024 | 39733 | 51317 | 24000 | 5445 | 18555 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 34 | 26 | 0 | 0 | 0 | 4 | 0 | 0% | 7% | 0.3 | 9.4 | 30 | 4 | 0 | 0 | 0 |  | 43.6 | 1 | 25287 DVZ ISG200 to SRX5800 T&M 60 days
25305 | 25305 Sempra Energy MX Upgrades | Jeffries, Stephanie | Awarded | In Progress | Green | 2016-12-19 | 2017-01-16 | 2017-07-28 |  | 2017-07-23 | 63% | -41% | -171% | Product Issues | AMER | US TERRITORIES | United States of America | Core & Edge |  |  | SECUREMATICS INC-Customer | SEMPRA ENERGY-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 222300 | 51129 | 171171 | 147200 | 144550 | 2650 | 73272 | 217822 | -70622 | 75100 | 4478 | 43% | 2% | 170122 | -41% | 99500 | 115993 | -16493 | 54130 | 170122 | -70622 | 20280 | 3398 | 16882 | 0 | 27420 | 25160 | 2260 | 0 | 53.1 | 144 | 90.3 | 53.8 | -90.945 | 0 | 48.4 | 49.5 | 0 | 0% | 52% | 3.1 | 5.5 | 35.2 | 49.5 | 0 | 0 | 5.6 |  | 98.9 | 1 | 25305 Sempra Energy MX Upgrades
25306 | 25306 CWC QoS Design - PS Consultant | Almanza, Henry | Awarded | Complete | Green |  | 2017-03-27 | 2017-06-30 | 2017-09-04 | 2017-07-21 | 12% | -2% | 0% | Under/Not Over budget | AMER | CALA | United States of America | Core & Edge |  |  | CWC Cable Wireless Communications - End User | CWC Cable Wireless Communications - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 81936 | 81936 | 0 | 65801 | 57489 | 8312 | 0 | 57489 | 8312 | 16135 | 24447 | 32% | 30% | 0 | -2% | 8312 | 0 | 8312 | 0 | 0 | 8312 | 0 | 0 | 0 | 0 | 57489 | 57489 | 0 | 0 | 67 | 67 | 7.8 | 59.2 | 0.0025 | 0 | 0 | 7.8 | 0 | 0% | 13% | 2.9 | 0 | 0 | 7.8 | 0 | 0 | 0 |  | 10.7 | 1 | 25306 CWC QoS Design - PS Consultant
25331 | 25331 Telstra - UAE 127 Days Extension - T&M | Davis, Joseph | Awarded | In Progress | Green | 2016-12-26 | 2017-01-16 | 2017-07-28 |  | 2017-07-07 | 97% | -20% | -2% | Under/Not Over budget | APAC | ANZ | Australia | Core & Edge |  |  | TELSTRA CORPORATION-Customer | TELSTRA CORPORATION LIMITED-EndUser | PO | Milestone Payments | Consulting – T & M |  | B | 183486 | 156035 | 27451 | 114300 | 147086 | -32786 | 4163 | 151249 | -36949 | 69186 | 32237 | 38% | 18% | 139657 | -20% | 114300 | 135494 | -21194 | 4163 | 139657 | -25357 | 0 | 0 | 0 | 0 | 0 | 11592 | 0 | -11592 | 127 | 130 | 126.1 | 3.9 | -3 | 0 | 130 | 2.9 | 0 | 0% | 0% | 0 | 0 | 123.3 | 2.9 | 0 | 0 | 0 |  | 126.1 | 1 | 25331 Telstra - UAE 127 Days Extension - T&M
25338 | 25338 Euronet BNG-VC Functional Validation Testing FFP 1 MS | Foster, David | Awarded | On Hold | Green | 2016-12-31 |  | 2017-07-28 |  | 2017-06-30 | 28% | 29% | -15% | Under/Not Over budget | EMEA | ENA-R-NORTH | Netherlands | Core & Edge |  |  | Telindus - CUSTOMER | Euronet | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 24478 | 0 | 24478 | 15569 | 1926 | 13643 | 9391 | 11316 | 4253 | 8909 | 13162 | 25% | 54% | 6476 | 29% | 10729 | 1926 | 8803 | 4551 | 6476 | 4253 | 4840 | 0 | 4840 | 0 | 0 | 0 | 0 | 0 | 10.6 | 12.1 | 3.4 | 8.7 | -1.5625 | 0.9 | 1.7 | 3.4 | 0 | 9% | 39% | 1.3 | 0 | 0 | 3.4 | 0 | 0 | 0 |  | 4.6 | 1 | 25338 Euronet BNG-VC Functional Validation Testing FFP 1 MS
25347 | 25347 Vivo GVT POC and Risk Analysis | Barbieri De Sousa, Alexandre | Awarded | In Progress | Green | 2016-12-02 | 2016-12-05 | 2017-09-29 |  |  | 36% | 58% | 0% |  | AMER | CALA | Brazil | Core & Edge |  |  | NEC CORPORATION-Customer | VIVO-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 120000 | 0 | 120000 | 0 | 22249 | -22249 | 0 | 22249 | -22249 | 120000 | 97751 | 23% | 81% | 22249 | 58% | 0 | 22249 | -22249 | 0 | 22249 | -22249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49 | 49 | 17.9 | 31.1 | 0 | 0 | 0 | 4.9 | 0 | 0% | 11% | 45.1 | 0 | 13 | 4.9 | 0 | 0 | 0 |  | 63 | 1 | 25347 Vivo GVT POC and Risk Analysis
25355 | 25355 DT PoC uCPE & CSO 2.0 T&M 18 days (FOC) | Subramaniam, Ragunath | Awarded | In Progress | Green |  | 2016-11-14 | 2017-05-19 |  | 2017-06-19 | 25% | 0% | 0% |  | EMEA | Germany | Germany | SDN |  |  | Juniper | DEUTSCHE TELEKOM AG-EndUser | Free of Charge | None | Consulting – T & M |  |  | 0 | 0 | 0 | 0 | 3169 | -3169 | 9506 | 12674 | -12674 | 0 | -12674 | 0% | 0% | 12674 | 0% | 0 | 3169 | -3169 | 9506 | 12674 | -12674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 4.5 | 13.5 | 0 | 0 | 0 | 0.1 | 0 | 0% | 1% | 0 | 0 | 4.4 | 0.1 | 0 | 0 | 0 |  | 4.5 | 1 | 25355 DT PoC uCPE & CSO 2.0 T&M 18 days (FOC)
25360 | 25360 - Exxon Mobil CREDITS BOOKING 110 CREDITS | Martin, David | Awarded | In Progress | Green | 2016-11-18 | 2017-01-09 | 2018-01-09 |  |  | 0% | 100% | 0% |  | AMER | US TERRITORIES |  | Network Automation |  |  | ATT-EndUser | EXXON MOBIL-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  |  | 217800 | 0 | 217800 | 0 | 0 | 0 | 222 | 222 | -222 | 217800 | 217578 | 0% | 100% | 222 | 100% | 0 | 0 | 0 | 222 | 222 | -222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0.0025 | 0 | 0 | 0 | 0 | 2% | 2% | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.8 | 1 | 25360 - Exxon Mobil CREDITS BOOKING 110 CREDITS
25367 | 25367 Softlayer 2017 JSD | Cicatello, James | Awarded | In Progress - Working at Risk | Amber |  | 2017-01-01 | 2017-07-31 |  | 2017-07-21 | 206% | 66% | -105% | Internal Issues | AMER | CLOUD PROVIDERS | United States of America | Juniper Strategic Delivery |  |  | SOFTLAYER-EndUser | SOFTLAYER-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 484936 | 0 | 484936 | 659210 | 64076 | 595134 | 0 | 64076 | 595134 | -174275 | 420859 | 21% | 87% | 64076 | 66% | 659210 | 64076 | 595134 | 0 | 64076 | 595134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 34 | 69.9 | 0 | -35.9038 | 0 | 0 | 3.6 | 0 | 0% | 5% | 0.7 | 0 | 66.3 | 3.6 | 0 | 0 | 0 |  | 70.6 | 1 | 25367 Softlayer 2017 JSD
25368 | 25368 Vodafone India - LCNAT APP ENHANCMENTS - FFP | Pathak, Nishant | Awarded | On Hold | Green | 2017-02-07 | 2017-02-01 | 2017-08-11 |  | 2017-07-03 | 112% | -9% | -12% | Internal Issues | APAC | India | India | Core & Edge |  |  | IBM-Customer | VODAFONE ESSAR SOUTH LTD-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | A | 12000 | 0 | 12000 | 8645 | 9694 | -1049 | 37 | 9731 | -1086 | 3355 | 2269 | 28% | 19% | 1886 | -9% | 800 | 1886 | -1086 | 0 | 1886 | -1086 | 0 | 0 | 0 | 0 | 7845 | 7808 | 37 | 0 | 39 | 39 | 43.8 | 0 | -4.75 | 39 | 39 | 8.8 | 30.3 | 0% | 821% | 0 | 0 | 35 | 8.8 | 0 | 0 | 0 |  | 43.8 | 1 | 25368 Vodafone India - LCNAT APP ENHANCMENTS - FFP
25370 | 25370 Mediaserv Design Support T&M 7 Days | M, Rahimunnisa | Awarded | In Progress | Green | 2016-12-28 | 2017-06-05 | 2017-08-31 | 2017-08-31 | 2017-06-23 | 196% | 1% | -96% |  | EMEA | France | France | Core & Edge |  |  | INTERDATA SAS-EndUser | MEDIASERV-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 24925 | 24925 | 0 | 15073 | 10509 | 4564 | 4450 | 14959 | 114 | 9852 | 9966 | 39% | 40% | 10509 | 1% | 10623 | 10509 | 114 | 0 | 10509 | 114 | 4450 | 0 | 4450 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 13.7 | 0 | -6.6875 | 0 | 0 | 2.7 | 0 | 0% | 24% | 0.6 | 1.5 | 11 | 2.7 | 0 | 0 | 0 |  | 15.8 | 1 | 25370 Mediaserv Design Support T&M 7 Days
25378 | 25378 OSP SB Upgrade PE Ulises FFP 1 MS | Oliver, Juan | Awarded | Complete | Green | 2016-12-07 | 2017-02-01 | 2017-02-28 |  |  | 50% | 19% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  |  | 6823 | 6823 | 0 | 2133 | 3577 | -1444 | 556 | 4133 | -2000 | 4690 | 2690 | 20% | 39% | 1113 | 19% | 2133 | 556 | 1577 | 556 | 1113 | 1020 | 0 | 0 | 0 | 0 | 0 | 3020 | 0 | -3020 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0% | 100% | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 1 | 1 | 25378 OSP SB Upgrade PE Ulises FFP 1 MS
25404 | 25404 TNB - MPLS 3 - FFP | Ang, Soon Aun | Awarded | In Progress | Green | 2017-04-16 | 2017-04-28 | 2017-09-30 |  | 2017-07-21 | 49% | 9% | -2% | Under/Not Over budget | APAC | ASEAN | Malaysia | Core & Edge |  |  | COMMVERGE SOLUTIONS LIMITED-Customer | TENAGA NASIONAL BERHAD-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 142349 | 26746 | 115603 | 113490 | 72503 | 40987 | 28339 | 100842 | 12648 | 28859 | 41507 | 20% | 29% | 39756 | 9% | 104400 | 20507 | 83893 | 19249 | 39756 | 64644 | 9090 | 0 | 9090 | 0 | 0 | 51996 | 0 | -51996 | 116 | 118.5 | 57.9 | 60.6 | -2.5 | 46 | 46.5 | 14.5 | 31.5 | 66% | 65% | 3 | 2.9 | 37.4 | 14.5 | 6 | 0 | 0 |  | 63.8 | 2 | 25404 TNB - MPLS 3 - FFP
25415 | 25415 Capgemini TM Support - 29d - FOC | Wiesner, Jill | Awarded | In Progress | Green |  | 2017-01-30 | 2017-07-28 | 2017-04-20 | 2017-06-23 | 111% | 0% | -11% | Resource Issues | AMER | US TERRITORIES | United States of America | Core & Edge |  |  | Capgemini | Capgemini | Free of Charge | None | Consulting – T & M |  | A | 0 | 0 | 0 | 24000 | 53518 | -29518 | 0 | 53518 | -29518 | -24000 | -53518 | 0% | 0% | 46406 | 0% | 24000 | 46406 | -22406 | 0 | 46406 | -22406 | 0 | 7112 | 0 | -7112 | 0 | 0 | 0 | 0 | 33 | 33 | 36.6 | 0 | -3.5875 | 31 | 31 | 15.8 | 15.2 | 1528% | 552% | 12.6 | 10.3 | 16.8 | 15.8 | 0 | 0 | 4 |  | 59.5 | 1 | 25415 Capgemini TM Support - 29d - FOC
25427 | 25427 Bharti - New Broadband Products - FFP | Pathak, Nishant | Awarded | On Hold | Amber | 2016-12-08 | 2016-12-12 | 2017-08-17 |  | 2017-07-03 | 63% | 0% | 0% | Under/Not Over budget | APAC | India | India | Core & Edge |  |  | TRANSITION SYSTEMS ASIA PTE LTD-Customer | BHARTI AIRTEL LIMITED-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 102000 | 102000 | 0 | 91890 | 89441 | 2449 | 2817 | 92258 | -368 | 10110 | 9742 | 10% | 10% | 2768 | 0% | 2400 | 1979 | 421 | 789 | 2768 | -368 | 0 | 0 | 0 | 0 | 89490 | 87462 | 2028 | 0 | 107 | 107 | 67.5 | 39.5 | 0 | 54.7 | 54.7 | 9.4 | 45.3 | 104% | 104% | 0 | 5 | 58.1 | 9.4 | 0 | 0 | 0 |  | 72.5 | 1 | 25427 Bharti - New Broadband Products - FFP
25429 | 25429-ATTM Contrail Cloud Mobility Lab Architect Support 2017 | Charleville, Vann | Awarded | In Progress | Green |  | 2017-01-23 | 2017-12-29 |  | 2017-07-12 | 44% | -4% | 0% | Under/Not Over budget | AMER | AT&T | United States of America | SDN | Security |  | AT&T MOBILITY, LLC.-EndUser | AT&T MOBILITY, LLC.-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 842400 | 0 | 842400 | 623200 | 289058 | 334142 | 370970 | 660029 | -36829 | 219200 | 182371 | 26% | 22% | 628829 | -4% | 592000 | 282572 | 309428 | 346257 | 628829 | -36829 | 31200 | 6487 | 24713 | 0 | 0 | 0 | 0 | 0 | 502.5 | 502.5 | 221.1 | 281.4 | 0 | 502.5 | 502.5 | 14.1 | 488.4 | 3092408% | 3092408% | 2 | 6.5 | 207 | 14.1 | 0 | 0 | 0 |  | 229.6 | 1 | 25429-ATTM Contrail Cloud Mobility Lab Architect Support 2017
25430 | 25430-ATTM SDG-ASE Sundance LAB-FFA Architect Support 2017 | Charleville, Vann | Awarded | In Progress | Green | 2017-01-20 | 2017-01-23 | 2017-12-29 |  | 2017-07-12 | 48% | 19% | 0% | Under/Not Over budget | AMER | AT&T | United States of America | Core & Edge |  |  | AT&T MOBILITY, LLC.-EndUser | AT&T MOBILITY, LLC.-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 953800 | 0 | 953800 | 678300 | 241506 | 436794 | 258033 | 499539 | 178761 | 275500 | 454261 | 29% | 48% | 499539 | 19% | 678300 | 241506 | 436794 | 258033 | 499539 | 178761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 516 | 248.3 | 267.8 | 0 | 276 | 276 | 15.6 | 260.4 | 115% | 115% | 2.3 | 0 | 232.6 | 15.6 | 0 | 0 | 0 |  | 250.5 | 1 | 25430-ATTM SDG-ASE Sundance LAB-FFA Architect Support 2017
25458 | 25458 WIND OpenNTI deployment to gather telemetry FFP 4 MS | Masci, Fabio | Awarded | In Progress | Green | 2017-06-30 | 2017-05-22 | 2017-10-31 |  | 2017-06-30 | 19% | -51% | 0% |  | EMEA | ENA-R-SOUTH | Italy | Network Automation |  |  | SIRTI - Customer | WIND ITALY-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 84000 | 0 | 84000 | 76576 | 12883 | 63693 | 66627 | 79510 | -2934 | 7424 | 4490 | 56% | 5% | 71425 | -51% | 68491 | 12883 | 55608 | 58542 | 71425 | -2934 | 8085 | 0 | 8085 | 0 | 0 | 0 | 0 | 0 | 79.3 | 79.3 | 14.8 | 64.6 | 0 | 27.9 | 27.9 | 0.6 | 27.3 | 54% | 54% | 2.7 | 0 | 14.1 | 0.6 | 0 | 0 | 0 |  | 17.4 | 1 | 25458 WIND OpenNTI deployment to gather telemetry FFP 4 MS
25462 | 25462 Talk Talk JSD Services FFP 1MS | Subramaniam, Ragunath | Awarded | In Progress | Green | 2016-12-30 | 2017-01-05 | 2017-12-29 |  | 2017-07-14 | 32% | -40% | -100% | Scoping Issues | EMEA | UK-I | United Kingdom | Juniper Strategic Delivery |  |  | Talk Talk - End User | Talk Talk - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 348010 | 348010 | 0 | 244725 | 40404 | 204321 | 342670 | 383074 | -138349 | 103285 | -35064 | 30% | -10% | 140329 | -40% | 1980 | 40404 | -38424 | 99925 | 140329 | -138349 | 0 | 0 | 0 | 0 | 242745 | 7358 | 242745 | -7358 | 120 | 240.5 | 76.2 | 164.3 | -120.5 | 0 | 39.6 | 1.7 | 0 | 0% | 20% | 0 | 0 | 74.5 | 1.7 | 0 | 0 | 0 |  | 76.2 | 1 | 25462 Talk Talk JSD Services FFP 1MS
25467 | 25467 BH Telecom PS Support T&M Consulting 4 Days (Remote) | Subramaniam, Ragunath | Awarded | In Progress | Green | 2017-01-20 | 2017-03-15 | 2017-08-30 |  | 2017-06-19 | 110% | 15% | -10% |  | EMEA | ENA-R-CEE | Bosnia and Hertzegovina | Network Automation |  |  | NOKIA CORPORATION-Customer | BH Telecom | PO | Fully in Advance | Consulting – T & M |  | A | 11509 | 11509 | 0 | 6829 | 4191 | 2638 | 0 | 4191 | 2638 | 4680 | 7318 | 49% | 64% | 4191 | 15% | 6829 | 4191 | 2638 | 0 | 4191 | 2638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4.4 | 0 | -0.40625 | 0 | 0 | 1.7 | 0 | 0% | 60% | 0.2 | 0 | 2.8 | 1.7 | 0 | 0 | 0 |  | 4.6 | 1 | 25467 BH Telecom PS Support T&M Consulting 4 Days (Remote)
25468 | 25468 NATIONAL GEOSPATIAL AGENCY (NGA) NETWORK REDESIGN - CSAT | Wiesner, Jill | Awarded | In Progress | Green |  | 2016-11-23 | 2017-07-31 | 2018-03-18 | 2017-06-23 | 48% | 0% | 0% | Under/Not Over budget | AMER | NATIONAL GOVERNMENT | United States of America | Security |  |  | NGA - NATIONAL GEOSPATIAL-INTEL AGENCY-EndUser | NGA - NATIONAL GEOSPATIAL-INTELLIGENCE AGENCY-EndUser | CSAT | None | Consulting – Fixed Price Custom |  | B | 0 | 0 | 0 | 265167 | 87444 | 177723 | 84468 | 171911 | 93256 | -265167 | -171911 | 0% | 0% | 163811 | 0% | 257067 | 83521 | 173546 | 80290 | 163811 | 93256 | 8100 | 3922 | 4178 | 0 | 0 | 0 | 0 | 0 | 164.5 | 164.5 | 79 | 85.5 | -0.00125 | 48 | 45.7 | 6.9 | 41 | 41% | 38% | 5.6 | 2.6 | 68.6 | 6.9 | 0 | 0 | 3.5 |  | 87.2 | 1 | 25468 NATIONAL GEOSPATIAL AGENCY (NGA) NETWORK REDESIGN - CSAT
25469 | 25469 Interxion Layer 3 Services FFP 8MS | Foster, David | Awarded | In Progress | Green | 2016-12-28 | 2017-01-15 | 2017-06-09 |  | 2017-07-14 | 106% | -15% | -80% | Customer Issues | EMEA | UK-I | United Kingdom | Core & Edge | Network Automation |  | XANTARO UK LTD - CUSTOMER | INTERXION - End user | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 94129 | 79229 | 14900 | 65680 | 75845 | -10165 | 13747 | 89592 | -23912 | 28449 | 4537 | 20% | 5% | 75112 | -15% | 51200 | 75112 | -23912 | 0 | 75112 | -23912 | 14480 | 733 | 13747 | 0 | 0 | 0 | 0 | 0 | 54 | 91.9 | 97.3 | 0 | -43.2975 | 0 | 0 | 11.4 | 0 | 0% | 13% | 1.4 | 0 | 81.6 | 11.4 | 0 | 4.3 | 0 |  | 98.8 | 1 | 25469 Interxion Layer 3 Services FFP 8MS
25493 | 25493 BHARTI AIRTEL - IPv6 Deployment - FFP | Pathak, Nishant | Awarded | On Hold | Amber | 2016-12-05 | 2016-11-30 | 2017-10-19 |  | 2017-07-11 | 86% | 5% | 0% |  | APAC | India | India | Core & Edge |  |  | TRANSITION SYSTEMS ASIA PTE LTD-Customer | BHARTI AIRTEL LIMITED-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 24767 | 0 | 24767 | 18575 | 16765 | 1810 | 470 | 17235 | 1340 | 6192 | 7532 | 25% | 30% | 660 | 5% | 2000 | 566 | 1434 | 94 | 660 | 1340 | 0 | 0 | 0 | 0 | 16575 | 16199 | 376 | 0 | 30 | 30 | 25.9 | 4.1 | 0 | 24.7 | 24.7 | 3.1 | 21.5 | 463% | 463% | 0 | 0 | 22.8 | 3.1 | 0 | 0 | 0 |  | 25.9 | 1 | 25493 BHARTI AIRTEL - IPv6 Deployment - FFP
25499 | 25499 VIVO BBIP Integration | Barbieri De Sousa, Alexandre | Awarded | In Progress | Green | 2017-06-06 | 2017-06-12 | 2018-03-30 |  |  | 1% | 45% | 0% |  | AMER | CALA | Brazil | Core & Edge |  |  | BINARIO DISTRIBUIDORA DE EQUIP. ELETRONICOS LTDA-Customer | VIVO-EndUser |  |  | Consulting – Fixed Price Custom |  | B | 531595 | 0 | 531595 | 0 | 2079 | -2079 | 128596 | 130675 | -130675 | 531595 | 400920 | 30% | 75% | 130675 | 45% | 0 | 2079 | -2079 | 128596 | 130675 | -130675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 1.5 | 138.5 | -140.0125 | 0 | 0 | 1.5 | 0 | 0% | 1% | 12.5 | 0 | 0 | 1.5 | 0 | 0 | 0 |  | 14 |  | 25499 VIVO BBIP Integration
25509 | 25509 Asia Investments - New DC - FFP | Jacobs, Christo | Awarded | In Progress | Green | 2017-01-10 | 2017-02-20 | 2017-08-18 |  | 2017-07-21 | 79% | 20% | -43% | Internal Issues | APAC | ASEAN | Singapore | Cloud |  |  | IBM-Customer | ASIA INVESTMENTS PTE LTD - Enduser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 67256 | 30738 | 36519 | 47205 | 28606 | 18599 | 4895 | 33502 | 13703 | 20051 | 33755 | 30% | 50% | 30841 | 20% | 47205 | 25946 | 21259 | 4895 | 30841 | 16364 | 0 | 0 | 0 | 0 | 0 | 2660 | 0 | -2660 | 49.5 | 71 | 56.4 | 14.6 | -21.5312 | 7.7 | 11.4 | 8.2 | 0 | 18% | 19% | 0 | 3.9 | 48.3 | 8.2 | 0 | 0 | 0 |  | 60.3 | 1 | 25509 Asia Investments - New DC - FFP
25516 | 25516 - Compugroup Medical SRX Migration Support | Ross, David | Awarded | Complete | Green | 2017-03-10 | 2017-03-27 | 2017-06-23 | 2017-09-15 | 2017-07-11 | 85% | 4% | -44% | Customer Issues | AMER | US TERRITORIES | United States of America | Security |  |  | INGRAM MICRO INC-Customer | Compugroup Medical - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 26100 | 26100 | 0 | 12640 | 17017 | -4377 | 0 | 17017 | -4377 | 13460 | 9083 | 31% | 35% | 14936 | 4% | 10800 | 14936 | -4136 | 0 | 14936 | -4136 | 1840 | 2081 | 0 | -241 | 0 | 0 | 0 | 0 | 10.8 | 15.6 | 13.3 | 2.3 | -4.75 | 10.8 | 14.8 | 3 | 7.8 | 0% | 1973% | 6.8 | 1.5 | 9.3 | 3 | 0 | 1 | 0 |  | 21.5 | 1 | 25516 - Compugroup Medical SRX Migration Support
25517 | 25517 State of CA OTech 50 PS Credits | Martin, David | Awarded | Booked | Green | 2017-06-28 | 2017-06-28 | 2018-06-28 | 2018-06-28 | 2017-07-11 | 0% | 100% | 0% |  | AMER | US TERRITORIES | United States of America | Core & Edge |  |  | Advantel-Customer | State of CA Office of Technology Service (OTech) - End User | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 99000 | 99000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99000 | 99000 | 0% | 100% | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.03125 | 0 | 0 | 0 | 0 | 0% | 178% | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.7 |  | 25517 State of CA OTech 50 PS Credits
25519 | 25519 Sprint OSS staff Aug | Henning, Mark | Awarded | In Progress | Green |  | 2017-05-03 | 2018-05-25 | 2018-05-25 | 2017-07-14 | 20% | -1% | 0% | Under/Not Over budget | AMER | US TERRITORIES | United States of America | Network Automation |  |  | SPRINT NEXTEL CORPORATION-Customer | SPRINT-EndUser | PO | Monthly in Arrears | Consulting – Packaged |  | B | 350001 | 0 | 350001 | 281120 | 53946 | 227174 | 246298 | 300244 | -19124 | 68881 | 49757 | 15% | 14% | 264124 | -1% | 245000 | 52120 | 192880 | 212004 | 264124 | -19124 | 36120 | 1826 | 34294 | 0 | 0 | 0 | 0 | 0 | 277.5 | 277.5 | 54.4 | 223.1 | 0 | 275 | 275 | 1.8 | 273.2 | 11000% | 11000% | 2.5 | 1 | 52.6 | 1.8 | 0 | 0 | 0 |  | 57.9 | 1 | 25519 Sprint OSS staff Aug
25521 | 25521 - Ricoh - PS Consulting Service - FFP | Henning, Riana | Awarded | In Progress | Green | 2016-12-28 | 2017-01-02 | 2018-01-01 |  | 2017-06-28 | 0% | -2% | 0% | Scoping Issues | APAC | Japan | Japan | SDN |  |  | J'S COMMUNICATION CO. LTD.-Customer | RICOH - EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 191952 | 95976 | 95976 | 56100 | 278 | 55823 | 58331 | 58608 | -2508 | 135852 | 133344 | 71% | 69% | 58608 | -2% | 56100 | 278 | 55823 | 58331 | 58608 | -2508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 66 | 0.3 | 65.7 | 0 | 9 | 9 | 0.3 | 8.7 | 16% | 16% | 0 | 0 | 0 | 0.3 | 0 | 0 | 0 |  | 0.3 | 1 | 25521 - Ricoh - PS Consulting Service - FFP
25525 | 25525 Swift JSD Network Planning 1 MS | Subramaniam, Ragunath | Opportunity | In Progress - Working at Risk | Green |  |  | 2017-05-30 |  | 2017-06-19 |  | 0% | 0% |  | EMEA | ENA-R-NORTH | Belgium | Juniper Strategic Delivery |  |  | WESTCON GROUP EUROPEAN OPERATIONS | SWIFT-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  |  | 160000 | 0 | 160000 | 110000 | 696 | 109304 | 110000 | 110696 | -696 | 50000 | 49304 | 31% | 31% | 696 | 0% | 0 | 696 | -696 | 0 | 696 | -696 | 0 | 0 | 0 | 0 | 110000 | 0 | 110000 | 0 | 0 | 0 | 1 | 0 | -1.0312 | 0 | 0 | 1 | 0 | 0% | 0% | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 1 |  | 25525 Swift JSD Network Planning 1 MS
25545 | 25545 - PA Courts SRX Implementation | Cicatello, James | Awarded | In Progress | Green | 2017-05-27 | 2017-06-26 | 2017-08-11 | 2017-12-15 | 2017-07-19 | 22% | 15% | 0% | Under/Not Over budget | AMER | US TERRITORIES | United States of America | Security |  |  | CNI Sales- Customer | Pennsylvania Courts - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 63000 | 0 | 63000 | 38010 | 6187 | 31823 | 23001 | 29189 | 8821 | 24990 | 33811 | 39% | 54% | 19979 | 15% | 28800 | 6187 | 22613 | 13791 | 19979 | 8821 | 9210 | 0 | 9210 | 0 | 0 | 0 | 0 | 0 | 24.4 | 24.4 | 5.3 | 19.1 | 0 | 4 | 4 | 2.4 | 1.6 | 20% | 20% | 2.8 | 3.6 | 0 | 2.4 | 2.9 | 0 | 0 |  | 11.7 | 1 | 25545 - PA Courts SRX Implementation
25555 | 25555 vBNG pilot for Rostelecom NW branch T&M CONSULTING 80 Days (FOC) | Subramaniam, Ragunath | Awarded | In Progress | Green |  | 2016-01-30 | 2017-10-30 |  | 2017-06-19 | 112% | 0% | -12% |  | EMEA | ENA-R-RCIS | Russia | Core & Edge |  |  | TECHNOSERV | ROS TELECOM-EndUser | Free of Charge | None | Consulting – T & M |  | A | 0 | 0 | 0 | 0 | 46451 | -46451 | 0 | 46451 | -46451 | 0 | -46451 | 0% | 0% | 46451 | 0% | 0 | 46451 | -46451 | 0 | 46451 | -46451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 89.5 | 0 | -9.4688 | 0 | 0 | 3.3 | 0 | 0% | 4% | 0 | 1.3 | 86.1 | 3.3 | 0 | 0 | 0 |  | 90.7 | 1 | 25555 vBNG pilot for Rostelecom NW branch T&M CONSULTING 80 Days (FOC)
25580 | 25580 STC GeoRed DR Site FW Deployment (was 21174) FFP 5MS | Bin Sabbar, Abdullah | Awarded | Booked | Green | 2017-06-15 | 2017-05-14 | 2017-10-31 |  | 2017-07-06 | 40% | 26% | 0% | Under/Not Over budget | EMEA | MEA | Saudi Arabia | Security |  |  | ERICSSON | STC - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 89785 | 17990 | 71795 | 55652 | 15677 | 39975 | 28355 | 44032 | 11620 | 34133 | 45753 | 25% | 51% | 38152 | 26% | 49772 | 15677 | 34095 | 22475 | 38152 | 11620 | 5880 | 0 | 5880 | 0 | 0 | 0 | 0 | 0 | 49.6 | 49.6 | 19.9 | 29.7 | 0 | 18.8 | 18.8 | 1.4 | 17.4 | 61% | 61% | 1.3 | 0 | 18.5 | 1.4 | 0 | 0 | 0 |  | 21.1 | 1 | 25580 STC GeoRed DR Site FW Deployment (was 21174) FFP 5MS
25587 | 25587 IBM RMS Ehningen 2017 | Akiyama, Mauricio | Awarded | In Progress | Green | 2016-12-28 | 2017-01-01 | 2018-01-01 |  | 2017-05-31 | 0% | 1% | 0% |  | AMER | CLOUD PROVIDERS | Remote | Network Automation |  |  | IBM CORP-EndUser | IBM CORP-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 145121 | 145121 | 0 | 107808 | 107808 | 0 | 0 | 107808 | 0 | 37313 | 37313 | 25% | 26% | 0 | 1% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107808 | 107808 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 1.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.4 | 1 | 25587 IBM RMS Ehningen 2017
25589 | 25589 IBM RMS France 2017 | Akiyama, Mauricio | Awarded | In Progress | Green | 2016-12-28 | 2017-01-01 | 2018-01-01 |  |  | 0% | 1% | 0% |  | AMER | CLOUD PROVIDERS | Remote | Network Automation |  |  | IBM CORP-EndUser | IBM CORP-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 118130 | 118130 | 0 | 86337 | 86337 | 0 | 575 | 86912 | -575 | 31793 | 31218 | 25% | 26% | 575 | 1% | 0 | 0 | 0 | 575 | 575 | -575 | 0 | 0 | 0 | 0 | 86337 | 86337 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 25589 IBM RMS France 2017
25590 | 25590 IBM RMS Brazil (Hortolandia) 2017 | Akiyama, Mauricio | Awarded | In Progress | Green | 2016-12-28 | 2017-01-01 | 2018-01-01 |  | 2017-05-31 | 0% | 2% | 0% |  | AMER | CLOUD PROVIDERS | Remote | Network Automation |  |  | IBM CORP-EndUser | IBM CORP-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 152346 | 152346 | 0 | 111350 | 111350 | 0 | 575 | 111925 | -575 | 40995 | 40420 | 25% | 27% | 575 | 2% | 0 | 0 | 0 | 575 | 575 | -575 | 0 | 0 | 0 | 0 | 111350 | 111350 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 25590 IBM RMS Brazil (Hortolandia) 2017
25591 | 25591 IBM RMS Amsterdam 2017 | Akiyama, Mauricio | Awarded | In Progress | Green | 2016-12-28 | 2017-01-01 | 2018-01-01 |  | 2017-05-31 | 0% | 16% | 0% |  | AMER | CLOUD PROVIDERS | Remote | Network Automation |  |  | IBM CORP-EndUser | IBM CORP-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 46088 | 46088 | 0 | 33689 | 33689 | 0 | 575 | 34264 | -575 | 12399 | 11824 | 10% | 26% | 575 | 16% | 0 | 0 | 0 | 575 | 575 | -575 | 0 | 0 | 0 | 0 | 33689 | 33689 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 25591 IBM RMS Amsterdam 2017
25592 | 25592 IBM RMS Toronto 2017 | Akiyama, Mauricio | Awarded | In Progress | Green | 2016-12-28 | 2017-01-01 | 2018-01-01 |  | 2017-05-31 | 0% | 1% | 0% |  | AMER | CLOUD PROVIDERS | Remote | Network Automation |  |  | IBM CORP-EndUser | IBM CORP-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 90251 | 90251 | 0 | 65960 | 65960 | 0 | 575 | 66535 | -575 | 24291 | 23716 | 25% | 26% | 575 | 1% | 0 | 0 | 0 | 575 | 575 | -575 | 0 | 0 | 0 | 0 | 65960 | 65960 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 25592 IBM RMS Toronto 2017
25594 | 25594 IBM RMS Barcelona 2017 | Akiyama, Mauricio | Awarded | In Progress | Green | 2016-12-28 | 2017-01-01 | 2018-01-01 |  | 2017-05-31 | 0% | 1% | 0% |  | AMER | CLOUD PROVIDERS | Remote | Network Automation |  |  | IBM CORP-EndUser | IBM CORP-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 74694 | 74694 | 0 | 54592 | 54592 | 0 | 575 | 55167 | -575 | 20103 | 19527 | 25% | 26% | 575 | 1% | 0 | 0 | 0 | 575 | 575 | -575 | 0 | 0 | 0 | 0 | 54592 | 54592 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 25594 IBM RMS Barcelona 2017
25595 | 25595 OSP SB Upgrade PE & Full Routing FFP 3 MS | Oliver, Juan | Awarded | Booked | Green | 2017-03-31 |  |  |  |  | 74% | 12% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT ORANGE-EndUser | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  |  | 8576 | 7718 | 858 | 4801 | 3104 | 1697 | 864 | 3968 | 833 | 3775 | 4608 | 42% | 54% | 1870 | 12% | 2703 | 1391 | 1312 | 479 | 1870 | 833 | 0 | 0 | 0 | 0 | 2098 | 1712 | 386 | 0 | 3.4 | 3.4 | 2.5 | 0.9 | 0 | 0 | 0 | 2.5 | 0 | 0% | 291% | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 |  | 2.5 | 1 | 25595 OSP SB Upgrade PE & Full Routing FFP 3 MS
25606 | 25606 TIM SBR Scripting | Barbieri De Sousa, Alexandre | Awarded | In Progress | Green | 2017-03-31 | 2017-06-19 | 2017-11-30 |  |  | 0% | 63% | -53% |  | AMER | CALA | Brazil | Network Automation |  |  | NEC CORPORATION-Customer | TIM BRASIL-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 35000 | 0 | 35000 | 23439 | 0 | 23439 | 753 | 753 | 22686 | 11561 | 34247 | 35% | 98% | 753 | 63% | 23439 | 0 | 23439 | 753 | 753 | 22686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.1 | 23 | 0 | 23 | -7.9275 | 0 | 0 | 0 | 0 | 0% | 0% | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3 | 1 | 25606 TIM SBR Scripting
25607 | 25607 VF Albania Replacement of existing ISG2000 FFP 6 MS | Moreno, Carlos | Awarded | In Progress | Amber | 2017-03-14 | 2017-04-03 | 2017-06-30 |  | 2017-07-12 | 134% | -17% | -34% | Resource Issues | EMEA | UK-I | Albania | Security |  |  | DSC d.o.o. | VODAFONE ALBANIA-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 29985 | 0 | 29985 | 19436 | 29127 | -9691 | 0 | 29127 | -9691 | 10549 | 858 | 20% | 3% | 28107 | -17% | 19436 | 28107 | -8671 | 0 | 28107 | -8671 | 0 | 1020 | 0 | -1020 | 0 | 0 | 0 | 0 | 27 | 27 | 36.1 | 0 | -9.125 | 0 | 0 | 6.4 | 0 | 0% | 21% | 2 | 1.8 | 29.8 | 6.4 | 0 | 0 | 0 |  | 39.9 | 1 | 25607 VF Albania Replacement of existing ISG2000 FFP 6 MS
25615 | 25615 KDDI - NITA Deploy - FFP | Oyama, Hirofumi | Awarded | In Progress | Amber | 2017-06-07 | 2017-05-12 | 2018-01-31 |  | 2017-07-10 | 18% | -156% | 0% | Internal Issues | APAC | Japan | Japan | Network Automation |  |  | NET ONE SYSTEMS COMPANY, LTD-Customer | KDDI CORPORATION-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 464917 | 0 | 464917 | 353938 | 214140 | 139798 | 863858 | 1077997 | -724060 | 110980 | -613080 | 24% | -132% | 1025560 | -156% | 301500 | 199232 | 102268 | 826328 | 1025560 | -724060 | 10688 | 10285 | 402 | 0 | 41750 | 4623 | 37128 | 0 | 1170.5 | 1170.5 | 211.6 | 958.9 | 0 | 618.2 | 618.2 | 51.5 | 566.7 | 112% | 112% | 5.9 | 11.9 | 160.1 | 51.5 | 0 | 0 | 0 |  | 229.4 | 1 | 25615 KDDI - NITA Deploy - FFP
25633 | 25633 TEF Fusion HL3-HL4 MAN VALENCIA/CASTELLON I&C FFP xMS | Gil, Jose | Awarded | In Progress | Green | 2016-12-21 | 2017-01-03 | 2017-10-27 |  |  | 45% | 22% | 0% |  | EMEA | Spain | Spain | Core & Edge |  |  | TELEFONICA DE ESPANA-EndUser | TELEFONICA DE ESPANA (FUSION)-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 1241476 | 366193 | 875283 | 859000 | 606029 | 252971 | 312132 | 918160 | -59160 | 382476 | 323316 | 4% | 26% | 59160 | 22% | 0 | 26781 | -26781 | 32380 | 59160 | -59160 | 9000 | 153 | 8847 | 0 | 850000 | 579095 | 270905 | 0 | 140 | 140 | 63.4 | 76.6 | 0 | 0 | 0 | 57 | 0 | 0% | 69% | 0 | 0 | 6.4 | 57 | 0 | 0 | 0 |  | 63.4 | 1 | 25633 TEF Fusion HL3-HL4 MAN VALENCIA/CASTELLON I&C FFP xMS
25644 | 25644 Globe - BNG Expansion - Phase 3 - T&M | Ang, Soon Aun | Awarded | On Hold | Green | 2016-12-15 | 2017-02-01 | 2017-09-30 |  | 2017-07-21 | 1% | -6% | 0% | Under/Not Over budget | APAC | ASEAN | Philippines | Core & Edge |  |  | COMMVERGE SOLUTIONS LIMITED-Customer | GLOBE TELECOM, INC.-EndUser | PO | Upon Completion | Consulting – T & M |  | A | 50000 | 0 | 50000 | 36800 | 161 | 36639 | 39859 | 40019 | -3219 | 13200 | 9981 | 26% | 20% | 32919 | -6% | 29700 | 161 | 29539 | 32759 | 32919 | -3219 | 7100 | 0 | 7100 | 0 | 0 | 0 | 0 | 0 | 28 | 28 | 0.3 | 27.8 | 0 | 28 | 28 | 0.3 | 27.8 | 0% | 0% | 0 | 0 | 0 | 0.3 | 0 | 0 | 0 |  | 0.3 | 1 | 25644 Globe - BNG Expansion - Phase 3 - T&M
25649 | 25649 OSP Colegios de Galicia I&C 10 Sites FFP 10 MS | Oliver, Juan | Awarded | Complete | Green | 2017-02-07 | 2017-03-01 | 2017-07-31 |  |  | 78% | 68% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT ORANGE-EndUser | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  |  | 131347 | 101607 | 29740 | 0 | 13830 | -13830 | 1175 | 15006 | -15006 | 131347 | 116341 | 21% | 89% | 15006 | 68% | 0 | 13830 | -13830 | 1175 | 15006 | -15006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 23.4 | 6.6 | 0 | 0 | 0 | 21 | 0 | 0% | 233% | 4.1 | 0 | 2.4 | 21 | 0 | 0 | 0 |  | 27.5 | 1 | 25649 OSP Colegios de Galicia I&C 10 Sites FFP 10 MS
25651 | 25651 Incapsula Juniper NCOB Junos Experience I | Subramaniam, Ragunath | Awarded | In Progress | Green | 2017-03-08 | 2017-05-03 | 2017-07-03 |  | 2017-06-19 | 19% | 60% | 0% |  | EMEA | ENA-R-CEE | Israel | Core & Edge |  |  | Zebra A>G>R Technologies LTD - Customer | INCAPSULA-EndUser | PO | Upon Completion | Consulting – Packaged |  | A | 31499 | 0 | 31499 | 23650 | 908 | 22742 | 3820 | 4728 | 18922 | 7849 | 26771 | 25% | 85% | 4728 | 60% | 23650 | 908 | 22742 | 3820 | 4728 | 18922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 1.3 | 5.7 | 0 | 0 | 0 | 1.3 | 0 | 0% | 24% | 0 | 0 | 0 | 1.3 | 0 | 0 | 0 |  | 1.3 | 1 | 25651 Incapsula Juniper NCOB Junos Experience I
25661 | 25661 Sport Pesa Tanzania (via XON) Phase1 DC Revamp Vodacom Interconnect FFP 2MS | Bhinder, Muhammad Amir Rashid | Awarded | In Progress | Green | 2017-03-31 | 2017-04-04 | 2017-07-31 |  | 2017-07-06 | 119% | 4% | -19% | Under/Not Over budget | EMEA | MEA | Tanzania | Cloud | Security | Network Automation | WESTCON GROUP EUROPEAN OPERATIONS | SPORT PESA - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 53529 | 22593 | 30936 | 36643 | 39088 | -2445 | 1781 | 40869 | -4226 | 16886 | 12660 | 20% | 24% | 36669 | 4% | 32443 | 36669 | -4226 | 0 | 36669 | -4226 | 4200 | 2419 | 1781 | 0 | 0 | 0 | 0 | 0 | 34.9 | 34.9 | 41.4 | 0 | -6.5625 | 13.5 | 13.5 | 4.9 | 8.6 | 63% | 48% | 1 | 8.3 | 36.5 | 4.9 | 0 | 0 | 0 |  | 50.8 | 1 | 25661 Sport Pesa Tanzania (via XON) Phase1 DC Revamp Vodacom Interconnect FFP 2MS
25663 | 25663 STC Get Better Plan 2020 Vision FOC (Rami) | Qasem, Waleed | Awarded | In Progress | Green |  | 2017-03-07 | 2017-06-29 |  | 2017-06-01 | 94% | 0% | 0% | Under/Not Over budget | EMEA | MEA | Saudi Arabia | Core & Edge | Security |  | Juniper | STC - End User | Free of Charge | None | Consulting – Fixed Price Custom |  | C | 0 | 0 | 0 | 263056 | 171023 | 92033 | 14951 | 185974 | 77082 | -263056 | -185974 | 0% | 0% | 156274 | 0% | 233356 | 156274 | 77082 | 0 | 156274 | 77082 | 29700 | 14749 | 14951 | 0 | 0 | 0 | 0 | 0 | 176 | 176 | 164.9 | 11.1 | 0 | 0 | 0 | 33.8 | 0 | 0% | 24% | 0 | 17.1 | 131.1 | 33.8 | 0 | 0 | 0 |  | 182.1 | 1 | 25663 STC Get Better Plan 2020 Vision FOC (Rami)
25664 | 25664 WIND Firewall for MOCN Interconnection FFP 7 MS | Masci, Fabio | Awarded | In Progress | Green | 2017-06-30 | 2017-07-03 | 2017-10-31 |  | 2017-06-30 | 23% | 11% | 0% |  | EMEA | ENA-R-SOUTH | Italy | Security |  |  | SIRTI - Customer | WIND-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 125000 | 0 | 125000 | 74349 | 14005 | 60344 | 55263 | 69268 | 5081 | 50651 | 55732 | 33% | 45% | 56508 | 11% | 61589 | 14005 | 47584 | 42503 | 56508 | 5081 | 12760 | 0 | 12760 | 0 | 0 | 0 | 0 | 0 | 65.3 | 65.3 | 15.1 | 50.1 | 0 | 16.2 | 16.2 | 0.4 | 15.8 | 33% | 33% | 2.6 | 0 | 14.3 | 0.4 | 0 | 0.5 | 0 |  | 17.8 | 1 | 25664 WIND Firewall for MOCN Interconnection FFP 7 MS
25668 | 25668 Apple 3yr JSD | Cicatello, James | Awarded | In Progress | Green | 2016-12-23 | 2017-01-01 | 2019-12-31 | 2019-12-31 | 2017-07-19 | 19% | 15% | 0% | Under/Not Over budget | AMER | CLOUD PROVIDERS | United States of America | Juniper Strategic Delivery | Core & Edge |  | LaSalle- Customer | APPLE-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | D | 5500000 | 5500000 | 0 | 4454268 | 159424 | 4294844 | 3975097 | 4134521 | 319747 | 1045732 | 1365479 | 10% | 25% | 850253 | 15% | 1170000 | 159424 | 1010576 | 690829 | 850253 | 319747 | 0 | 0 | 0 | 0 | 3284268 | 547374 | 3284268 | -547374 | 1095 | 1095 | 204.6 | 890.4 | 0 | 0 | 0 | 54 | 0 | 0% | 5% | 1 | 0 | 150.6 | 54 | 0 | 0 | 0 |  | 205.6 | 1 | 25668 Apple 3yr JSD
25676 | 25676 OSP Pedrosa MX960 Design & InC FFP 2 MS | Oliver, Juan | Awarded | Complete | Green | 2017-03-30 | 2017-02-01 | 2017-04-25 |  |  | 8% | 30% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer | ORANGE ESPAGNE, S.A.U.-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  |  | 46106 | 46106 | 0 | 27258 | 5501 | 21757 | 11779 | 17281 | 9977 | 18848 | 28825 | 33% | 63% | 11200 | 30% | 21177 | 1183 | 19994 | 10017 | 11200 | 9977 | 0 | 0 | 0 | 0 | 6081 | 4319 | 1762 | 0 | 26 | 26 | 2.1 | 23.9 | 0 | 0 | 0 | 2.1 | 0 | 0% | 9% | 3.5 | 0 | 0 | 2.1 | 0 | 0 | 0 |  | 5.6 | 1 | 25676 OSP Pedrosa MX960 Design & InC FFP 2 MS
25680 | 25680 - Kronos Cloud, Code Upgrade Support | Cardenas, Peter | Awarded | Booked | Green |  | 2017-08-14 | 2017-09-08 |  | 2017-07-13 | 0% | 22% | -7% | Under/Not Over budget | AMER | US TERRITORIES | United States of America | Core & Edge | Security |  | IPC-Customer | KRONOS-EndUser | PO | Upon Completion | Consulting – T & M |  | A | 40050 | 0 | 40050 | 20000 | 0 | 20000 | 11404 | 11404 | 8596 | 20050 | 28646 | 50% | 72% | 11404 | 22% | 20000 | 0 | 20000 | 11404 | 11404 | 8596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 15 | 0 | 15 | -1 | 0 | 0.7 | 0 | 0 | 0% | 5% | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4.3 | 1 | 25680 - Kronos Cloud, Code Upgrade Support
25694 | 25694 BT IPP WLP - 1 PTX 5000 I&C - Redbus | Foster, David | Awarded | In Progress | Green | 2016-12-29 | 2017-06-11 | 2017-08-31 |  | 2017-06-14 | 57% | 15% | 0% | Under/Not Over budget | EMEA | UK-I | United Kingdom | Core & Edge |  |  | BRITISH TELECOM - Customer | BRITISH TELECOM-EndUser | PO | Milestone Payments | Install Custom |  | B | 25789 | 0 | 25789 | 16578 | 981 | 15597 | 14369 | 15350 | 1228 | 9211 | 10439 | 25% | 40% | 1712 | 15% | 2940 | 981 | 1959 | 731 | 1712 | 1228 | 0 | 0 | 0 | 0 | 13638 | 0 | 13638 | 0 | 3 | 3 | 1.7 | 1.3 | 0 | 3 | 3 | 1.7 | 1.3 | 0% | 0% | 0 | 0 | 0 | 1.7 | 0 | 0 | 0 |  | 1.7 | 1 | 25694 BT IPP WLP - 1 PTX 5000 I&C - Redbus
25705 | 25705 TIM Brazil POC and Risk Analysis 2017 | Barbieri De Sousa, Alexandre | Awarded | Booked | Green | 2017-03-31 | 2017-10-02 | 2017-12-30 |  |  | 0% | 57% | 0% |  | AMER | CALA | Brazil | Core & Edge |  |  | NEC CORPORATION-Customer | TIM BRAZIL - RIO-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 207086 | 0 | 207086 | 0 | 0 | 0 | 16090 | 16090 | -16090 | 207086 | 190996 | 35% | 92% | 16090 | 57% | 0 | 0 | 0 | 16090 | 16090 | -16090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 70 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2.5 | 1 | 25705 TIM Brazil POC and Risk Analysis 2017
25707 | 25707 BT IPP WLP - 1 PTX 5000 I&C - Interxion | Foster, David | Awarded | In Progress | Green | 2016-12-29 | 2017-06-18 | 2017-06-30 |  | 2017-07-14 | 6% | 15% | 0% | Under/Not Over budget | EMEA | UK-I | United Kingdom | Core & Edge |  |  | BRITISH TELECOM - Customer | BRITISH TELECOM-EndUser | PO | Milestone Payments | Install Custom |  | B | 25789 | 0 | 25789 | 16578 | 107 | 16471 | 15243 | 15350 | 1228 | 9211 | 10439 | 25% | 40% | 1712 | 15% | 2940 | 107 | 2833 | 1605 | 1712 | 1228 | 0 | 0 | 0 | 0 | 13638 | 0 | 13638 | 0 | 3 | 3 | 0.2 | 2.8 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0.2 | 0 | 0 | 0 | 0 |  | 0.2 | 1 | 25707 BT IPP WLP - 1 PTX 5000 I&C - Interxion
25717 | 25717 Orange Jordan Part-2 IPv6 BNG, AFTR, CGNAT, DS-Lite FFP 7MS | Al Aswad, Waseem | Awarded | Booked | Green | 2016-12-28 | 2017-02-12 | 2017-11-30 |  | 2017-06-22 | 92% | 3% | 0% | Scoping Issues | EMEA | MEA | Jordan | Core & Edge |  |  | NETWORKING SOLUTIONS & SERVICE - Customer | Orange Jordan | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 136343 | 44637 | 91706 | 85796 | 74887 | 10909 | 19602 | 94489 | -8693 | 50547 | 41854 | 28% | 31% | 78304 | 3% | 69611 | 74887 | -5276 | 3417 | 78304 | -8693 | 16185 | 0 | 16185 | 0 | 0 | 0 | 0 | 0 | 82 | 82 | 75.6 | 6.4 | 0 | 0 | 0 | 16.7 | 0 | 0% | 26% | 0 | 3 | 58.9 | 16.7 | 0 | 0 | 0 |  | 78.6 | 1 | 25717 Orange Jordan Part-2 IPv6 BNG, AFTR, CGNAT, DS-Lite FFP 7MS
25728 | 25728 Swisscom MX Testing T&M 40 days | Subramaniam, Ragunath | Awarded | Booked | Green | 2017-02-08 |  |  |  | 2017-06-19 | 0% | 83% | 0% |  | EMEA | ENA-R-CEE | Switzerland | Core & Edge |  |  | Swisscom-Customer | SWISSCOM AG-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 150000 | 0 | 150000 | 83900 | 0 | 83900 | 38224 | 38224 | 45676 | 66100 | 111776 | -9% | 75% | 26824 | 83% | 72500 | 0 | 72500 | 26824 | 26824 | 45676 | 11400 | 0 | 11400 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.3 | 1 | 25728 Swisscom MX Testing T&M 40 days
25749 | 25749 Expedia 25 PS Credits | Akiyama, Mauricio | Awarded | Booked | Green | 2017-01-31 | 2017-01-31 | 2018-01-31 |  |  | 0% | 100% | 0% |  | AMER | US TERRITORIES | United States of America | Security |  |  | World Wide Technologies | Expedia -EndUser | PO/Tokens | Fully in Advance | Consulting – Fixed Price Custom |  | B | 49500 | 49500 | 0 | 0 | 0 | 0 | 17 | 17 | -17 | 49500 | 49483 | 0% | 100% | 17 | 100% | 0 | 0 | 0 | 17 | 17 | -17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.8 | 1 | 25749 Expedia 25 PS Credits
25752 | 25752 Zalando Junos Fusion Enterprise T&M 5 Days | M, Rahimunnisa | Awarded | Booked | Green | 2017-06-23 |  |  |  | 2017-06-27 |  | 82% | 0% |  | EMEA | DACH | Germany | Security |  |  | WESTCON GROUP EUROPEAN OPERATIONS | Zalando-End User | PO | Fully in Advance | Consulting – T & M |  | A | 14875 | 0 | 14875 | 10088 | 106 | 9982 | 2500 | 2606 | 7482 | 4787 | 12269 | 0% | 82% | 106 | 82% | 7588 | 106 | 7482 | 0 | 106 | 7482 | 2500 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | -0.25 | 0 | 0 | 0.3 | 0 | 0% | 0% | 0 | 0 | 0 | 0.3 | 0 | 0 | 0 |  | 0.3 |  | 25752 Zalando Junos Fusion Enterprise T&M 5 Days
25794 | 25794 Bharti - SRC Expansion - FFP | Manohar, Ravindra | Awarded | Booked | Green | 2016-12-30 | 2017-01-05 | 2017-08-22 |  | 2017-06-10 | 3% | -50% | 0% |  | APAC | India | India | Core & Edge |  |  | IBM-Customer | BHARTI AIRTEL LTD-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 75586 | 0 | 75586 | 57241 | 95330 | -38089 | 0 | 95330 | -38089 | 18345 | -19744 | 24% | -26% | 0 | -50% | 6400 | 0 | 6400 | 0 | 0 | 6400 | 0 | 0 | 0 | 0 | 50841 | 95330 | 0 | -44489 | 80 | 80 | 2 | 78 | 0 | 0 | 0 | 2 | 0 | 0% | 3% | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 2 | 1 | 25173 Bharti - SRC Expansion - FFP | 25794 Bharti - SRC Expansion - FFP
25801 | 25801 Orange SB ACX Installations Q1-2017 | Oliver, Juan | Awarded | In Progress | Green | 2017-01-02 | 2017-02-09 | 2017-08-31 |  |  | 86% | 33% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer-EndUser | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  |  | 207137 | 168773 | 38364 | 0 | 97468 | -97468 | 432 | 97899 | -97899 | 207137 | 109238 | 20% | 53% | 3005 | 33% | 0 | 2574 | -2574 | 432 | 3005 | -3005 | 0 | 0 | 0 | 0 | 0 | 94894 | 0 | -94894 | 60 | 60 | 51.6 | 8.4 | 0 | 0 | 0 | 47 | 0 | 0% | 362% | 0 | 0 | 4.6 | 47 | 0 | 0 | 0 |  | 51.6 | 1 | 25801 Orange SB ACX Installations Q1-2017
25835 | 25835 Equinix Brazil Contrail Cloud | Barbieri De Sousa, Alexandre | Awarded | In Progress | Green |  | 2017-06-05 | 2017-08-31 |  |  | 15% | -52% | 0% |  | AMER | CLOUD PROVIDERS | Brazil | Cloud |  |  | NEC CORPORATION-Customer | EQUINIX, INC.-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 35000 | 0 | 35000 | 0 | 7849 | -7849 | 34755 | 42605 | -42605 | 35000 | -7605 | 30% | -22% | 42461 | -52% | 0 | 7705 | -7705 | 34755 | 42461 | -42461 | 0 | 144 | 0 | -144 | 0 | 0 | 0 | 0 | 0 | 66.5 | 10.1 | 56.4 | -66.5088 | 0 | 14.5 | 0 | 0 | 0% | 28% | 5.3 | 0 | 10.1 | 0 | 0 | 0 | 0 |  | 15.4 |  | 25835 Equinix Brazil Contrail Cloud
25854 | 25854 Comcast Training Resource (PSCredits) | Smith, Ronald | Awarded | In Progress | Green |  | 2017-04-24 | 2017-12-31 | 2018-04-30 | 2017-07-21 | 3% | -27% | 0% | Scoping Issues | AMER | CABLES | United States of America | Core & Edge |  |  | COMCAST CORPORATION-Customer | COMCAST-EndUser | Token/Credit | Milestone Payments | Consulting – Fixed Price Custom |  | B | 420000 | 10500 | 409500 | 270000 | 273857 | -3857 | 107771 | 381628 | -111628 | 150000 | 38372 | 36% | 9% | 111628 | -27% | 0 | 3857 | -3857 | 107771 | 111628 | -111628 | 0 | 0 | 0 | 0 | 270000 | 270000 | 0 | 0 | 108 | 108 | 3.3 | 104.7 | 0 | 0 | 0 | 3.3 | 0 | 0% | 3% | 2.3 | 0 | 0 | 3.3 | 0 | 0 | 0 |  | 5.6 | 1 | 25854 Comcast Training Resource (PSCredits)
25856 | 25856 SST - JCS 3.0 Design Test Build - FFP | Jacobs, Christo | Awarded | In Progress | Green | 2017-05-14 | 2017-05-22 | 2017-09-21 |  | 2017-07-21 | 55% | -5% | -8% | Under/Not Over budget | APAC | Greater China | China | SDN |  |  | WESTCON GROUP PTE LTD - Customer | SST - Enduser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 142433 | 0 | 142433 | 106913 | 50298 | 56615 | 63400 | 113698 | -6784 | 35520 | 28735 | 25% | 20% | 91532 | -5% | 84780 | 50265 | 34515 | 41266 | 91532 | -6752 | 22133 | 0 | 22133 | 0 | 0 | 33 | 0 | -33 | 95 | 103 | 56.6 | 46.4 | -8 | 25.2 | 28.4 | 6.9 | 18.3 | 36% | 38% | 0 | 0 | 49.7 | 6.9 | 0 | 0 | 0 |  | 56.6 | 2 | 25856 SST - JCS 3.0 Design Test Build - FFP
25860 | 25860 BT DIXONS CSO / NFX SRX pilot T&M CONSULTING 31 Days (FOC) | Subramaniam, Ragunath | Awarded | Booked | Green |  |  |  |  | 2017-06-19 | 1% | 0% | 0% |  | EMEA | UK-I | United Kingdom | Network Automation |  |  | BT-Customer | BT-EndUser | Free of Charge | None | Consulting – T & M |  | A | 0 | 0 | 0 | 14000 | 169 | 13831 | 34578 | 34747 | -20747 | -14000 | -34747 | 0% | 0% | 20747 | 0% | 0 | 169 | -169 | 20578 | 20747 | -20747 | 14000 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 31 | 31 | 0.3 | 30.8 | 0 | 0 | 0 | 0.3 | 0 | 0% | 1% | 0.3 | 0 | 0 | 0.3 | 0 | 0 | 0 |  | 0.5 | 1 | 25860 BT DIXONS CSO / NFX SRX pilot T&M CONSULTING 31 Days (FOC)
25875 | 25875 Telenet JSD-CCL Service - AS Credits Redemption | Subramaniam, Ragunath | Awarded | Booked | Green |  |  | 2017-04-28 |  | 2017-06-19 | 1% | 51% | 0% |  | EMEA | ENA-R-NORTH | Belgium | Juniper Strategic Delivery |  |  | TELENET-Customer | TELENET-EndUser | Token/Credit | None | JSD - CCL Services |  | A | 30000 | 0 | 30000 | 0 | 148 | -148 | 14477 | 14624 | -14624 | 30000 | 15376 | 0% | 51% | 14624 | 51% | 0 | 148 | -148 | 14477 | 14624 | -14624 | 0 | 0 | 0 | 0 | 0 | 1471 | 0 | -1471 | 20 | 20 | 0.2 | 19.8 | 0 | 0 | 0 | 0.2 | 0 | 0% | 1% | 0.1 | 0 | 0 | 0.2 | 0 | 0 | 0 |  | 0.3 | 1 | 25875 Telenet JSD-CCL Service - AS Credits Redemption
25877 | 25877 - Goldman Sachs - US B2B Vendor FW Conversion | Kouzionis, Nicholas | Awarded | In Progress | Green |  | 2017-05-30 | 2017-07-31 | 2017-11-13 | 2017-06-05 | 42% | 17% | 0% |  | AMER | GLOBAL FINANCIAL SERVICES | United States of America | Security |  |  | DIMENSION DATA-EndUser | GOLDMAN SACHS-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 27170 | 0 | 27170 | 18600 | 7254 | 11346 | 6896 | 14150 | 4450 | 8570 | 13020 | 31% | 48% | 14150 | 17% | 18600 | 7254 | 11346 | 6896 | 14150 | 4450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.5 | 15.5 | 6.5 | 9 | 0 | 6 | 6 | 1.5 | 4.5 | 63% | 63% | 2.3 | 0 | 5 | 1.5 | 0 | 0 | 0 |  | 8.8 | 1 | 25877 - Goldman Sachs - US B2B Vendor FW Conversion
25879 | 25879 Flag Telecom - Wada-TOK Alien WL over Infinera - FFP | Ang, Soon Aun | Awarded | On Hold | Green | 2017-04-18 | 2017-06-26 | 2017-08-31 |  | 2017-07-21 | 53% | -7% | 0% | Under/Not Over budget | APAC | Japan | Japan | Cloud |  |  | TRANSITION SYSTEMS ASIA PTE LTD-Customer | FLAG TELECOM - EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 45500 | 0 | 45500 | 33087 | 11084 | 22003 | 25134 | 36218 | -3131 | 12413 | 9282 | 27% | 20% | 20363 | -7% | 17232 | 10818 | 6414 | 9545 | 20363 | -3131 | 0 | 0 | 0 | 0 | 15855 | 266 | 15589 | 0 | 24 | 24 | 12.8 | 11.3 | 0 | 24 | 24 | 5.8 | 18.3 | 0% | 0% | 0 | 0 | 7 | 5.8 | 0 | 0 | 0 |  | 12.8 | 1 | 25879 Flag Telecom - Wada-TOK Alien WL over Infinera - FFP
25901 | 25901 Claro Peru Core Edge FoC | Almanza, Henry | Awarded | On Hold | Green |  | 2017-01-25 | 2017-10-27 | 2017-05-13 | 2017-07-21 | 59% | 47% | 0% | Under/Not Over budget | AMER | CALA | Peru | Core & Edge |  |  | NEC CORPORATION-Customer | CLARO Peru-EndUser | Free of Charge | None | Consulting – Fixed Price Custom |  | A | 46975 | 0 | 46975 | 36124 | 9639 | 26485 | 15490 | 25129 | 10995 | 10851 | 21846 | 0% | 47% | 14729 | 47% | 25724 | 9639 | 16085 | 5090 | 14729 | 10995 | 10400 | 0 | 10400 | 0 | 0 | 0 | 0 | 0 | 21 | 21 | 12.5 | 8.5 | 0 | 0 | 0 | 3.8 | 0 | 0% | 22% | 1.3 | 0 | 8.8 | 3.8 | 0 | 0 | 0 |  | 13.8 | 1 | 25901 Claro Peru Core Edge FoC
25908 | 25908 OSP Colegios Galicia Design FFP 8 MS | Oliver, Juan | Awarded | Booked | Green | 2017-06-13 | 2017-01-17 |  |  |  | 3% | 3% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer-EndUser | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 122779 | 122779 | 0 | 124585 | 2365 | 122220 | 61848 | 64213 | 60372 | -1806 | 58566 | 45% | 48% | 64213 | 3% | 124585 | 2365 | 122220 | 61848 | 64213 | 60372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.9 | 136.9 | 4.3 | 132.7 | 0 | 42.1 | 42.1 | 4.3 | 37.8 | 44% | 44% | 1 | 0 | 0 | 4.3 | 0 | 0 | 0 |  | 5.3 | 1 | 25908 OSP Colegios Galicia Design FFP 8 MS
25909 | 25909 VZW FFP VPER Deployment support | Lovin, Daniel | Awarded | In Progress | Green | 2017-02-06 | 2017-02-20 | 2017-08-25 |  | 2017-07-19 | 83% | -433% | -8% | Under/Not Over budget | AMER | VERIZON | United States of America | Core & Edge |  |  | VERIZON WIRELESS-EndUser | VERIZON WIRELESS-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | B | 140000 | 0 | 140000 | 870000 | 576298 | 293702 | 120942 | 697240 | 172760 | -730000 | -557240 | 35% | -398% | 697240 | -433% | 870000 | 576298 | 293702 | 120942 | 697240 | 172760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 618.8 | 668.8 | 552.6 | 116.2 | -49.9988 | 426.6 | 464.1 | 0 | 426.6 | 222% | 227% | 0.6 | 0 | 552.6 | 0 | 0 | 0 | 0 |  | 553.2 | 1 | 25909 VZW FFP VPER Deployment support
25910 | 25910 DT CR01 to 23616 MW Changes FFP 1 MS | Chouaieb, Mejda | Awarded | In Progress | Green | 2017-03-20 | 2017-05-14 | 2017-09-29 |  | 2017-05-04 | 67% | 10% | 0% | Under/Not Over budget | EMEA | DACH | Germany | Security |  |  | DEUTSCHE TELEKOM-Customer | DEUTSCHE TELEKOM-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 77335 | 0 | 77335 | 46357 | 23240 | 23117 | 21965 | 45205 | 1152 | 30978 | 32130 | 32% | 42% | 31555 | 10% | 32707 | 22078 | 10629 | 9477 | 31555 | 1152 | 13650 | 1162 | 12488 | 0 | 0 | 0 | 0 | 0 | 34.3 | 34.3 | 23 | 11.3 | 0 | 34.3 | 34.3 | 0 | 34.3 | 0% | 0% | 0 | 1 | 23 | 0 | 0 | 0 | 0 |  | 24 | 1 | 23616 DT SecGW refresh FFP 22 MS | 25910 DT CR01 to 23616 MW Changes FFP 1 MS
25913 | 25913 Vodafone VPN Plus RFP FFP xMS | Stirling, Alan | Opportunity | In Progress - Working at Risk | Amber |  | 2017-07-10 | 2017-12-22 |  | 2017-07-21 |  | 242% | 0% | Scoping Issues | EMEA | UK-I | United Kingdom | SDN |  |  | VODAFONE | VODAFONE UK-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 8918184 | 0 | 8918184 | 2054450 | 8848 | 2045602 | 214577 | 223425 | 1831025 | 6863734 | 8694759 | -144% | 97% | 8848 | 242% | 1839873 | 8848 | 1831025 | 0 | 8848 | 1831025 | 214577 | 0 | 214577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 0 | -10.375 | 0 | 0 | 2.4 | 0 | 0% | 30% | 11.4 | 1 | 8 | 2.4 | 0 | 0 | 0 |  | 22.8 |  | 25913 Vodafone VPN Plus RFP FFP xMS
25915 | 25915 VENTE-PRIVEE.COM NCOB Package II | Subramaniam, Ragunath | Awarded | In Progress | Green | 2017-06-22 |  |  |  | 2017-06-19 | 8% | 54% | 0% |  | EMEA | France | France | Security |  |  | AVNET INC.-Customer | VENTE-PRIVEE.COM | PO | Upon Completion | Consulting – Packaged |  | A | 63000 | 63000 | 0 | 0 | 528 | -528 | 6226 | 6754 | -6754 | 63000 | 56246 | 35% | 89% | 6754 | 54% | 0 | 528 | -528 | 6226 | 6754 | -6754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0.8 | 9.2 | 0 | 0 | 0 | 0.8 | 0 | 0% | 8% | 0 | 0 | 0 | 0.8 | 0 | 0 | 0 |  | 0.8 | 1 | 25915 VENTE-PRIVEE.COM NCOB Package II
25917 | 25917 Banque de France NSM to SPACE Migration FFP 2 MS | Subramaniam, Ragunath | Awarded | Booked | Green | 2017-06-30 |  |  |  |  | 0% | 11% | 0% |  | EMEA | France | France | Network Automation |  |  | WESTCON-Customer | BANQUE DE FRANCE-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 76548 | 0 | 76548 | 47336 | 0 | 47336 | 45416 | 45416 | 1920 | 29212 | 31132 | 30% | 41% | 37096 | 11% | 39016 | 0 | 39016 | 37096 | 37096 | 1920 | 8320 | 0 | 8320 | 0 | 0 | 0 | 0 | 0 | 41.4 | 41.4 | 0 | 41.4 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.3 | 1 | 25917 Banque de France NSM to SPACE Migration FFP 2 MS
25934 | 25934 DT 8 x10 PS CREDITS BOOKING | Sauter, Thorsten | Awarded | Booked | Green | 2017-02-16 | [5 empty] | 67% | 0% |  | EMEA | DACH | Germany | Core & Edge |  |  | DEUTSCHE TELEKOM-Customer | DEUTSCHE TELEKOM AG-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 148000 | 148000 | 0 | 0 | 48219 | -48219 | 0 | 48219 | -48219 | 148000 | 99781 | 0% | 67% | 46135 | 67% | 0 | 46135 | -46135 | 0 | 46135 | -46135 | 0 | 2083 | 0 | -2083 | 0 | 0 | 0 | 0 | 0 | 0 | 59.6 | 0 | -59.625 | 0 | 0 | 59.6 | 0 | 0% | 0% | 0 | 0 | 0 | 59.6 | 0 | 0 | 0 |  | 59.6 | 1 | 25934 DT 8 x10 PS CREDITS BOOKING
25936 | 25936 Home Office NSMxpress to NSM Software Migration FFP 3MS | Stirling, Alan | Awarded | In Progress | Green | 2017-02-17 | 2017-02-16 | 2017-08-04 |  | 2017-07-21 | 91% | -4% | 0% | Customer Issues | EMEA | UK-I | United Kingdom | Security |  |  | TS EUROPE BVBA - Customer | Home Office-End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 52730 | 31105 | 21625 | 32076 | 36139 | -4062 | 2814 | 38953 | -6876 | 20654 | 13777 | 30% | 26% | 33253 | -4% | 26376 | 33253 | -6876 | 0 | 33253 | -6876 | 5700 | 2886 | 2814 | 0 | 0 | 0 | 0 | 0 | 31.4 | 31.4 | 28.6 | 2.8 | -0.00125 | 0 | 0 | 5.4 | 0 | 0% | 21% | 1 | 3.5 | 23.3 | 5.4 | 0 | 0 | 0 |  | 33.1 | 1 | 25936 Home Office NSMxpress to NSM Software Migration FFP 3MS
25940 | 25940 Orange CIT MPC4 Evolution FFP 6 MS | Ferrari, Lenora | Awarded | In Progress | Green | 2017-05-08 | 2017-06-05 | 2017-10-27 |  | 2017-06-30 | 9% | 14% | 0% |  | EMEA | ENA-R-SOUTH | Cote D'Ivoire | Core & Edge |  |  | #NAME? | ORANGE COTE D'IVOIRE-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 72151 | 0 | 72151 | 66210 | 3794 | 62416 | 67355 | 71149 | -4939 | 5941 | 1002 | -13% | 1% | 52749 | 14% | 47810 | 3794 | 44016 | 48955 | 52749 | -4939 | 18400 | 0 | 18400 | 0 | 0 | 0 | 0 | 0 | 57.2 | 57.2 | 5.3 | 52 | 0 | 20 | 20 | 5.3 | 14.7 | 54% | 54% | 0.5 | 0 | 0 | 5.3 | 0 | 0 | 0 |  | 5.8 | 1 | 23734 Orange CIT T&M 5 Days | 25940 Orange CIT MPC4 Evolution FFP 6 MS
25950 | 25950 - James River Insurance EVPN Implementation | Kouzionis, Nicholas | Awarded | In Progress | Green | 2017-03-03 | 2017-03-13 | 2017-07-31 | 2017-09-08 | 2017-07-14 | 155% | -24% | -55% | Resource Issues | AMER | US TERRITORIES | United States of America | Core & Edge |  |  | SLAIT CONSULTING-Customer | James River Insurance - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 14850 | 10395 | 4455 | 9600 | 13235 | -3635 | 0 | 13235 | -3635 | 5250 | 1615 | 35% | 11% | 13235 | -24% | 9600 | 13235 | -3635 | 0 | 13235 | -3635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 10.9 | 0 | -3.875 | 4.3 | 4.3 | 3.8 | 0.5 | 155% | 64% | 3.3 | 0 | 6.3 | 3.8 | 0 | 0 | 0.9 |  | 14.2 | 1 | 25950 - James River Insurance EVPN Implementation
25953 | 25953 Telefonica Ecuador P1 Case Support | Barbieri De Sousa, Alexandre | Awarded | In Progress | Green | 2017-04-12 | 2017-05-01 | 2018-05-01 | 2018-05-20 |  | 49% | -12% | 0% |  | AMER | CALA | Ecuador | Core & Edge |  |  | NEC CORPORATION-Customer | TELEFONICA - Customer | PO |  | Consulting – Fixed Price Custom |  | B | 93000 | 0 | 93000 | 0 | 81000 | -81000 | 0 | 81000 | -81000 | 93000 | 12000 | 25% | 13% | 0 | -12% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81000 | 0 | -81000 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 1% | 98% | 0.6 | 0 | 0 | 0.5 | 0 | 0 | 0 |  | 1.1 | 1 | 25953 Telefonica Ecuador P1 Case Support
25955 | 25955 Telefonica Peru P1 Case Support | Barbieri De Sousa, Alexandre | Awarded | In Progress | Green | 2017-04-19 | 2017-05-01 | 2018-05-01 | 2018-06-29 |  | 2% | 9% | -595% |  | AMER | CALA | Peru | Core & Edge |  |  | NEC CORPORATION-Customer | TELEFONICA PERU-EndUser | PO | Monthly in Advance | Consulting – Fixed Price Custom |  | B | 156000 | 0 | 156000 | 0 | 81000 | -81000 | 0 | 81000 | -81000 | 156000 | 75000 | 39% | 48% | 0 | 9% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81000 | 0 | -81000 | 1 | 7 | 0.1 | 6.9 | -6 | 0 | 6 | 0.1 | 0 | 1% | 601% | 0.8 | 0 | 0 | 0.1 | 0 | 0 | 0 |  | 0.9 | 1 | 25955 Telefonica Peru P1 Case Support
25957 | 25957 Telefonica Chile P1 Case Support | Barbieri De Sousa, Alexandre | Awarded | In Progress | Green | 2017-03-31 | 2017-04-04 | 2018-04-04 |  |  | 0% | 9% | -2% |  | AMER | CALA | Chile | Core & Edge |  |  | NEC CORPORATION-Customer | TELEFONICA CHILE-EndUser | PO | Monthly in Advance | Consulting – Fixed Price Custom |  | B | 160000 | 0 | 160000 | 0 | 81000 | -81000 | 0 | 81000 | -81000 | 160000 | 79000 | 40% | 49% | 0 | 9% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81000 | 0 | -81000 | 365 | 371 | 0 | 371 | -6 | 0 | 0 | 0 | 0 | 0% | 0% | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.1 | 1 | 25957 Telefonica Chile P1 Case Support
25958 | 25958 Telefonica Argentina P1 Case Support | Barbieri De Sousa, Alexandre | Awarded | Booked | Green | 2017-04-04 | 2017-07-07 | 2018-07-07 |  |  | 0% | -19% | -2% |  | AMER | CALA | Argentina | Core & Edge |  |  | NEC CORPORATION-Customer | TELEFONICA ARGENTINA-EndUser | PO | Monthly in Advance | Consulting – Fixed Price Custom |  | B | 88000 | 0 | 88000 | 0 | 78000 | -78000 | 0 | 78000 | -78000 | 88000 | 10000 | 30% | 11% | 0 | -19% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78000 | 0 | -78000 | 365 | 371 | 0 | 371 | -6 | 0 | 0 | 0 | 0 | 0% | 0% | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.8 | 1 | 25958 Telefonica Argentina P1 Case Support
25959 | 25959 Telefonica Brazil P1 Case Support | Barbieri De Sousa, Alexandre | Awarded | In Progress | Green | 2017-03-31 | 2017-07-03 | 2018-07-03 |  |  | 0% | 58% | -2% |  | AMER | CALA | Brazil | Core & Edge |  |  | NEC CORPORATION-Customer | TELEFONICA BRAZIL-EndUser | PO | Monthly in Advance | Consulting – Fixed Price Custom |  | B | 200450 | 0 | 200450 | 0 | 24180 | -24180 | 0 | 24180 | -24180 | 200450 | 176270 | 30% | 88% | 0 | 58% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24180 | 0 | -24180 | 365 | 371 | 0 | 371 | -6 | 0 | 0 | 0 | 0 | 0% | 0% | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.5 | 1 | 25959 Telefonica Brazil P1 Case Support
25960 | 25960 DHL ARROW FFP 2MS | Stirling, Alan | Awarded | In Progress | Green | 2017-06-07 | 2017-05-31 | 2017-09-09 |  | 2017-07-21 | 45% | -81% | -100% | Customer Issues | EMEA | ENA-R-CEE | Czech Republic | Security |  |  | ARROW - Customer | DHL-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 26287 | 0 | 26287 | 15556 | 19203 | -3647 | 20542 | 39745 | -24189 | 10731 | -13458 | 30% | -51% | 39745 | -81% | 15556 | 19203 | -3647 | 20542 | 39745 | -24189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.3 | 40.7 | 18.2 | 22.5 | -20.34 | 18.2 | 36.5 | 1.5 | 16.7 | 869% | 869% | 1.9 | 0 | 13.9 | 1.5 | 0 | 2.8 | 0 |  | 20.1 | 1 | 25960 DHL ARROW FFP 2MS
25965 | 25965 - West Chester University Onboarding I + T&M | Ross, David | Awarded | Complete | Green | 2017-03-17 | 2017-04-27 | 2017-06-21 | 2017-09-22 | 2017-06-21 | 93% | 20% | -4% |  | AMER | US TERRITORIES | United States of America | Core & Edge |  |  | INGRAM MICRO INC-Customer | West Chester University- End User | PO | Monthly in Arrears | Consulting – T & M |  | A | 38450 | 37291 | 1159 | 11600 | 18065 | -6465 | 1154 | 19220 | -7620 | 26850 | 19230 | 30% | 50% | 17220 | 20% | 9600 | 17220 | -7620 | 0 | 17220 | -7620 | 2000 | 846 | 1154 | 0 | 0 | 0 | 0 | 0 | 13.6 | 14.1 | 13.1 | 1 | -0.49875 | 3 | 3.4 | 1.8 | 1.3 | 28% | 31% | 3.6 | 2 | 11.4 | 1.8 | 0 | 0 | 0 |  | 18.7 | 1 | 25965 - West Chester University Onboarding I + T&M
25973 | 25973 OSP Colegios Galicia Workshop FFP xMS | Oliver, Juan | Awarded | Booked | Green | 2017-05-26 | 2017-06-05 |  |  |  | 25% | 27% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer-EndUser | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 24950 | 0 | 24950 | 14508 | 1739 | 12769 | 5981 | 7720 | 6788 | 10442 | 17230 | 42% | 69% | 4821 | 27% | 11609 | 1739 | 9870 | 3082 | 4821 | 6788 | 2310 | 0 | 2310 | 0 | 589 | 0 | 589 | 0 | 12.6 | 12.6 | 3.1 | 9.5 | 0 | 12.6 | 12.6 | 3.1 | 9.5 | 0% | 0% | 3 | 0 | 0 | 3.1 | 0 | 0 | 0 |  | 6.1 | 1 | 25973 OSP Colegios Galicia Workshop FFP xMS
25977 | 25977 Rackspace Onboarding JE I | Kouzionis, Nicholas | Awarded | In Progress | Green | 2017-04-21 | 2017-06-12 | 2017-08-25 |  | 2017-06-16 | 10% | 56% | -4% |  | AMER | US TERRITORIES | United States of America | Security |  |  | World Wide Technologies | Rackspace | PO | Upon Completion | Consulting – Packaged |  | A | 31500 | 0 | 31500 | 0 | 873 | -873 | 5195 | 6069 | -6069 | 31500 | 25431 | 25% | 81% | 6069 | 56% | 0 | 873 | -873 | 5195 | 6069 | -6069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7.3 | 0.8 | 6.5 | -0.25125 | 1 | 1.3 | 0.8 | 0.3 | 17% | 21% | 0.2 | 0 | 0 | 0.8 | 0 | 0 | 0 |  | 0.9 | 1 | 25977 Rackspace Onboarding JE I
25985 | 25985 IBM CMS POC Automation | Henning, Mark | Awarded | On Hold | Green |  | 2017-02-24 | 2017-10-27 | 2017-12-15 | 2017-07-14 | 98% | 52% | 0% | Under/Not Over budget | AMER | CLOUD PROVIDERS | United States of America | Network Automation | Core & Edge |  | IBM CORP-EndUser | IBM CORP-EndUser | Free of Charge | None | Consulting – Fixed Price Custom |  | B | 156150 | 0 | 156150 | 86423 | 52278 | 34145 | 22950 | 75228 | 11195 | 69727 | 80922 | 0% | 52% | 52278 | 52% | 63473 | 52278 | 11195 | 0 | 52278 | 11195 | 22950 | 0 | 22950 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 59 | 1 | 0 | 0 | 0 | 3.6 | 0 | 0% | 6% | 1.3 | 0 | 55.4 | 3.6 | 0 | 0 | 0 |  | 60.3 | 1 | 25985 IBM CMS POC Automation
25987 | 25987 IBM RMS WIN - Winterthur Switzerland | Akiyama, Mauricio | Awarded | In Progress | Green | 2017-03-02 | 2017-01-01 | 2018-01-01 |  | 2017-05-31 | 0% | 1% | 0% |  | AMER | CLOUD PROVIDERS | Remote | Network Automation |  |  | IBM CORP-EndUser | IBM CORP-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 131522 | 131522 | 0 | 93944 | 93944 | 0 | 0 | 93944 | 0 | 37578 | 37578 | 28% | 29% | 0 | 1% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93944 | 93944 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.3 | 1 | 25987 IBM RMS WIN - Winterthur Switzerland
25988 | 25988 IBM RMS UKF - Fareham, UK | Akiyama, Mauricio | Awarded | In Progress | Green | 2017-03-30 | 2017-03-15 | 2018-03-15 |  | 2017-05-31 | 0% | -29% | 0% |  | AMER | CLOUD PROVIDERS | Remote | Network Automation |  |  | IBM CORP-EndUser | IBM CORP-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 167105 | 167105 | 0 | 116515 | 116515 | 0 |  |  |  | 50590 |  | 29% | 0% |  | -29% | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 116515 | 116515 | 0 | 0 | 0 | 0 | 0 | 0 | -0.00875 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 25988 IBM RMS UKF - Fareham, UK
25990 | 25990 IBM RMS SYD - Sydney | Akiyama, Mauricio | Awarded | In Progress | Green | 2017-03-02 | 2017-01-01 | 2018-01-01 |  | 2017-05-31 | 0% | -28% | 0% |  | AMER | CLOUD PROVIDERS | Remote | Network Automation |  |  | IBM CORP-EndUser | IBM CORP-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 83602 | 0 | 83602 | 59716 | 59716 | 0 |  |  |  | 23886 |  | 28% | 0% |  | -28% | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 59716 | 59716 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 25990 IBM RMS SYD - Sydney
25991 | 25991 IBM RMS POK - Poughkeepsie, NY | Akiyama, Mauricio | Awarded | In Progress | Green | 2017-03-02 | 2017-01-01 | 2018-01-01 |  | 2017-05-31 | 0% | -28% | 0% |  | AMER | CLOUD PROVIDERS | Remote | Network Automation |  |  | IBM CORP-EndUser | IBM CORP-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 129398 | 129398 | 0 | 92427 | 92427 | 0 |  |  |  | 36971 |  | 28% | 0% |  | -28% | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 92427 | 92427 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 25991 IBM RMS POK - Poughkeepsie, NY
25992 | 25992 IBM RMS TOK - Tokyo | Akiyama, Mauricio | Awarded | In Progress | Green | 2017-03-02 | 2017-01-01 | 2018-01-01 |  | 2017-05-31 | 0% | -28% | 0% |  | AMER | CLOUD PROVIDERS | Remote | Network Automation |  |  | IBM CORP-EndUser | IBM CORP-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 88957 | 88957 | 0 | 63540 | 63540 | 0 |  |  |  | 25417 |  | 28% | 0% |  | -28% | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 63540 | 63540 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 25992 IBM RMS TOK - Tokyo
25994 | 25994 IBM RMS SA - South Africa | Akiyama, Mauricio | Awarded | In Progress | Green | 2017-03-30 | 2017-03-15 | 2018-03-15 |  | 2017-05-31 | 0% | 1% | 0% |  | AMER | CLOUD PROVIDERS | United States of America | Network Automation |  |  | IBM CORP-EndUser | IBM CORP-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 166338 | 166338 | 0 | 115902 | 115902 | 0 | 0 | 115902 | 0 | 50437 | 50437 | 29% | 30% | 0 | 1% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115902 | 115902 | 0 | 0 | 0 | 0 | 0 | 0 | -0.00875 | 0 | 0 | 0 | 0 | 0% | 0% | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.4 |  | 25994 IBM RMS SA - South Africa
25995 | 25995 IBM RMS SGP Singapore | Akiyama, Mauricio | Awarded | In Progress | Green | 2017-03-17 | 2017-03-01 | 2018-02-28 | 2018-02-28 |  | 0% | -28% | 0% |  | AMER | CLOUD PROVIDERS | United States of America | Core & Edge |  |  | IBM CORP-EndUser | IBM CORP-EndUser | PO |  | Consulting – Fixed Price Custom |  | A | 16628 | 16628 | 0 | 11877 | 11877 | 0 |  |  |  | 4751 |  | 28% | 0% |  | -28% | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 11877 | 11877 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 25995 IBM RMS SGP Singapore
26002 | 26002 Telstra - REX-Extension-R1 - T&M | Davis, Joseph | Awarded | In Progress | Green | 2017-04-12 | 2017-05-01 | 2017-08-04 |  | 2017-07-07 | 90% | -2% | -5% | Under/Not Over budget | APAC | ANZ | Australia | Core & Edge |  |  | TELSTRA CORPORATION-Customer | TELSTRA CORPORATION LIMITED-EndUser | PO | Upon Completion | Consulting – T & M |  | A | 83665 | 0 | 83665 | 55800 | 57348 | -1548 | 254 | 57602 | -1802 | 27865 | 26063 | 33% | 31% | 2574 | -2% | 55800 | 2320 | 53480 | 254 | 2574 | 53226 | 0 | 0 | 0 | 0 | 0 | 55028 | 0 | -55028 | 62 | 65 | 58.6 | 6.4 | -3 | 0 | 63.5 | 2.6 | 0 | 0% | 4233% | 0 | 0 | 56 | 2.6 | 0 | 0 | 0 |  | 58.6 | 1 | 26002 Telstra - REX-Extension-R1 - T&M
26011 | 26011 TEF FUSION I&C HL3-HL4 BCN MAN (19 Quotes) | Gil, Jose | Awarded | In Progress | Green | 2017-02-07 | 2017-02-01 | 2017-09-29 |  |  | 50% | 8% | 0% |  | EMEA | Spain | Spain | Core & Edge |  |  | TELEFONICA-EndUser | TELEFONICA DE ESPANA (FUSION)-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 1632682 | 853914 | 778768 | 1353500 | 1028280 | 325220 | 400713 | 1428993 | -75493 | 279182 | 203688 | 4% | 12% | 75493 | 8% | 0 | 37702 | -37702 | 37792 | 75493 | -75493 | 3500 | 0 | 3500 | 0 | 1350000 | 990578 | 359422 | 0 | 160 | 160 | 80.1 | 79.9 | 0 | 0 | 0 | 80.1 | 0 | 0% | 100% | 0 | 0 | 0 | 80.1 | 0 | 0 | 0 |  | 80.1 | 1 | 26011 TEF FUSION I&C HL3-HL4 BCN MAN (19 Quotes)
26021 | 26021 T-Systems IT Security T&M 5 Days | Subramaniam, Ragunath | Awarded | Booked | Green | 2017-04-28 |  |  |  |  | 6% | 32% | 0% |  | EMEA | DACH | Germany | Security |  |  | DEUTSCHE TELEKOM-Customer | DEUTSCHE TELEKOM-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 13475 | 0 | 13475 | 8688 | 211 | 8477 | 4266 | 4477 | 4211 | 4787 | 8998 | 35% | 67% | 3377 | 32% | 7588 | 211 | 7377 | 3166 | 3377 | 4211 | 1100 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0.3 | 4.7 | -5 | 0 | 0 | 0.3 | 0 | 0% | 7% | 0 | 0 | 0 | 0.3 | 0 | 0 | 0 |  | 0.3 |  | 26021 T-Systems IT Security T&M 5 Days
26045 | 26045 DNA Finland POC support T&M 7 days (FOC) | Subramaniam, Ragunath | Awarded | Complete | Green |  | 2017-03-30 | 2017-04-07 |  | 2017-04-06 | 117% | 0% | -17% |  | EMEA | ENA-R-NORTH | Finland | Core & Edge |  |  | Juniper | DNA Finland | Free of Charge | None | Consulting – T & M |  | A | 0 | 0 | 0 | 0 | 8936 | -8936 | 0 | 8936 | -8936 | 0 | -8936 | 0% | 0% | 8936 | 0% | 0 | 8936 | -8936 | 0 | 8936 | -8936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 8.2 | 0 | -1.1562 | 0 | 0 | 1.2 | 0 | 0% | 17% | 0 | 2.5 | 7 | 1.2 | 0 | 0 | 0 |  | 10.7 | 1 | 26045 DNA Finland POC support T&M 7 days (FOC)
26060 | 26060 Vodafone Spain CGNAT FFP 11 MS | Moreno, Carlos | Awarded | In Progress | Green | 2017-03-30 | 2017-04-03 | 2017-06-30 |  | 2017-07-12 | 111% | 3% | -11% |  | EMEA | UK-I | Spain | Security |  |  | VODAFONE | VODAFONE-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 38006 | 0 | 38006 | 26028 | 25103 | 925 | 908 | 26011 | 17 | 11978 | 11995 | 29% | 32% | 22960 | 3% | 22977 | 22960 | 17 | 0 | 22960 | 17 | 788 | 0 | 788 | 0 | 2263 | 2143 | 120 | 0 | 27 | 27 | 29.9 | 0 | -2.875 | 0 | 0 | 6 | 0 | 0% | 25% | 0.1 | 1 | 23.9 | 6 | 0 | 0 | 0 |  | 31 | 1 | 26060 Vodafone Spain CGNAT FFP 11 MS
26068 | 26068 MOD PS Support T&M Consulting 4 Days (Onsite) | M, Rahimunnisa | Awarded | Booked | Green | 2017-06-02 |  | 2017-07-31 |  | 2017-06-23 | 5% | 33% | 0% |  | EMEA | ENA-R-NORTH | Netherlands | Core & Edge |  |  | DIMENSION DATA HOLDINGS LTD-Customer | MINISTERIE VAN DEFENSIE - End User | PO | Fully in Advance | Consulting – T & M |  | A | 12700 | 0 | 12700 | 7070 | 79 | 6991 | 2839 | 2919 | 4151 | 5630 | 9781 | 44% | 77% | 1919 | 33% | 6070 | 79 | 5991 | 1839 | 1919 | 4151 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0.2 | 3.8 | 0 | 0 | 0 | 0.2 | 0 | 0% | 5% | 0.1 | 0 | 0 | 0.2 | 0 | 0 | 0 |  | 0.3 | 1 | 26068 MOD PS Support T&M Consulting 4 Days (Onsite)
26088 | 26088 Lockheed Martin Contrail SDN Support | Wiesner, Jill | Awarded | Booked | Green | 2017-03-06 | 2017-06-05 | 2017-08-31 |  | 2017-06-26 | 23% | 1% | 0% |  | AMER | NATIONAL GOVERNMENT | United States of America | SDN |  |  | LOCKHEED MARTIN CORPORATION-Customer | LOCKHEED MARTIN CORP-EndUser | PO | Milestone Payments | Consulting – Packaged |  | B | 32310 | 0 | 32310 | 17785 | 3775 | 14010 | 13536 | 17311 | 474 | 14525 | 14999 | 45% | 46% | 14061 | 1% | 14535 | 3775 | 10760 | 10286 | 14061 | 474 | 3250 | 0 | 3250 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 2.8 | 9.2 | 0 | 11.5 | 11.5 | 1.1 | 10.4 | 2296% | 2296% | 1.4 | 0 | 1.8 | 1.1 | 0 | 0 | 0 |  | 4.2 | 1 | 26088 Lockheed Martin Contrail SDN Support
26101 | 26101 FSK DC Interconnect FFP 2MS | Chouaieb, Mejda | Awarded | In Progress | Green | 2017-04-26 | 2017-04-27 | 2017-07-14 |  | 2017-06-30 | 104% | 4% | -4% | Under/Not Over budget | EMEA | ENA-R-NORTH | Sweden | Cloud |  |  | WESTCON GROUP EUROPEAN OPERATIONS | FORSAKRINGSKASSAN DATA AB-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 50320 | 0 | 50320 | 32535 | 34683 | -2148 | 963 | 35646 | -3111 | 17785 | 14674 | 25% | 29% | 32646 | 4% | 29535 | 32646 | -3111 | 0 | 32646 | -3111 | 3000 | 2037 | 963 | 0 | 0 | 0 | 0 | 0 | 31.4 | 31.4 | 32.5 | 0 | -1.125 | 18.3 | 18.3 | 6.6 | 11.7 | 140% | 129% | 1.3 | 1.8 | 17.3 | 6.6 | 0 | 0 | 8.6 |  | 35.5 | 1 | 26101 FSK DC Interconnect FFP 2MS
26104 | 26104 - Goldman Sachs SRX 5600 Testing CCL | Cicatello, James | Awarded | In Progress | Amber | 2017-03-17 | 2017-05-30 | 2017-07-24 |  | 2017-07-17 | 106% | -90% | -102% | Internal Issues | AMER | GLOBAL FINANCIAL SERVICES | United States of America | Juniper Strategic Delivery |  |  | DIMENSION DATA HOLDINGS LTD-Customer | GOLDMAN SACHS-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 37050 | 0 | 37050 | 25101 | 57033 | -31932 | 1101 | 58134 | -33033 | 11949 | -21084 | 33% | -57% | 57033 | -90% | 24000 | 57033 | -33033 | 0 | 57033 | -33033 | 0 | 0 | 0 | 0 | 1101 | 1101 | 1101 | -1101 | 25.5 | 48.5 | 51.6 | 0 | -26.0538 | 1 | 24 | 15.2 | 0 | 4% | 87% | 2 | 0 | 36.4 | 15.2 | 0 | 0 | 0 |  | 53.6 | 1 | 26104 - Goldman Sachs SRX 5600 Testing CCL
26106 | 26106 (P26910) STC 2017 IGW Expansion FFP 7 MS | Qasem, Waleed | Awarded | Booked | Green | 2017-05-25 | 2017-05-14 | 2017-12-31 |  | 2017-06-01 | 16% | -10% | -1% | Under/Not Over budget | EMEA | MEA | Saudi Arabia | Core & Edge |  |  | ARABIAN INTERNET & COMMUNICATIONS SERVICES COMPANY - Customer | STC - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 454315 | 0 | 454315 | 406847 | 48929 | 357918 | 403855 | 452784 | -45937 | 47468 | 1531 | 10% | 0% | 314904 | -10% | 268967 | 48929 | 220038 | 265975 | 314904 | -45937 | 43004 | 0 | 43004 | 0 | 94876 | 0 | 94876 | 0 | 340.3 | 345.3 | 53.6 | 291.7 | -5 | 132.8 | 137.3 | 2.8 | 130 | 64% | 66% | 0 | 0 | 33.3 | 2.8 | 13.8 | 0 | 3.8 |  | 53.6 | 1 | 26910 STC IGW 26106 + North 26116 + 26439 ***LEVEL 1*** | 26106 (P26910) STC 2017 IGW Expansion FFP 7 MS
26107 | 26107 Telstra - Strategic Consulting - Extension 1 - T&M | Davis, Joseph | Awarded | In Progress | Green | 2017-03-22 | 2017-05-01 | 2018-01-25 |  | 2017-07-07 | 26% | -30% | 0% | Under/Not Over budget | APAC | ANZ | Australia | Core & Edge |  |  | TELSTRA CORPORATION-Customer | TELSTRA CORPORATION LIMITED-EndUser | PO | Upon Completion | Consulting – T & M |  | B | 262730 | 62827 | 199903 | 174600 | 66404 | 108196 | 184637 | 251041 | -76441 | 88130 | 11689 | 34% | 4% | 251041 | -30% | 174600 | 66404 | 108196 | 184637 | 251041 | -76441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194 | 194 | 51.4 | 142.6 | 0 | 187.3 | 187.3 | 2.1 | 185.2 | 2810% | 2810% | 0 | 0 | 49.3 | 2.1 | 0 | 0 | 0 |  | 51.4 | 1 | 26107 Telstra - Strategic Consulting - Extension 1 - T&M
26111 | 26111 Expedia Chandler 6 FW Conversions (Using PS Credits) | Kouzionis, Nicholas | Awarded | In Progress | Green |  | 2017-03-27 | 2017-07-17 | 2017-09-30 | 2017-07-13 | 66% | -22% | -28% | Customer Issues | AMER | US TERRITORIES | United States of America | Security |  |  | WORLD WIDE TECHNOLOGY HOLDING CO,. INC.-Customer | Expedia -EndUser | Token/Credit | Monthly in Advance | Consulting – Fixed Price Custom |  | B | 56050 | 0 | 56050 | 77434 | 48134 | 29300 | 20477 | 68611 | 8823 | -21384 | -12561 | 0% | -22% | 68611 | -22% | 77434 | 48134 | 29300 | 20477 | 68611 | 8823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.5 | 84 | 55.4 | 28.6 | -18.5 | 14.6 | 11 | 9.8 | 4.8 | 29% | 15% | 5 | 0 | 45.6 | 9.8 | 0 | 0 | 0 |  | 60.4 | 1 | 26111 Expedia Chandler 6 FW Conversions (Using PS Credits)
26116 | 26116 (P26910) STC 2017 North Phase 2 9MS FFP | Abuelneel, Ahmed | Awarded | Booked | Green | 2017-05-24 |  |  |  |  | 14% | 30% | 85% |  | EMEA | MEA | Saudi Arabia | Core & Edge |  |  | ARABIAN INTERNET & COMMUNICATIONS SERVICES COMPANY - Customer | STC - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 1222397 | 0 | 1222397 | 1141658 | 13443 | 1128215 | 760423 | 773866 | 367792 | 80739 | 448531 | 7% | 37% | 89729 | 30% | 457521 | 13443 | 444078 | 76286 | 89729 | 367792 | 44187 | 0 | 44187 | 0 | 639950 | 0 | 639950 | 0 | 745 | 112 | 16 | 96 | 633 | 69.1 | 19.4 | 0 | 69.1 | 10% | 21% | 0 | 0 | 14.9 | 0 | 0 | 0 | 1.1 |  | 16 | 1 | 26910 STC IGW 26106 + North 26116 + 26439 ***LEVEL 1*** | 26116 (P26910) STC 2017 North Phase 2 9MS FFP
26121 | 26121 RockYou Onboarding JEI | Hassan, Saqib | Awarded | Booked | Green | 2017-02-14 | 2017-07-05 | 2017-09-29 | 2017-12-29 | 2017-07-21 | 0% | 75% | 0% | Under/Not Over budget | AMER | US TERRITORIES | United States of America | Core & Edge |  |  | Datec, Inc.-Customer | ROCKYOU - End User | PO | Upon Completion | Consulting – Packaged |  | A | 31500 | 0 | 31500 | 7000 | 0 | 7000 | 0 | 0 | 7000 | 24500 | 31500 | 25% | 100% | 0 | 75% | 7000 | 0 | 7000 | 0 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.4 | 1 | 26121 RockYou Onboarding JEI
26124 | 26124 Lattelecom PS Support T&M Consulting 5 days (Onsite) | Subramaniam, Ragunath | Awarded | In Progress | Green | 2017-03-01 | 2017-02-15 | 2017-08-15 |  | 2017-06-19 | 95% | -9% | 0% |  | EMEA | ENA-R-NORTH | Latvia | Cloud |  |  | ARROW - Customer | Lattelecom | PO | Fully in Advance | Consulting – T & M |  | A | 12150 | 12150 | 0 | 7304 | 3864 | 3440 | 2236 | 6099 | 1204 | 4846 | 6050 | 58% | 50% | 3849 | -9% | 5054 | 3849 | 1204 | 0 | 3849 | 1204 | 2250 | 14 | 2236 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 4.8 | 0.3 | 0 | 0 | 0 | 1.1 | 0 | 0% | 29% | 0 | 1.5 | 3.6 | 1.1 | 0 | 0 | 0 |  | 6.3 | 1 | 26124 Lattelecom PS Support T&M Consulting 5 days (Onsite)
26127 | 26127 Sandia National Labs Contrail and Space Support - T&M | Wiesner, Jill | Awarded | In Progress | Green | 2017-05-05 | 2017-08-01 | 2017-10-31 | 2018-02-01 | 2017-06-23 | 24% | 19% | 0% | Under/Not Over budget | AMER | NATIONAL GOVERNMENT | United States of America | Network Automation | SDN |  | ABBA Technologies - Customer | SANDIA NATIONAL LABS-EndUser | PO | Monthly in Arrears | Consulting – T & M |  | B | 105490 | 0 | 105490 | 71938 | 11747 | 60191 | 40730 | 52477 | 19461 | 33552 | 53013 | 31% | 50% | 49227 | 19% | 68688 | 11747 | 56941 | 37480 | 49227 | 19461 | 3250 | 0 | 3250 | 0 | 0 | 0 | 0 | 0 | 64 | 64 | 15.2 | 48.8 | 0 | 64 | 64 | 0.4 | 63.6 | 0% | 0% | 0.9 | 0 | 14.8 | 0.4 | 0 | 0 | 0 |  | 16.1 | 1 | 26127 Sandia National Labs Contrail and Space Support - T&M
26137 | 26137 VF SP MPC Expansion FFP 21 MS | Moreno, Carlos | Awarded | In Progress | Green | 2017-06-21 | 2017-06-19 | 2017-08-31 |  | 2017-07-12 | 27% | 14% | 0% |  | EMEA | UK-I | Spain | Security |  |  | VODAFONE | VODAFONE ESPANA-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 142643 | 22629 | 120014 | 55382 | 52383 | 2999 | 31686 | 84069 | -28687 | 87261 | 58574 | 27% | 41% | 43278 | 14% | 50779 | 11592 | 39187 | 31686 | 43278 | 7501 | 0 | 0 | 0 | 0 | 4603 | 40791 | 0 | -36188 | 59.8 | 59.8 | 16.1 | 43.6 | 0 | 22.7 | 22.7 | 9.1 | 13.6 | 61% | 61% | 1.4 | 0 | 7 | 9.1 | 0 | 0 | 0 |  | 17.5 | 1 | 26137 VF SP MPC Expansion FFP 21 MS
26141 | 26141 FASTWEB WANDL FFP 3 MS 35 Credits Redemption | Masci, Fabio | Awarded | In Progress | Green |  | 2017-03-27 | 2017-08-31 |  | 2017-06-30 | 5% | -30% | 0% |  | EMEA | ENA-R-SOUTH | Italy | Core & Edge |  |  | #NAME? | FASTWEB-EndUser | Token/Credit | None | Consulting – Fixed Price Custom |  |  | 0 | 0 | 0 | 0 | 1622 | -1622 | 28801 | 30423 | -30423 | 0 | -30423 | 30% | 0% | 30423 | -30% | 0 | 1622 | -1622 | 28801 | 30423 | -30423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 2.1 | 37.9 | 0 | 0 | 0 | 0.8 | 0 | 0% | 2% | 0.7 | 0 | 1.3 | 0.8 | 0 | 0 | 0 |  | 2.8 | 1 | 26141 FASTWEB WANDL FFP 3 MS 35 Credits Redemption
26142 | 26142 Comcast OTT VPN NFX Testing | LaSalle, Glenn | Opportunity | On Hold | Green |  | 2017-03-27 |  |  |  | 0% | 65% | 0% |  | AMER | CABLES | United States of America | Network Automation |  |  | COMCAST CORPORATION-Customer | COMCAST-EndUser | Token/Credit | Milestone Payments | Consulting – Fixed Price Custom |  | B | 105404 | 0 | 105404 | 68513 | 0 | 68513 | 0 | 0 | 68513 | 36891 | 105404 | 35% | 100% | 0 | 65% | 68513 | 0 | 68513 | 0 | 0 | 68513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.00875 | 0 | 0 | 0 | 0 | 0% | 0% | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.5 |  | 26142 Comcast OTT VPN NFX Testing
26147 | 26147 ITDZ Release Upgrade Support FFP 2 MS | Chouaieb, Mejda | Awarded | In Progress | Green | 2017-06-09 | 2017-06-12 | 2017-08-25 |  | 2017-06-30 | 0% | 21% | 0% | Under/Not Over budget | EMEA | DACH | Germany | Security |  |  | WESTCON-Customer | IT-DIENSTLEISTUNGSZENTRUM BERLIN-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 8905 | 0 | 8905 | 5487 | 0 | 5487 | 4434 | 4434 | 1053 | 3418 | 4471 | 29% | 50% | 3279 | 21% | 4332 | 0 | 4332 | 3279 | 3279 | 1053 | 1155 | 0 | 1155 | 0 | 0 | 0 | 0 | 0 | 4.6 | 4.6 | 0 | 4.6 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.2 | 1 | 26147 ITDZ Release Upgrade Support FFP 2 MS
26149 | 26149 Interoute Control Plane Testing FFP 2MS - Credits Redemption | Foster, David | Awarded | In Progress | Amber |  | 2017-07-07 | 2017-09-15 |  | 2017-07-14 | 0% | -39% | 0% | Under/Not Over budget | EMEA | UK-I | United Kingdom | Core & Edge |  |  | TELENT COMMUNICATIONS HOLDINGS LTD-Customer | INTEROUTE-EndUser | Token/Credit | Fully in Advance | Consulting – Fixed Price Custom |  | B | 0 | 0 | 0 | 17799 | 0 | 17799 | 11091 | 11091 | 6708 | -17799 | -11091 | 39% | 0% | 8715 | -39% | 15423 | 0 | 15423 | 8715 | 8715 | 6708 | 2376 | 0 | 2376 | 0 | 0 | 0 | 0 | 0 | 16.7 | 16.7 | 0 | 16.7 | 0 | 9.4 | 9.4 | 0 | 9.4 | 128% | 128% | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 1 | 26149 Interoute Control Plane Testing FFP 2MS - Credits Redemption
26150 | 26150 Comcast MX2010 Install | LaSalle, Glenn | Opportunity | On Hold | Green | [5 empty] | 0% | 6% | 0% |  | AMER | US TERRITORIES | United States of America | Core & Edge |  |  | COMCAST CORPORATION-Customer | COMCAST-EndUser | Token/Credit | Milestone Payments |  |  |  | 30888 | 0 | 30888 | 20540 | 0 | 20540 | 16915 | 16915 | 3625 | 10348 | 13973 | 39% | 45% | 0 | 6% | 3625 | 0 | 3625 | 0 | 0 | 3625 | 16915 | 0 | 16915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.00875 | 0 | 0 | 0 | 0 | 0% | 0% | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.1 |  | 26150 Comcast MX2010 Install
26186 | 26186 MOD Automation Driven Implementation - Onsite lab project 5days FOC + 35days T&M | Subramaniam, Ragunath | Awarded | Booked | Green | 2017-06-26 | 2017-06-01 | 2017-12-31 |  | 2017-06-19 | 36% | 32% | 0% |  | EMEA | UK-I | United Kingdom | Core & Edge |  |  | ARROW - Customer | MOD-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 75530 | 75530 | 0 | 63613 | 13073 | 50540 | 30386 | 43459 | 20154 | 11917 | 32071 | 10% | 42% | 32959 | 32% | 53113 | 12870 | 40243 | 20089 | 32959 | 20154 | 10500 | 203 | 10297 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 14.3 | 25.7 | 0 | 40 | 40 | 1.8 | 38.2 | 0% | 0% | 0.3 | 2.8 | 12.5 | 1.8 | 0 | 0 | 0 |  | 17.4 | 1 | 26186 MOD Automation Driven Implementation - Onsite lab project 5days FOC + 35days T&M
26193 | 26193 Orange Spain G3 ISGF a MULTIMODO FFP 3 MS | Oliver, Juan | Awarded | Complete | Green | 2017-03-10 | 2017-02-14 | 2017-07-28 |  |  | 0% | -25% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT ORANGE-EndUser | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  |  | 4895 | 0 | 4895 | 3227 | 856 | 2371 |  |  |  | 1668 |  | 25% | 0% |  | -25% | 2227 | 0 | 2227 |  |  |  | 0 | 0 | 0 | 0 | 1000 | 856 | 144 | 0 | 2.4 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 26193 Orange Spain G3 ISGF a MULTIMODO FFP 3 MS
26194 | 26194 Oracle OPC JSD | Cicatello, James | Awarded | In Progress | Green | 2017-04-10 | 2017-04-10 | 2018-04-10 | 2018-04-10 | 2017-07-19 | 3% | 2% | -27704% | Under/Not Over budget | AMER | CLOUD PROVIDERS | United States of America | Juniper Strategic Delivery |  |  | Oracle Corporation - Customer | ORACLE CORP-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 547523 | 547523 | 0 | 363961 | 5655 | 358306 | 312053 | 317708 | 46253 | 183562 | 229815 | 40% | 42% | 231734 | 2% | 277987 | 5655 | 272332 | 226079 | 231734 | 46253 | 0 | 0 | 0 | 0 | 85974 | 21494 | 85974 | -21494 | 2 | 558.5 | 14.2 | 544.3 | -556.5 | 0 | 556.5 | 0.2 | 0 | 0% | 27825% | 0.1 | 0 | 14 | 0.2 | 0 | 0 | 0 |  | 14.3 | 2 | 26194 Oracle OPC JSD
26208 | 26208 Orange SA JSD | Subramaniam, Ragunath | Awarded | Booked | Green | 2017-03-31 |  | 2017-12-31 |  | 2017-06-19 |  | 80% | 0% |  | EMEA | France | France | Juniper Strategic Delivery |  |  | #NAME? | ORANGE SA-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  |  | 135000 | 0 | 135000 | 0 | 464 | -464 | 0 | 464 | -464 | 135000 | 134536 | 20% | 100% | 464 | 80% | 0 | 464 | -464 | 0 | 464 | -464 | 0 | 0 | 0 | 0 | 0 | 4299 | 0 | -4299 | 0 | 0 | 0.7 | 0 | -0.6875 | 0 | 0 | 0.7 | 0 | 0% | 0% | 0 | 0 | 0 | 0.7 | 0 | 0 | 0 |  | 0.7 |  | 26208 Orange SA JSD
26215 | 26215 Telstra - Resiliency work - Bain#41 - T&M | Davis, Joseph | Awarded | In Progress | Green | 2017-03-29 | 2017-03-15 | 2018-02-28 |  | 2017-07-06 | 43% | 3% | 0% | Under/Not Over budget | APAC | ANZ | Australia | Core & Edge |  |  | TELSTRA CORPORATION-Customer | TELSTRA CORPORATION LIMITED-EndUser | PO | Milestone Payments | Consulting – T & M |  | B | 282690 | 86092 | 196598 | 211577 | 87884 | 123694 | 115089 | 202973 | 8604 | 71113 | 79717 | 25% | 28% | 202973 | 3% | 211577 | 87884 | 123694 | 115089 | 202973 | 8604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 95.3 | 124.8 | 0 | 0 | 0 | 2.6 | 0 | 0% | 1% | 0 | 0 | 92.6 | 2.6 | 0 | 0 | 0 |  | 95.3 | 1 | 26215 Telstra - Resiliency work - Bain#41 - T&M
26218 | 26218 OSP SB PE Growth FFP 1 MS | Oliver, Juan | Awarded | Complete | Green | 2017-02-27 | 2017-03-14 | 2017-07-21 |  |  | 63% | 23% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT ORANGE-EndUser | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 5189 | 5189 | 0 | 3147 | 1800 | 1347 | 662 | 2461 | 686 | 2042 | 2728 | 30% | 53% | 1812 | 23% | 2506 | 1151 | 1355 | 662 | 1812 | 694 | 0 | 0 | 0 | 0 | 641 | 649 | 0 | -8 | 3.2 | 3.2 | 2 | 1.2 | 0 | 0 | 0 | 1.8 | 0 | 0% | 125% | 0 | 0 | 0.3 | 1.8 | 0 | 0 | 0 |  | 2 | 1 | 26218 OSP SB PE Growth FFP 1 MS
26223 | 26223 WIND MPC7 Testing FFP Phase 1 4 MS | Masci, Fabio | Awarded | In Progress | Green | 2017-06-30 | 2017-05-22 | 2017-10-31 |  | 2017-06-30 | 20% | 0% | 0% |  | EMEA | ENA-R-SOUTH | Italy | Core & Edge |  |  | #NAME? | WIND-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 70000 | 0 | 70000 | 69567 | 9461 | 60106 | 53152 | 62612 | 6954 | 433 | 7388 | 11% | 11% | 46496 | 0% | 53451 | 9228 | 44223 | 37269 | 46496 | 6954 | 16116 | 233 | 15883 | 0 | 0 | 0 | 0 | 0 | 58.8 | 58.8 | 11.6 | 47.1 | 0 | 23.5 | 23.5 | 0.4 | 23.1 | 67% | 67% | 0.1 | 0 | 11.3 | 0.4 | 0 | 0 | 0 |  | 11.8 | 1 | 26223 WIND MPC7 Testing FFP Phase 1 4 MS
26231 | 26231 BT Harlequin LNS and vRR (NFX and MX) FFP 5MS | Foster, David | Awarded | In Progress | Amber | 2017-03-25 | 2017-04-25 | 2017-09-29 |  | 2017-07-14 | 32% | 10% | 0% | Customer Issues | EMEA | UK-I | United Kingdom | Core & Edge |  |  | BT Retail-Customer | BT RETAIL-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 114736 | 0 | 114736 | 72706 | 24313 | 48393 | 50252 | 74565 | -1859 | 42030 | 40171 | 25% | 35% | 72990 | 10% | 71131 | 24229 | 46902 | 48761 | 72990 | -1859 | 1575 | 84 | 1491 | 0 | 0 | 0 | 0 | 0 | 84.4 | 84.4 | 27.3 | 57.1 | 0 | 0 | 0 | 3.6 | 0 | 0% | 4% | 0.1 | 0 | 17.6 | 3.6 | 0 | 6.1 | 0 |  | 27.4 | 1 | 26231 BT Harlequin LNS and vRR (NFX and MX) FFP 5MS
26232 | 26232 BT Harlequin MX Upgrade Plan Validation FFP 1MS | Foster, David | Awarded | In Progress | Amber | 2017-03-29 | 2017-05-10 | 2017-07-21 |  | 2017-07-14 | 43% | 10% | 0% | Customer Issues | EMEA | UK-I | United Kingdom | Core & Edge |  |  | BT Retail-Customer | BT RETAIL-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 10221 | 0 | 10221 | 6639 | 2479 | 4159 | 4147 | 6626 | 12 | 3583 | 3595 | 25% | 35% | 5636 | 10% | 5649 | 2479 | 3169 | 3157 | 5636 | 12 | 990 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 7.2 | 7.2 | 3.1 | 4.1 | 0 | 0 | 0 | 1.3 | 0 | 0% | 21% | 0 | 0 | 1.8 | 1.3 | 0 | 0.1 | 0 |  | 3.1 | 1 | 26231 BT Harlequin LNS and vRR (NFX and MX) FFP 5MS | 26232 BT Harlequin MX Upgrade Plan Validation FFP 1MS
26266 | 26266 Algeria Telecom JSA Tuning and Design FFP 1 MS | Chouaieb, Mejda | Opportunity | In Progress - Working at Risk | Amber |  | 2017-03-30 | 2017-07-07 |  | 2017-06-30 | 139% | 1% | -39% | Product Issues | EMEA | ENA-R-SOUTH | Algeria | SDN |  |  | #NAME? | Algeria Telecom | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 29754 | 0 | 29754 | 18234 | 16024 | 2210 | 4620 | 20644 | -2410 | 11520 | 9110 | 30% | 31% | 16024 | 1% | 13614 | 16024 | -2410 | 0 | 16024 | -2410 | 4620 | 0 | 4620 | 0 | 0 | 0 | 0 | 0 | 14.4 | 14.4 | 20 | 0 | -5.5738 | 13 | 13 | 4.5 | 8.5 | 903% | 185% | 0.1 | 0 | 5.9 | 4.5 | 0 | 0 | 9.6 |  | 20.1 | 1 | 26266 Algeria Telecom JSA Tuning and Design FFP 1 MS
26268 | 26268 - Tractor Supply Company OnboardingII | Ross, David | Awarded | In Progress | Green |  | 2017-06-05 | 2017-09-15 | 2017-09-15 | 2017-07-12 | 48% | 35% | -33% |  | AMER | US TERRITORIES | United States of America | Core & Edge |  |  | CDW - Customer | Tractor Supply Company - End User | PO | Monthly in Arrears | Consulting – T & M |  | A | 70310 | 0 | 70310 | 27650 | 11901 | 15749 | 12726 | 24627 | 3023 | 42660 | 45683 | 30% | 65% | 19227 | 35% | 22250 | 10555 | 11695 | 8672 | 19227 | 3023 | 5400 | 1346 | 4054 | 0 | 0 | 0 | 0 | 0 | 15 | 19.9 | 9.5 | 10.4 | -4.875 | 7.5 | 12.4 | 1 | 6.5 | 100% | 165% | 2.4 | 0 | 4.6 | 1 | 3.9 | 0 | 0 |  | 11.9 | 1 | 26268 - Tractor Supply Company OnboardingII
26270 | 26270 Riot Games 150 PS Credits | Martin, David | Awarded | Booked | Green | 2017-03-02 | 2017-03-01 | 2018-03-01 |  | 2017-06-07 | 0% | 58% | 0% |  | AMER | CLOUD PROVIDERS | United States of America | Core & Edge |  |  | Independent Technology Group-Customer | Riot Games-EndUser | PO/Tokens | Fully in Advance | Consulting – Fixed Price Custom |  | B | 297000 | 297000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 297000 | 297000 | 42% | 100% | 0 | 58% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.1 | 1 | 26270 Riot Games 150 PS Credits
26301 | 26301 ATOS Contrail Jumpstart and T&M 8 Days | Subramaniam, Ragunath | Awarded | Booked | Green | 2017-03-31 |  | 2018-01-30 |  | 2017-06-19 | 40% | 52% | 0% |  | EMEA | France | France | SDN |  |  | WESTCON-Customer | ATOS INFOGERANCE-EndUser | PO | Upon Completion | Consulting – Packaged |  | A | 51300 | 0 | 51300 | 0 | 2780 | -2780 | 4125 | 6905 | -6905 | 51300 | 44395 | 35% | 87% | 6905 | 52% | 0 | 2780 | -2780 | 4125 | 6905 | -6905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 3.2 | 4.8 | 0 | 0 | 0 | 0.8 | 0 | 0% | 12% | 0 | 0 | 2.4 | 0.8 | 0 | 0 | 0 |  | 3.2 | 1 | 26301 ATOS Contrail Jumpstart and T&M 8 Days
26312 | 26312 Fiberail - FSB Eastern Main - FFP | Ang, Soon Aun | Awarded | On Hold | Green | 2017-03-21 | 2017-03-29 | 2017-08-31 |  | 2017-07-21 | 108% | 71% | -8% | Under/Not Over budget | APAC | ASEAN | Malaysia | Cloud |  |  | ECS HOLDING COMPANY-Customer | FIBERAIL SDN BHD (190730-W) - EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | A | 11145 | 0 | 11145 | 8450 | 161 | 8289 | 350 | 511 | 7939 | 2695 | 10634 | 24% | 95% | 161 | 71% | 8100 | 161 | 7939 | 0 | 161 | 7939 | 0 | 0 | 0 | 0 | 350 | 0 | 350 | 0 | 13 | 13 | 14 | 0 | -1 | 13 | 13 | 0.3 | 12.8 | 0% | 1300% | 0 | 0 | 13.8 | 0.3 | 0 | 0 | 0 |  | 14 | 1 | 26312 Fiberail - FSB Eastern Main - FFP
26313 | 26313 DT JSD Engagement FOC/Carve-Out | M, Rahimunnisa | Awarded | In Progress | Green | 2017-03-31 | 2017-01-01 | 2017-12-31 |  | 2017-06-27 |  | -66% | 0% |  | EMEA | DACH | Germany | Juniper Strategic Delivery |  |  | DEUTSCHE TELEKOM-Customer | DEUTSCHE TELEKOM-EndUser | Reclass | None | Consulting – Fixed Price Custom |  | B | 968000 | 0 | 968000 | 1113000 | 191193 | 921808 | 1113000 | 1304193 | -191193 | -145000 | -336193 | 32% | -35% | 191193 | -66% | 0 | 191193 | -191193 | 0 | 191193 | -191193 | 1113000 | 0 | 1113000 | 0 | 0 | 169000 | 0 | -169000 | 0 | 0 | 413.5 | 0 | -413.5 |  | 0 | 0 |  | 0% | 0% | 123 | 0 | 413.5 | 0 | 0 | 0 | 0 |  | 536.5 | 1 | 26313 DT JSD Engagement FOC/Carve-Out
26314 | 26314 Swisscom SULTAN assistance w/ Migration discussion/POC T&M 15 (FOC) | M, Rahimunnisa | Awarded | Booked | Green |  |  | 2017-07-31 |  | 2017-06-23 | 8% | 0% | 0% |  | EMEA | ENA-R-NORTH | Switzerland | Core & Edge |  |  | SWISSCOM LTD-Customer | SWISSCOM AG-EndUser | Free of Charge | None | Consulting – T & M |  | A | 0 | 0 | 0 | 0 | 501 | -501 | 5832 | 6334 | -6334 | 0 | -6334 | 0% | 0% | 6334 | 0% | 0 | 501 | -501 | 5832 | 6334 | -6334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 1.2 | 13.8 | 0 | 0 | 0 | 1.2 | 0 | 0% | 9% | 0 | 0 | 0 | 1.2 | 0 | 0 | 0 |  | 1.2 | 1 | 26314 Swisscom SULTAN assistance w/ Migration discussion/POC T&M 15 (FOC)
26315 | 26315 Orange MS-DPC to MS-MPC migration FFP 2 MS | Chouaieb, Mejda | Awarded | In Progress | Green | 2017-03-31 | 2017-05-10 | 2017-08-31 |  | 2017-06-30 | 66% | 24% | 0% | Under/Not Over budget | EMEA | France | France | Core & Edge |  |  | ORANGE SA-Customer | ORANGE FRANCE-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 26636 | 26636 | 0 | 7643 | 8196 | -553 | 3542 | 11738 | -4095 | 18993 | 14898 | 32% | 56% | 11738 | 24% | 7643 | 8196 | -553 | 3542 | 11738 | -4095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.2 | 17.2 | 11.4 | 5.8 | 0 | 0 | 0 | 4.3 | 0 | 0% | 33% | 1 | 0 | 7.1 | 4.3 | 0 | 0 | 0 |  | 12.4 | 1 | 26315 Orange MS-DPC to MS-MPC migration FFP 2 MS
26317 | 26317 STC CLOUD BNG Migration & AAA Integration FFP 3MS | Bin Sabbar, Abdullah | Awarded | In Progress | Green | 2017-05-17 | 2017-05-01 | 2017-07-31 |  | 2017-07-06 |  | 38% | 0% |  | EMEA | MEA | Saudi Arabia | Core & Edge |  |  | ARABIAN INTERNET & COMMUNICATIONS SERVICES COMPANY - Customer | STC - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 62135 | 54072 | 8063 | 42243 | 15089 | 27155 | 3630 | 18719 | 23525 | 19892 | 43416 | 32% | 70% | 15089 | 38% | 38613 | 15089 | 23525 | 0 | 15089 | 23525 | 3630 | 0 | 3630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.3 | 0 | -18.25 | 0 | 0 | 1.6 | 0 | 0% | 10% | 0 | 0 | 16.6 | 1.6 | 0 | 0 | 0 |  | 18.3 | 1 | 26317 STC CLOUD BNG Migration & AAA Integration FFP 3MS
26326 | 26326 Fiberail - FSB Eastern Sub - FFP | Ang, Soon Aun | Awarded | On Hold | Green | 2017-03-21 | 2017-03-30 | 2017-08-31 |  | 2017-07-21 | 31% | 70% | 0% | Under/Not Over budget | APAC | ASEAN | Malaysia | Cloud |  |  | ECS HOLDING COMPANY-Customer | FIBERAIL SDN BHD (190730-W) - EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | A | 11145 | 11145 | 0 | 8450 | 80 | 8370 | 531 | 611 | 7839 | 2695 | 10534 | 24% | 95% | 261 | 70% | 8100 | 80 | 8020 | 181 | 261 | 7839 | 0 | 0 | 0 | 0 | 350 | 0 | 350 | 0 | 13 | 13 | 4 | 9 | 0 | 12 | 12 | 0 | 12 | 1200% | 1200% | 0 | 0 | 4 | 0 | 0 | 0 | 0 |  | 4 | 1 | 26326 Fiberail - FSB Eastern Sub - FFP
26328 | 26328 NTT Singapore - APG Expansion Ph3 - FFP | Ang, Soon Aun | Awarded | In Progress | Green | 2017-04-17 | 2017-06-01 | 2017-07-21 |  | 2017-07-21 | 93% | -18% | -111% | Product Issues | APAC | ASEAN | Singapore | Cloud |  |  | NERA TELECOMMUNICATIONS LTD-Customer | NTT SINGAPORE PTE LTD-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | A | 35309 | 0 | 35309 | 23680 | 11371 | 12309 | 18781 | 30152 | -6472 | 11629 | 5157 | 33% | 15% | 12172 | -18% | 5700 | 11371 | -5671 | 801 | 12172 | -6472 | 0 | 0 | 0 | 0 | 17980 | 0 | 17980 | 0 | 9 | 19 | 17.8 | 1.3 | -10 | 4.5 | 4.5 | 17.8 | 0 | 100% | 1420% | 0 | 0 | 0 | 17.8 | 0 | 0 | 0 |  | 17.8 | 2 | 26328 NTT Singapore - APG Expansion Ph3 - FFP
26329 | 26329 TIM NFV Accenture PS Consultancy T&M 8 days | M, Rahimunnisa | Awarded | In Progress | Green | 2017-04-26 | 2017-05-09 | 2017-07-31 | 2017-07-31 | 2017-06-23 | 94% | 29% | 0% |  | EMEA | ENA-R-SOUTH | Italy | SDN |  |  | ERICSSON AB | TELECOM ITALIA MOBILE-EndUser | PO | Milestone Payments | Consulting – T & M |  | A | 18500 | 18500 | 0 | 12140 | 6598 | 5542 | 242 | 6840 | 5300 | 6360 | 11660 | 34% | 63% | 6840 | 29% | 12140 | 6598 | 5542 | 242 | 6840 | 5300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 7.5 | 0.5 | 0 | 8 | 8 | 0.8 | 7.3 | 0% | 0% | 0.2 | 0 | 6.8 | 0.8 | 0 | 0 | 0 |  | 7.7 | 1 | 26329 TIM NFV Accenture PS Consultancy T&M 8 days
26345 | 26345 Comcast-Savannah MX2010 Install(PSCredits) | Smith, Ronald | Awarded | In Progress | Green |  | 2017-06-05 | 2017-10-31 | 2017-10-31 | 2017-07-21 | 32% | 7% | 0% | Scoping Issues | AMER | CABLES | United States of America | Core & Edge |  |  | COMCAST CORPORATION-Customer | COMCAST-EndUser | Token/Credit | Milestone Payments | Install Custom |  | A | 108100 | 4950 | 103150 | 77741 | 60749 | 16993 | 7236 | 67985 | 9757 | 30359 | 40115 | 30% | 37% | 7733 | 7% | 17490 | 3347 | 14143 | 4386 | 7733 | 9757 | 2850 | 0 | 2850 | 0 | 57401 | 57401 | 0 | 0 | 9 | 9 | 2.9 | 6.1 | 0 | 7 | 7 | 2.9 | 4.1 | 350% | 350% | 1.8 | 0 | 0 | 2.9 | 0 | 0 | 0 |  | 4.7 | 1 | 26345 Comcast-Savannah MX2010 Install(PSCredits)
26349 | 26349 TEF Fusion HL1 Migrations | Gil, Jose | Awarded | In Progress | Green | 2017-03-03 | 2017-03-13 | 2017-07-30 |  |  | 15% | 7% | 0% |  | EMEA | Spain | Spain | Core & Edge |  |  | TELEFONICA DE ESPANA (FUSION)-EndUser | TELEFONICA DE ESPANA (FUSION)-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 82642 | 0 | 82642 | 47500 | 30835 | 16665 | 54808 | 85643 | -38143 | 35142 | -3001 | -10% | -4% | 38143 | 7% | 0 | 5820 | -5820 | 32323 | 38143 | -38143 | 2500 | 0 | 2500 | 0 | 45000 | 25015 | 19985 | 0 | 54 | 54 | 8.3 | 45.8 | 0 | 0 | 0 | 4.8 | 0 | 0% | 10% | 0 | 0 | 3.5 | 4.8 | 0 | 0 | 0 |  | 8.3 | 1 | 26349 TEF Fusion HL1 Migrations
26372 | 26372 University of Texas (TAMU) - 50 PS Credits | Martin, David | Awarded | Booked | Green | 2017-05-24 | 2017-05-24 | 2018-05-23 | 2018-05-23 | 2017-06-07 | 0% | 58% | 0% |  | AMER | US TERRITORIES | United States of America | Core & Edge |  |  | M&S TECHNOLOGIES-Customer | University of Texas TAMU- End User | PO/Tokens | Milestone Payments | Consulting – Fixed Price Custom |  |  | 104500 | 104500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104500 | 104500 | 42% | 100% | 0 | 58% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.00875 | 0 | 0 | 0 | 0 | 0% | 0% | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.1 |  | 26372 University of Texas (TAMU) - 50 PS Credits
26373 | 26373 Ricoh - UTM/WAN/LAN - CSAT | Oyama, Hirofumi | Awarded | In Progress | Green |  | 2017-02-21 | 2017-08-31 |  | 2017-06-27 | 89% | 0% | -67% | Under/Not Over budget | APAC | Japan | Japan | Security |  |  | RICOH JAPAN CORPORATION-Enduser | RICOH JAPAN CORPORATION-Enduser | CSAT | None | Consulting – T & M |  |  | 0 | 0 | 0 | 0 | 112168 | -112168 | 10147 | 122315 | -122315 | 0 | -122315 | 0% | 0% | 116800 | 0% | 0 | 106654 | -106654 | 10147 | 116800 | -116800 | 0 | 0 | 0 | 0 | 0 | 5514 | 0 | -5514 | 114.8 | 191.3 | 170.4 | 20.8 | -76.5 | 113.8 | 191.3 | 69.4 | 44.3 | 11375% | 0% | 0 | 4.6 | 0 | 69.4 | 0 | 0 | 101 |  | 175.1 | 1 | 26373 Ricoh - UTM/WAN/LAN - CSAT
26383 | 26383 VF IT GTP Firewall FFP 11 MS | Moreno, Carlos | Awarded | In Progress | Green | 2017-06-30 | 2017-06-20 | 2017-10-31 |  | 2017-07-04 | 3% | -4% | 0% |  | EMEA | UK-I | Italy | Security |  |  | VODAFONE | VODAFONE ITALY-EndUser | PO | Milestone Payments | Install Custom |  | B | 122649 | 0 | 122649 | 98086 | 41268 | 56818 | 59927 | 101195 | -3109 | 24563 | 21454 | 21% | 17% | 53827 | -4% | 50718 | 1322 | 49396 | 52505 | 53827 | -3109 | 6352 | 0 | 6352 | 0 | 41016 | 39946 | 1070 | 0 | 72.5 | 72.5 | 2.4 | 70.1 | 0 | 16.5 | 16.5 | 2.4 | 14.1 | 29% | 29% | 0.8 | 0 | 0 | 2.4 | 0 | 0 | 0 |  | 3.1 | 1 | 26383 VF IT GTP Firewall FFP 11 MS
26385 | 26385 OSP SB Extensions FFP 10 Quotes | Oliver, Juan | Awarded | Booked | Green | 2017-04-10 | 2017-04-27 | 2017-08-31 |  |  | 68% | 10% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT ORANGE-EndUser | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  |  | 136625 | 18963 | 117662 | 100682 | 19503 | 81179 | 69687 | 89190 | 11492 | 35943 | 47435 | 25% | 35% | 7012 | 10% | 18504 | 4800 | 13704 | 2212 | 7012 | 11492 | 0 | 0 | 0 | 0 | 82179 | 14704 | 67475 | 0 | 12.6 | 12.6 | 8.6 | 4 | 0 | 0 | 0 | 8.6 | 0 | 0% | 217% | 0 | 0 | 0 | 8.6 | 0 | 0 | 0 |  | 8.6 | 1 | 26385 OSP SB Extensions FFP 10 Quotes
26392 | 26392 Equinix - SG 7800 #21 - FFP | Ang, Soon Aun | Awarded | On Hold | Green | 2017-06-27 | 2017-09-27 | 2017-09-30 |  | 2017-07-21 | 0% | -42% | 0% | Under/Not Over budget | APAC | ASEAN | Singapore | Cloud |  |  | EQUINIX, INC.-Customer | EQUINIX (SINGAPORE) ENTERPRISES PTE. LTD-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | A | 16617 | 0 | 16617 | 9700 | 0 | 9700 |  |  |  | 6917 |  | 42% | 0% |  | -42% | 5400 | 0 | 5400 |  |  |  | 0 | 0 | 0 | 0 | 4300 | 0 | 4300 | 0 | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 26392 Equinix - SG 7800 #21 - FFP
26426 | 26426 Airbus PS/CP FW Migration SRX TM 20 Days | Subramaniam, Ragunath | Awarded | In Progress | Green | 2017-04-05 | 2017-03-20 | 2017-09-20 |  | 2017-06-19 | 7% | 23% | 0% |  | EMEA | France | France | Security |  |  | FRANCE TELECOM SA (DBA: ORANGE BUSINESS SERVICES)-EndUser | Airbus | PO | Fully in Advance | Consulting – T & M |  | A | 55750 | 55750 | 0 | 4600 | 992 | 3608 | 28858 | 29850 | -25250 | 51150 | 25900 | 24% | 46% | 25250 | 23% | 0 | 992 | -992 | 24258 | 25250 | -25250 | 4600 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 1.5 | 18.5 | 0 | 0 | 0 | 1.5 | 0 | 0% | 8% | 0.3 | 0 | 0 | 1.5 | 0 | 0 | 0 |  | 1.7 | 1 | 26426 Airbus PS/CP FW Migration SRX TM 20 Days
26427 | 26427 Comcast MPC6 Swaps (FOC) | Smith, Ronald | Awarded | In Progress | Amber |  | 2017-06-12 | 2017-12-31 | 2017-12-31 | 2017-07-21 | 10% | 0% | 0% | Scoping Issues | AMER | CABLES | United States of America | Core & Edge |  |  | COMCAST-EndUser | COMCAST-EndUser | Free of Charge | None | Install Custom |  | B | 0 | 0 | 0 | 698544 | 64076 | 634468 | 627627 | 691704 | 6840 | -698544 | -691704 | 0% | 0% | 250834 | 0% | 257674 | 26576 | 231098 | 224257 | 250834 | 6840 | 1840 | 0 | 1840 | 0 | 439030 | 37500 | 401530 | 0 | 217.6 | 217.6 | 21.6 | 196.1 | 0 | 101.5 | 101.5 | 10.2 | 91.3 | 87% | 87% | 12.8 | 0 | 11.4 | 10.2 | 0 | 0 | 0 |  | 34.4 | 1 | 26427 Comcast MPC6 Swaps (FOC)
26430 | 26430 VF TR CGNAT LTE SecGW Support T&M 10 days | M, Rahimunnisa | Awarded | Booked | Green | 2017-03-31 |  | 2017-07-28 |  | 2017-06-23 | 5% | 56% | 0% |  | EMEA | UK-I | Turkey | Core & Edge |  |  | BNTPRO BILGI VE ILETISIM HIZMETLERI LTD-Customer | VODAFONE-EndUser | PO | Milestone Payments | Consulting – T & M |  | A | 22500 | 0 | 22500 | 15175 | 211 | 14964 | 4011 | 4222 | 10953 | 7325 | 18278 | 25% | 81% | 4222 | 56% | 15175 | 211 | 14964 | 4011 | 4222 | 10953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0.5 | 9.5 | 0 | 0 | 0 | 0.5 | 0 | 0% | 5% | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 |  | 0.5 | 1 | 26430 VF TR CGNAT LTE SecGW Support T&M 10 days
26440 | 26440 LA FRANCAISE AM 3xDC (EX+QFX+SRX) JTAC cases Audits FFP xMS | Chouaieb, Mejda | Awarded | In Progress | Green | 2017-06-26 | 2017-07-03 | 2017-07-31 |  | 2017-07-13 | 35% | -3% | 0% | Under/Not Over budget | EMEA | France | France | Cloud |  |  | TS EUROPE BVBA - Customer | LA FRANCAISE AM-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 17873 | 0 | 17873 | 10667 | 2938 | 7729 | 8272 | 11210 | -543 | 7206 | 6663 | 40% | 37% | 8669 | -3% | 8126 | 2938 | 5188 | 5731 | 8669 | -543 | 2541 | 0 | 2541 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 3.1 | 5.9 | 0 | 9 | 9 | 1 | 8 | 0% | 0% | 0.4 | 0 | 2.1 | 1 | 0 | 0 | 0 |  | 3.5 | 1 | 26440 LA FRANCAISE AM 3xDC (EX+QFX+SRX) JTAC cases Audits FFP xMS
26442 | 26442 TEF Fusion HL4 Migration MAN (VALENCIA/CASTELLON) FFP 3 MS | Gil, Jose | Awarded | In Progress | Green | 2017-04-04 | 2017-04-03 | 2017-12-15 |  |  | 8% | 77% | 0% |  | EMEA | Spain | Spain | Core & Edge |  |  | TELEFONICA DE ESPANA (FUSION)-EndUser | TELEFONICA DE ESPANA (FUSION)-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 1275966 | 0 | 1275966 | 0 | 149442 | -149442 | 93229 | 242671 | -242671 | 1275966 | 1033294 | 4% | 81% | 100874 | 77% | 0 | 7645 | -7645 | 93229 | 100874 | -100874 | 0 | 188 | 0 | -188 | 0 | 141610 | 0 | -141610 | 180 | 180 | 13.6 | 166.4 | 0 | 0 | 0 | 13.6 | 0 | 0% | 8% | 0 | 0 | 0 | 13.6 | 0 | 0 | 0 |  | 13.6 | 1 | 26442 TEF Fusion HL4 Migration MAN (VALENCIA/CASTELLON) FFP 3 MS
26447 | 26447 Sky CISCO ACL Conversion FFP 3 MS | Chouaieb, Mejda | Awarded | In Progress | Green | 2017-06-27 | 2017-06-05 | 2017-10-02 |  | 2017-06-30 | 54% | -9% | 0% | Under/Not Over budget | EMEA | DACH | Germany | Security |  |  | DIMENSION DATA-EndUser | SKY DEUTSCHLAND AG-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 31341 | 0 | 31341 | 14220 | 11645 | 2575 | 10012 | 21657 | -7437 | 17121 | 9684 | 40% | 31% | 21657 | -9% | 14220 | 11645 | 2575 | 10012 | 21657 | -7437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.1 | 19.1 | 10.3 | 8.9 | 0 | 16.6 | 16.6 | 2.4 | 14.2 | 664% | 664% | 0 | 0 | 7.9 | 2.4 | 0 | 0 | 0 |  | 10.3 | 1 | 26447 Sky CISCO ACL Conversion FFP 3 MS
26450 | 26450 Starhub - RAR Expansion - T&M | Ang, Soon Aun | Awarded | In Progress | Green | 2017-04-17 | 2017-03-16 | 2017-09-30 |  | 2017-07-21 | 113% | 66% | -13% | Under/Not Over budget | APAC | ASEAN | Singapore | Cloud |  |  | NERA TELECOMMUNICATIONS LTD-Customer | STARHUB LTD-EndUser | PO | Milestone Payments | Consulting – T & M |  | A | 1581 | 791 | 791 | 1200 | 161 | 1039 | 0 | 161 | 1039 | 381 | 1421 | 24% | 90% | 161 | 66% | 1200 | 161 | 1039 | 0 | 161 | 1039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2.3 | 0 | -0.25 | 2 | 2 | 0.3 | 1.8 | 0% | 800% | 0 | 0 | 2 | 0.3 | 0 | 0 | 0 |  | 2.3 | 1 | 26450 Starhub - RAR Expansion - T&M
26453 | 26453 Flag Telecom - SG GCX EQX FIBERCOMM 02X100G Part 1 (SG) - FFP | Ang, Soon Aun | Awarded | In Progress | Green | 2017-03-28 | 2017-04-10 | 2017-09-30 |  | 2017-07-21 | 126% | -1% | -26% | SOW Issues | APAC | ASEAN | Singapore | Cloud |  |  | TRANSITION SYSTEMS ASIA PTE LTD-Customer | FLAG TELECOM SINGAPORE PTE LTD - EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 61080 | 61080 | 0 | 49808 | 29194 | 20614 | 21502 | 50696 | -888 | 11272 | 10384 | 18% | 17% | 27888 | -1% | 27000 | 27888 | -888 | 0 | 27888 | -888 | 17900 | 0 | 17900 | 0 | 4908 | 1307 | 3602 | 0 | 45 | 45 | 56.8 | 0 | -11.75 | 6 | 6 | 13.9 | 0 | 16% | 32% | 0 | 1.5 | 42.9 | 13.9 | 0 | 0 | 0 |  | 58.3 | 1 | 26453 Flag Telecom - SG GCX EQX FIBERCOMM 02X100G Part 1 (SG) - FFP
26464 | 26464 Lockheed Martin Aero FW Policy Conversion - PS Credits | Wiesner, Jill | Awarded | In Progress | Green |  | 2017-05-29 | 2017-06-30 | 2017-07-07 | 2017-06-23 | 27% | 8% | 0% | Under/Not Over budget | AMER | NATIONAL GOVERNMENT | United States of America | Security |  |  | LOCKHEED MARTIN-EndUser | LOCKHEED MARTIN-EndUser | Token/Credit | Milestone Payments | Consulting – Fixed Price Custom |  | A | 19800 | 0 | 19800 | 11921 | 3286 | 8635 | 8488 | 11775 | 146 | 7879 | 8025 | 33% | 41% | 11775 | 8% | 11921 | 3286 | 8635 | 8488 | 11775 | 146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 2.8 | 7.3 | 0 | 10 | 10 | 0.9 | 9.1 | 800600% | 0% | 0.2 | 0 | 1.6 | 0.9 | 0.3 | 0 | 0 |  | 2.9 | 1 | 24286 LMCO AERO CREDIT BOOKING - 10 CREDITS | 26464 Lockheed Martin Aero FW Policy Conversion - PS Credits
26467 | 26467 MTNL - Junos Space Implementation - FFP | Pathak, Nishant | Awarded | In Progress | Green | 2017-03-22 | 2017-03-20 | 2017-09-21 |  | 2017-06-30 | 92% | 10% | 0% |  | APAC | India | India | Core & Edge |  |  | Nokia Siemens Networks (NSN)-Customer | MAHANAGAR TELEPHONE NIGAM LIMITED - EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 33734 | 14408 | 19326 | 25594 | 18466 | 7128 | 3918 | 22384 | 3210 | 8140 | 11350 | 24% | 34% | 6646 | 10% | 22044 | 6278 | 15766 | 368 | 6646 | 15398 | 3550 | 0 | 3550 | 0 | 0 | 12188 | 0 | -12188 | 36 | 36 | 33.3 | 2.8 | 0 | 10.6 | 10.6 | 12.6 | 0 | 42% | 54% | 0 | 0 | 18.3 | 12.6 | 0 | 0 | 2.4 |  | 33.3 | 1 | 26467 MTNL - Junos Space Implementation - FFP
26475 | 26475 WOW NW LSP Automation Ph 2 | Hassan, Saqib | Awarded | In Progress | Green | 2017-05-22 | 2017-05-31 | 2017-09-29 | 2017-12-01 | 2017-07-21 | 32% | 5% | 0% | Under/Not Over budget | AMER | CABLES | United States of America | Network Automation |  |  | WOW (Wide Open West Financial)-Customer | WOW-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 120437 | 36131 | 84306 | 84122 | 70760 | 13362 | 9024 | 79783 | 4339 | 36315 | 40654 | 29% | 34% | 11053 | 5% | 15392 | 4230 | 11162 | 6824 | 11053 | 4339 | 2200 | 0 | 2200 | 0 | 66530 | 66530 | 0 | 0 | 13.3 | 13.3 | 4.2 | 9.1 | 0 | 13.1 | 13.1 | 3.3 | 9.8 | 7681% | 7681% | 1.9 | 0 | 0.9 | 3.3 | 0 | 0 | 0 |  | 6.1 | 1 | 26475 WOW NW LSP Automation Ph 2
26476 | 26476 - University of Arkansas Agriculture Space SD/ND Implementation | Gregory, Mina | Awarded | Booked | Green |  | 2017-07-24 | 2017-08-31 |  | 2017-06-29 | 0% | 53% | 0% |  | AMER | US TERRITORIES | United States of America | Security |  |  | CXTec-Customer | UNIVERSITY OF ARKANSAS-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 40500 | 0 | 40500 | 30116 | 0 | 30116 | 8480 | 8480 | 21636 | 10384 | 32020 | 26% | 79% | 0 | 53% | 21636 | 0 | 21636 | 0 | 0 | 21636 | 8480 | 0 | 8480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.00875 | 0 | 0 | 0 | 0 | 0% | 0% | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.8 |  | 26476 - University of Arkansas Agriculture Space SD/ND Implementation
26477 | 26477 HPC 5 Days T&M | Wiesner, Jill | Awarded | In Progress | Green | 2017-04-17 | 2017-09-25 | 2017-09-29 | 2017-10-10 | 2017-07-19 | 1% | 25% | 0% | Under/Not Over budget | AMER | NATIONAL GOVERNMENT | United States of America | Security |  |  | World Wide Technologies | HPC-EndUser | PO | Monthly in Arrears | Consulting – T & M |  | A | 14305 | 0 | 14305 | 10650 | 79 | 10571 | 7117 | 7196 | 3454 | 3655 | 7109 | 25% | 50% | 3696 | 25% | 7150 | 79 | 7071 | 3617 | 3696 | 3454 | 3500 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0.1 | 4.9 | -0.00125 | 0 | 0 | 0.1 | 0 | 0% | 1% | 1.6 | 0 | 0 | 0.1 | 0 | 0 | 0 |  | 1.6 | 1 | 26477 HPC 5 Days T&M
26478 | 26478 ORANGE LK PS IGN (ext 25919) PS Consultancy T&M 20 days | Subramaniam, Ragunath | Awarded | In Progress | Green | 2017-03-31 | 2017-03-04 | 2017-09-04 |  | 2017-06-19 | 31% | 25% | 0% |  | EMEA | France | France | SDN |  |  | ORANGE SA-Customer | ORANGE SA-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 52250 | 52250 | 0 | 35850 | 5518 | 30332 | 17420 | 22938 | 12912 | 16400 | 29312 | 31% | 56% | 17438 | 25% | 30350 | 5518 | 24832 | 11920 | 17438 | 12912 | 5500 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 6.3 | 13.7 | 0 | 0 | 0 | 1.3 | 0 | 0% | 7% | 0 | 0 | 5 | 1.3 | 0 | 0 | 0 |  | 6.3 | 1 | 26478 ORANGE LK PS IGN (ext 25919) PS Consultancy T&M 20 days
26487 | 26487 BP FW Rule Change Automation FFP 2MS | Stirling, Alan | Opportunity | In Progress - Working at Risk | Green |  | 2017-05-29 | 2017-07-21 |  | 2017-07-21 | 15% | -53% | -100% | Customer Issues | EMEA | UK-I | United Kingdom | Network Automation |  |  | BP-EndUser | BP-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 63568 | 0 | 63568 | 38109 | 10602 | 27507 | 61363 | 71965 | -33856 | 25459 | -8397 | 40% | -13% | 70175 | -53% | 36319 | 10602 | 25717 | 59573 | 70175 | -33856 | 1790 | 0 | 1790 | 0 | 0 | 0 | 0 | 0 | 39.4 | 78.8 | 11.8 | 67.1 | -39.42 | 36.3 | 72.5 | 2 | 34.3 | 1151% | 1151% | 0 | 0 | 9.8 | 2 | 0 | 0 | 0 |  | 11.8 | 1 | 26487 BP FW Rule Change Automation FFP 2MS
26492 | 26492 FIBERCORP T&M | Almanza, Henry | Awarded | Booked | Green |  | 2017-07-31 | 2018-04-30 | 2018-07-27 | 2017-07-21 | 0% | 4% | 0% | Under/Not Over budget | AMER | CALA | Argentina | Core & Edge |  |  | CABLEVISION SYSTEMS CORPORATION-Customer | FIBERCORP-EndUser | PO | Monthly in Arrears | Consulting – T & M |  | B | 49500 | 0 | 49500 | 35400 | 0 | 35400 | 33600 | 33600 | 1800 | 14100 | 15900 | 28% | 32% | 0 | 4% | 1800 | 0 | 1800 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 33600 | 0 | 33600 | 0 | 0 | 0 | 0 | 0 | -0.01 | 0 | 0 | 0 | 0 | 0% | 700% | 1.9 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.9 |  | 26492 FIBERCORP T&M
26500 | 26500 Singtel - TM-Support - CGNAT - T&M | Pathak, Nishant | Awarded | In Progress | Green | 2017-03-29 | 2017-04-01 | 2018-03-31 |  |  | 51% | 35% | 0% |  | APAC | ASEAN | Singapore | Core & Edge |  |  | NERA TELECOMMUNICATIONS LTD-Customer | SINGAPORE TELECOMMUNICATIONS LIMITED-EndUser | PO | Upon Completion | Consulting – T & M |  | A | 149998 | 0 | 149998 | 109344 | 29755 | 79589 | 26599 | 56354 | 52990 | 40654 | 93644 | 27% | 62% | 56354 | 35% | 109344 | 29755 | 79589 | 26599 | 56354 | 52990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 102 | 52.5 | 49.5 | 0 | 102 | 102 | 5.1 | 96.9 | 0% | 0% | 0 | 1.4 | 46.9 | 5.1 | 0 | 0 | 0.5 |  | 53.9 | 1 | 26500 Singtel - TM-Support - CGNAT - T&M
26501 | 26501 Ooredoo Qatar ISP Peering PS Consultancy T&M 5 days | Bhinder, Muhammad Amir Rashid | Opportunity | Complete - Working at Risk | Green |  | 2017-05-17 | 2017-07-31 |  | 2017-07-06 |  | -11% | 0% | Under/Not Over budget | EMEA | MEA | Qatar | Core & Edge |  |  | MINDWARE S.A.-Customer | OOREDOO QTEL-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 14000 | 0 | 14000 | 9338 | 10483 | -1145 | 1117 | 11600 | -2262 | 4662 | 2400 | 28% | 17% | 9850 | -11% | 7588 | 9850 | -2262 | 0 | 9850 | -2262 | 1750 | 633 | 1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.6 | 0 | -12.625 | 0 | 0 | 1.5 | 0 | 0% | 13% | 0 | 1.3 | 8.8 | 1.5 | 0 | 0 | 2.4 |  | 13.9 |  | 26501 Ooredoo Qatar ISP Peering PS Consultancy T&M 5 days
26516 | 26516 Oracle Space SD POC | Kouzionis, Nicholas | Awarded | In Progress | Green |  | 2017-07-10 | 2017-08-31 |  | 2017-07-10 | 3% | 5% | 0% |  | AMER | CLOUD PROVIDERS | United States of America | Security |  |  | DIMENSION DATA HOLDINGS LTD-Customer | ORACLE CORP-EndUser | Token/Credit | None | Consulting – Fixed Price Custom |  | B | 36100 | 0 | 36100 | 21312 | 582 | 20730 | 19087 | 19669 | 1643 | 14788 | 16431 | 41% | 46% | 19669 | 5% | 21312 | 582 | 20730 | 19087 | 19669 | 1643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.5 | 0.5 | 18 | -18.5087 | 0 | 3 | 0.5 | 0 | 0% | 19% | 0.1 | 0 | 0 | 0.5 | 0 | 0 | 0 |  | 0.6 |  | 25137 Oracle 50 PS Credits | 26516 Oracle Space SD POC
26528 | 26528 Bell Canada SRC Upgrade | Hassan, Saqib | Awarded | In Progress | Green | 2017-05-16 | 2017-06-05 | 2017-08-31 | 2017-12-08 | 2017-07-21 | 45% | 31% | 0% | Under/Not Over budget | AMER | CANADA | Canada | Core & Edge |  |  | Bell Canada - Customer | BELL CANADA-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 89024 | 0 | 89024 | 54089 | 13467 | 40622 | 16733 | 30200 | 23889 | 34935 | 58824 | 35% | 66% | 30200 | 31% | 54089 | 13467 | 40622 | 16733 | 30200 | 23889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 27 | 12 | 15 | 0 | 15 | 15 | 2.8 | 12.3 | 125% | 125% | 0 | 0 | 9.3 | 2.8 | 0 | 0 | 0 |  | 12.1 | 1 | 26528 Bell Canada SRC Upgrade
26530 | 26530 Yardi FW Migration | Wiesner, Jill | Awarded | In Progress | Green | 2017-04-04 | 2017-04-17 | 2017-09-29 | 2017-09-29 | 2017-05-30 | 111% | 35% | -11% | Under/Not Over budget | AMER | US TERRITORIES | United States of America | Security |  |  | FUSIONSTORM-Customer | Yardi Systems - End User | PO | Milestone Payments | Consulting – Fixed Price Custom | Consulting – Packaged | B | 102150 | 0 | 102150 | 52323 | 38649 | 13674 | 464 | 39113 | 13210 | 49827 | 63037 | 27% | 62% | 37273 | 35% | 50483 | 37273 | 13210 | 0 | 37273 | 13210 | 1840 | 1376 | 464 | 0 | 0 | 0 | 0 | 0 | 35.5 | 35.5 | 39.4 | 0 | -3.875 | 20.5 | 20.5 | 4.9 | 15.6 | 137% | 109% | 0.7 | 1.3 | 34.3 | 4.9 | 0.3 | 0 | 0 |  | 41.3 | 1 | 26530 Yardi FW Migration
26534 | 26534 VZ FFP Atlanta_Dallas SBR Upgrade | Stroud, Charlie | Awarded | In Progress | Green | 2017-05-09 | 2017-03-27 | 2017-07-28 |  | 2017-06-29 | 67% | 1% | 0% |  | AMER | VERIZON | United States of America | Core & Edge |  |  | VERIZON COMMUNICATIONS-EndUser | VERIZON COMMUNICATIONS-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | A | 49000 | 0 | 49000 | 25300 | 18130 | 7170 | 5828 | 23958 | 1342 | 23700 | 25042 | 50% | 51% | 23958 | 1% | 25300 | 18130 | 7170 | 5828 | 23958 | 1342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.1 | 23.1 | 15.6 | 7.6 | 0 | 23.1 | 23.1 | 0 | 23.1 | 1850500% | 0% | 2.6 | 0 | 15.6 | 0 | 0 | 0 | 0 |  | 18.2 | 1 | 26534 VZ FFP Atlanta_Dallas SBR Upgrade
26538 | 26538 Cenitex - DC Firewall Migration - FFP | Davis, Joseph | Awarded | In Progress | Amber | 2017-06-20 | 2017-05-22 | 2017-08-18 |  | 2017-07-17 | 81% | -42% | -319% | Resource Issues | APAC | ANZ | Australia | Security |  |  | IBM-Customer | CENITEX-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 113593 | 47576 | 66018 | 78818 | 102743 | -23925 | 23573 | 126317 | -47499 | 34775 | -12723 | 31% | -11% | 71232 | -42% | 68715 | 57761 | 10954 | 13470 | 71232 | -2517 | 10103 | 0 | 10103 | 0 | 0 | 44982 | 0 | -44982 | 27 | 113 | 91.4 | 21.6 | -86 | 4.2 | 17.8 | 15.4 | 0 | 18% | 19% | 0 | 1 | 72 | 15.4 | 0 | 0 | 4 |  | 92.4 | 2 | 26538 Cenitex - DC Firewall Migration - FFP
26547 | 26547 VF IT MX LM Nord Expansion I&C FFP 5 MS | Moreno, Carlos | Awarded | In Progress | Green | 2017-04-28 | 2017-05-29 | 2017-07-28 |  | 2017-07-12 | 31% | 10% | 0% |  | EMEA | UK-I | Italy | Security |  |  | VODAFONE | VODAFONE ITALY-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 14373 | 14373 | 0 | 7575 | 3784 | 3791 | 2412 | 6196 | 1379 | 6798 | 8177 | 47% | 57% | 2852 | 10% | 4231 | 904 | 3327 | 1948 | 2852 | 1379 | 0 | 0 | 0 | 0 | 3344 | 2880 | 464 | 0 | 5.3 | 5.3 | 1.6 | 3.6 | 0 | 2.6 | 2.6 | 1.6 | 1 | 100% | 100% | 0.1 | 0 | 0 | 1.6 | 0 | 0 | 0 |  | 1.8 | 1 | 26547 VF IT MX LM Nord Expansion I&C FFP 5 MS
26553 | 26553 Starhub - Schedule4_excess_37_access_NE - FFP | Ang, Soon Aun | Awarded | In Progress | Green | 2017-06-30 | 2017-09-25 | 2017-12-25 |  | 2017-07-21 | 5% | 0% | 0% | Under/Not Over budget | APAC | ASEAN | Singapore | Cloud |  |  | STARHUB LTD-EndUser | STARHUB LTD-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | A | 155773 | 0 | 155773 | 77886 | 0 | 77886 | 77886 | 77886 | 0 | 77887 | 77887 | 50% | 50% | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77886 | 0 | 77886 | 0 | 60 | 60 | 3 | 57 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 3 | 1 | 26553 Starhub - Schedule4_excess_37_access_NE - FFP
26555 | 26555 Matrix - 3 Nodes 100G ROADM - FFP | Ang, Soon Aun | Awarded | In Progress | Green | 2017-06-30 | 2017-09-25 | 2017-10-03 |  | 2017-07-21 | 61% | 3% | 0% | Under/Not Over budget | APAC | ASEAN | Singapore | Cloud |  |  | DIMENSION DATA HOLDINGS LTD-Customer | MATRIX NETWORKS PTE. LTD. - EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | A | 16868 | 0 | 16868 | 11594 | 3526 | 8068 | 7495 | 11021 | 573 | 5274 | 5847 | 31% | 35% | 5771 | 3% | 6344 | 3526 | 2818 | 2245 | 5771 | 573 | 0 | 0 | 0 | 0 | 5250 | 0 | 5250 | 0 | 9 | 9 | 5.5 | 3.5 | 0 | 2 | 2 | 3 | 0 | 29% | 50% | 0 | 0 | 0 | 3 | 2.5 | 0 | 0 |  | 5.5 | 1 | 26555 Matrix - 3 Nodes 100G ROADM - FFP
26558 | 26558 Equinix JP - TY 7800 #11 TY1 - FFP | Ang, Soon Aun | Awarded | On Hold | Green | 2017-06-26 | 2017-09-28 | 2017-09-29 |  | 2017-07-21 | 13% | -1% | 0% | Under/Not Over budget | APAC | Japan | Japan | Cloud |  |  | EQUINIX (JAPAN) ENTERPRISES K.K.-EndUser | EQUINIX (JAPAN) ENTERPRISES K.K.-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | A | 9551 | 0 | 9551 | 6420 | 161 | 6259 | 6344 | 6504 | -84 | 3131 | 3047 | 33% | 32% | 1284 | -1% | 1200 | 161 | 1039 | 1124 | 1284 | -84 | 220 | 0 | 220 | 0 | 5000 | 0 | 5000 | 0 | 2 | 2 | 0.3 | 1.8 | 0 | 0 | 0 | 0.3 | 0 | 0% | 14% | 0 | 0 | 0 | 0.3 | 0 | 0 | 0 |  | 0.3 | 1 | 26558 Equinix JP - TY 7800 #11 TY1 - FFP
26559 | 26559 Equinix JP - TY 7800 #11 TY2 - FFP | Ang, Soon Aun | Awarded | On Hold | Green | 2017-06-26 | 2017-09-28 | 2017-09-29 |  | 2017-07-21 | 25% | -5% | 0% | Under/Not Over budget | APAC | Japan | Japan | Cloud |  |  | EQUINIX (JAPAN) ENTERPRISES K.K.-EndUser | EQUINIX (JAPAN) ENTERPRISES K.K.-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | A | 1801 | 0 | 1801 | 1420 | 321 | 1099 | 1183 | 1504 | -84 | 381 | 297 | 21% | 16% | 1284 | -5% | 1200 | 321 | 879 | 963 | 1284 | -84 | 220 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0.5 | 1.5 | 0 | 0 | 0 | 0.5 | 0 | 0% | 33% | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 |  | 0.5 | 1 | 26559 Equinix JP - TY 7800 #11 TY2 - FFP
26560 | 26560 Equinix JP - TY 7800 #11 TY4 - FFP | Ang, Soon Aun | Awarded | On Hold | Green | 2017-06-26 | 2017-09-28 | 2017-09-29 |  | 2017-07-21 | 13% | -5% | 0% | Under/Not Over budget | APAC | Japan | Japan | Cloud |  |  | EQUINIX (JAPAN) ENTERPRISES K.K.-EndUser | EQUINIX (JAPAN) ENTERPRISES K.K.-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | A | 1801 | 0 | 1801 | 1420 | 161 | 1259 | 1344 | 1504 | -84 | 381 | 297 | 21% | 16% | 1284 | -5% | 1200 | 161 | 1039 | 1124 | 1284 | -84 | 220 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0.3 | 1.8 | 0 | 0 | 0 | 0.3 | 0 | 0% | 14% | 0 | 0 | 0 | 0.3 | 0 | 0 | 0 |  | 0.3 | 1 | 26560 Equinix JP - TY 7800 #11 TY4 - FFP
26565 | 26565 Etisalat Assessment Recommendations Execution T&M 18 days CSAT | Bhinder, Muhammad Amir Rashid | Awarded | In Progress | Green |  | 2017-03-23 | 2017-08-31 | 2017-10-31 | 2017-07-06 | 23% | 0% | 0% | Under/Not Over budget | EMEA | MEA | UAE | Core & Edge | Network Automation |  | Juniper | ETISALAT-EndUser | CSAT | None | Consulting – T & M |  | A | 0 | 0 | 0 | 2000 | 3217 | -1217 | 12481 | 15698 | -13698 | -2000 | -15698 | 0% | 0% | 13698 | 0% | 0 | 3217 | -3217 | 10481 | 13698 | -13698 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 3.5 | 11.5 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0.5 | 0 | 3 |  | 3.5 | 1 | 26565 Etisalat Assessment Recommendations Execution T&M 18 days CSAT
26578 | 26578 CRST BTI Upgrade | Meyer, James | Awarded | In Progress | Green | 2017-05-10 | 2017-06-08 | 2017-07-28 |  | 2017-07-12 | 3214% | 40% | 0% |  | AMER | US TERRITORIES | United States of America | Core & Edge |  |  | CRST Telephone Authority - End User | CRST Telephone Authority - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 18810 | 0 | 18810 | 10764 | 225 | 10539 | 2950 | 3175 | 7589 | 8046 | 15635 | 43% | 83% | 225 | 40% | 7814 | 225 | 7589 | 0 | 225 | 7589 | 2950 | 0 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | -0.28125 | 0 | 0 | 0.3 | 0 | 0% | 0% | 0.1 | 0 | 0 | 0.3 | 0 | 0 | 0 |  | 0.4 |  | 26578 CRST BTI Upgrade
26589 | 26589 Telstra - Engineering Drafting 60 Days - T&M | Saini, Shagun | Awarded | In Progress | Green | 2017-04-11 | 2017-05-15 | 2017-08-25 |  | 2017-07-14 | 88% | 6% | 0% | Under/Not Over budget | APAC | ANZ | Australia | Core & Edge |  |  | TELSTRA CORPORATION-Customer | TELSTRA CORPORATION LTD.-EndUser | PO | Upon Completion | Consulting – T & M |  | B | 87168 | 0 | 87168 | 69680 | 63252 | 6428 | 1447 | 64699 | 4981 | 17488 | 22469 | 20% | 26% | 12969 | 6% | 69680 | 11522 | 58158 | 1447 | 12969 | 56711 | 0 | 0 | 0 | 0 | 0 | 51729 | 0 | -51729 | 60 | 60 | 53.1 | 6.9 | 0 | 0 | 0 | 13.1 | 0 | 0% | 28% | 0 | 0 | 40 | 13.1 | 0 | 0 | 0 |  | 53.1 | 1 | 26589 Telstra - Engineering Drafting 60 Days - T&M
26590 | 26590 Etisalat NEC-Netcracker NSC Integration Support T&M 21 Days | Subramaniam, Ragunath | Opportunity | In Progress - Working at Risk | Green |  | 2017-04-10 | 2017-08-31 |  | 2017-06-19 | 175% | 49% | 33% |  | EMEA | MEA | UAE | SDN |  |  | NEC CORPORATION-Customer | ETISALAT-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 55440 | 0 | 55440 | 31868 | 4695 | 27173 | 0 | 4695 | 27173 | 23572 | 50745 | 43% | 92% | 4695 | 49% | 31868 | 4695 | 27173 | 0 | 4695 | 27173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 8 | 14 | 0 | 7 | 0 | 8 | 5.9 | 0 | 0% | 133% | 0.2 | 0 | 8.1 | 5.9 | 0 | 0 | 0 |  | 14.2 | 2 | 26590 Etisalat NEC-Netcracker NSC Integration Support T&M 21 Days
26592 | 26592 Telefonica O2 T&M 13 Days | M, Rahimunnisa | Awarded | Booked | Green | 2017-05-12 |  | 2017-07-31 |  | 2017-06-23 | 7% | 44% | 0% | Resource Issues | EMEA | DACH | Germany | Core & Edge |  |  | XANTARO DEUTSCHLAND GMBH-Customer | TELEFONICA O2 GERMANY GMBH & CO KG-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 28300 | 0 | 28300 | 21223 | 369 | 20854 | 7056 | 7425 | 13798 | 7077 | 20875 | 30% | 74% | 5930 | 44% | 19728 | 369 | 19359 | 5561 | 5930 | 13798 | 1495 | 0 | 1495 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0.9 | 12.1 | 0 | 0 | 0 | 0.9 | 0 | 0% | 7% | 0.3 | 0 | 0 | 0.9 | 0 | 0 | 0 |  | 1.1 | 1 | 26592 Telefonica O2 T&M 13 Days
26602 | 26602 Uber 2017 | Cicatello, James | Awarded | In Progress - Working at Risk | Amber |  | 2017-01-01 | 2017-07-31 |  | 2017-07-19 | 88% | 35% | 0% | Internal Issues | AMER | US TERRITORIES | United States of America | Juniper Strategic Delivery |  |  | UBER-EndUser | UBER-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 769368 | 0 | 769368 | 497026 | 89212 | 407814 | 216162 | 305374 | 191652 | 272342 | 463994 | 25% | 60% | 100848 | 35% | 292500 | 89212 | 203288 | 11636 | 100848 | 191652 | 0 | 0 | 0 | 0 | 204526 | 102263 | 204526 | -102263 | 150 | 150 | 132.5 | 17.5 | 0 | 0 | 0 | 55.5 | 0 | 0% | 59% | 0 | 0 | 77 | 55.5 | 0 | 0 | 0 |  | 132.5 | 1 | 26602 Uber 2017
26603 | 26603 - InComm ISG Key Recovery T&M | Gregory, Mina | Awarded | Booked | Green |  | 2017-07-24 | 2017-07-28 |  | 2017-07-10 | 100% | -7% | 0% |  | AMER | US TERRITORIES | Remote | Security |  |  | #NAME? | InComm-EndUser | PO | Monthly in Arrears |  |  | A | 4950 | 0 | 4950 | 2400 | 2785 | -385 | 0 | 2785 | -385 | 2550 | 2165 | 51% | 44% | 2785 | -7% | 2400 | 2785 | -385 | 0 | 2785 | -385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 2 | 0% | 0% | 0.4 | 0 | 2 | 0 | 0 | 0 | 0 |  | 2.4 | 1 | 26603 - InComm ISG Key Recovery T&M
26610 | 26610 - Goldman Sachs SRX5400 Testing CCL | Cicatello, James | Awarded | In Progress | Amber | 2017-05-16 | 2017-05-30 | 2017-08-01 |  | 2017-07-17 | 49% | -9% | 0% | Internal Issues | AMER | GLOBAL FINANCIAL SERVICES | United States of America | Juniper Strategic Delivery |  |  | DIMENSION DATA HOLDINGS LTD-Customer | GOLDMAN SACHS & CO.-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 16150 | 0 | 16150 | 10176 | 6985 | 3191 | 5340 | 12325 | -2149 | 5974 | 3825 | 33% | 24% | 12325 | -9% | 10176 | 6985 | 3191 | 5340 | 12325 | -2149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 12.5 | 6.2 | 6.3 | 0 | 10 | 10 | 2.7 | 7.3 | 400% | 400% | 1.3 | 0 | 3.5 | 2.7 | 0 | 0 | 0 |  | 7.5 | 1 | 26610 - Goldman Sachs SRX5400 Testing CCL
26658 | 26658 Sempra Add'l T&M Consulting Support | Wiesner, Jill | Awarded | On Hold | Green | 2017-05-12 | 2017-06-19 | 2017-09-29 | 2017-11-09 | 2017-06-23 | 0% | 3% | 0% | Under/Not Over budget | AMER | US TERRITORIES | United States of America | Core & Edge |  |  | IAS | SEMPRA ENERGY-EndUser | PO | Monthly in Arrears | Consulting – T & M |  | A | 29550 | 0 | 29550 | 16450 | 0 | 16450 | 15764 | 15764 | 686 | 13100 | 13786 | 44% | 47% | 12764 | 3% | 13450 | 0 | 13450 | 12764 | 12764 | 686 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 0 | 11 | -0.00125 | 0 | 0 | 0 | 0 | 0% | 0% | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.9 | 1 | 26658 Sempra Add'l T&M Consulting Support
26660 | 26660 Ooredoo Junos Space Platform + CSD Base Packaged Service Package | Bhinder, Muhammad Amir Rashid | Awarded | Booked | Green | 2017-07-07 | 2017-07-31 | 2017-10-31 |  | 2017-07-13 | 0% | -38% | 0% | Under/Not Over budget | EMEA | MEA | Oman | Network Automation |  |  | MINDWARE S.A.-Customer | OOREDOO QTEL-EndUser | PO | Upon Completion | Consulting – Packaged |  | A | 31255 | 0 | 31255 | 19503 | 0 | 19503 |  |  |  | 11752 |  | 38% | 0% |  | -38% | 15576 | 0 | 15576 |  |  |  | 3927 | 0 | 3927 | 0 | 0 | 0 | 0 | 0 | 21 | 21 | 0 | 21 | 0 | 3 | 3 | 0 | 3 | 17% | 17% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 26660 Ooredoo Junos Space Platform + CSD Base Packaged Service Package
26663 | 26663 VF GR SRX5800 I&C FFP 4 MS | Moreno, Carlos | Awarded | In Progress | Green | 2017-06-26 | 2017-06-26 | 2017-07-28 |  | 2017-07-12 | 55% | 5% | 0% |  | EMEA | UK-I | Greece | Security |  |  | VODAFONE | VODAFONE-EndUser | PO | Milestone Payments | Install Custom |  | A | 16039 | 0 | 16039 | 10176 | 5761 | 4415 | 3608 | 9369 | 807 | 5863 | 6670 | 37% | 42% | 7717 | 5% | 8524 | 4231 | 4293 | 3486 | 7717 | 807 | 0 | 0 | 0 | 0 | 1652 | 1530 | 122 | 0 | 9.6 | 9.6 | 5.3 | 4.4 | 0 | 5.1 | 5.1 | 1.8 | 3.3 | 112% | 112% | 0 | 0 | 3.5 | 1.8 | 0 | 0 | 0 |  | 5.3 | 1 | 26663 VF GR SRX5800 I&C FFP 4 MS
26672 | 26672 Telstra - Bain41_Operations_PS - T&M | Saini, Shagun | Awarded | In Progress | Green | 2017-06-07 | 2017-07-19 | 2018-07-18 |  | 2017-06-08 | 0% | 3% | 0% |  | APAC | ANZ | Australia | Core & Edge |  |  | TELSTRA CORPORATION-Customer | TELSTRA CORPORATION LTD.-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 250471 | 250471 | 0 | 208720 | 330 | 208390 | 202070 | 202400 | 6320 | 41751 | 48071 | 17% | 19% | 202400 | 3% | 208720 | 330 | 208390 | 202070 | 202400 | 6320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230 | 0.4 | 229.6 | -230 | 0 | 10 | 0.4 | 0 | 0% | 5% | 0 | 0 | 0 | 0.4 | 0 | 0 | 0 |  | 0.4 |  | 26672 Telstra - Bain41_Operations_PS - T&M
26677 | 26677 VHA - Third Link Provisioning JNA0032 - FFP | Wood, Russell | Awarded | In Progress | Green | 2017-06-12 | 2017-05-29 | 2017-08-07 |  | 2017-06-13 |  | 33% | 0% |  | APAC | ANZ | Australia | Core & Edge |  |  | VODAFONE HUTCHISON AUSTRALIA-EndUser | VODAFONE HUTCHINSON AUSTRALIA PTY LTD - EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | A | 81560 | 0 | 81560 | 51354 | 24519 | 26835 | 0 | 24519 | 26835 | 30206 | 57041 | 37% | 70% | 24519 | 33% | 51354 | 24519 | 26835 | 0 | 24519 | 26835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.8 | 0 | -23.8125 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 1.5 | 23.8 | 0 | 0 | 0 | 0 |  | 25.3 |  | 26677 VHA - Third Link Provisioning JNA0032 - FFP
26680 | 26680 FASTWEB IH MERGE 18 Credits Redemption | Masci, Fabio | Awarded | In Progress | Green |  | 2017-05-15 | 2017-07-31 |  | 2017-06-30 |  | 0% | 0% |  | EMEA | ENA-R-SOUTH | Italy | Core & Edge |  |  | Juniper | FASTWEB S.P.A.-EndUser | PO/Tokens | None | Consulting – Fixed Price Custom |  | A | 0 | 0 | 0 | 0 | 6574 | -6574 | 0 | 6574 | -6574 | 0 | -6574 | 0% | 0% | 6574 | 0% | 0 | 6574 | -6574 | 0 | 6574 | -6574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.2 | 0 | -5.1875 | 0 | 0 | 0.2 | 0 | 0% | 4% | 1.5 | 0.4 | 5 | 0.2 | 0 | 0 | 0 |  | 7.1 |  | 26680 FASTWEB IH MERGE 18 Credits Redemption
26681 | 26681 FASTWEB Service Chaining 11 Credits Redemption | Masci, Fabio | Awarded | In Progress | Green |  | 2017-05-15 | 2017-07-31 |  | 2017-06-30 | 74% | 0% | 0% |  | EMEA | ENA-R-SOUTH | Italy | Core & Edge |  |  | Juniper | FASTWEB S.P.A.-EndUser | PO/Tokens | None | Consulting – Fixed Price Custom |  | A | 0 | 0 | 0 | 0 | 11434 | -11434 | 0 | 11434 | -11434 | 0 | -11434 | 0% | 0% | 11434 | 0% | 0 | 11434 | -11434 | 0 | 11434 | -11434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.6 | 12.6 | 9.3 | 3.3 | 0 | 7.4 | 7.4 | 0.3 | 7.1 | 140% | 140% | 9.3 | 0.3 | 9 | 0.3 | 0 | 0 | 0 |  | 18.8 | 1 | 26681 FASTWEB Service Chaining 11 Credits Redemption
26683 | 26683 VF IT SecGW X48 Testing FFP 3 MS | Moreno, Carlos | Opportunity | In Progress - Working at Risk | Green |  | 2017-07-17 | 2017-08-31 |  | 2017-07-12 | 0% | -19% | 0% |  | EMEA | UK-I | Italy | Security |  |  | VODAFONE | VODAFONE ITALY-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 47821 | 0 | 47821 | 31015 | 0 | 31015 | 40310 | 40310 | -9295 | 16806 | 7511 | 35% | 16% | 34502 | -19% | 25207 | 0 | 25207 | 34502 | 34502 | -9295 | 5808 | 0 | 5808 | 0 | 0 | 0 | 0 | 0 | 27.4 | 27.4 | 0 | 27.4 | 0 | 16.5 | 16.5 | 0 | 16.5 | 152% | 152% | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.3 | 1 | 26683 VF IT SecGW X48 Testing FFP 3 MS
26710 | 26710 TEF Fusion Migration Barcelona FFP 4 MS | Gil, Jose | Awarded | In Progress | Green | 2017-04-25 | 2017-05-03 | 2017-12-15 |  |  | 1% | 37% | 0% |  | EMEA | Spain | Spain | Core & Edge |  |  | TELEFONICA DE ESPANA (FUSION)-EndUser | TELEFONICA SA-Customer | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 502970 | 0 | 502970 | 3500 | 116885 | -113385 | 179737 | 296623 | -293123 | 499470 | 206347 | 4% | 41% | 177174 | 37% | 0 | 937 | -937 | 176237 | 177174 | -177174 | 3500 | 0 | 3500 | 0 | 0 | 115948 | 0 | -115948 | 0 | 260 | 1.4 | 258.6 | -260 | 0 | 0 | 0.5 | 0 | 0% | 0% | 0 | 0 | 0.9 | 0.5 | 0 | 0 | 0 |  | 1.4 |  | 26710 TEF Fusion Migration Barcelona FFP 4 MS
26714 | 26714 - Abercrombie & Fitch Automated Workbench | Stroud, Charlie | Awarded | In Progress | Green | 2017-06-15 | 2017-06-19 | 2017-11-24 |  | 2017-06-28 | 5% | -702% | 0% |  | AMER | US TERRITORIES | United States of America | Network Automation |  |  | Abercrombie & Fitch - End User | Abercrombie & Fitch - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 72000 | 0 | 72000 | 62880 | 24860 | 38020 | 539885 | 564745 | -501865 | 9120 | -492745 | 18% | -684% | 556265 | -702% | 54400 | 24860 | 29540 | 531405 | 556265 | -501865 | 8480 | 0 | 8480 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 23.5 | 491.5 | -515.0087 | 0 | 107.5 | 2 | 0 | 0% | 26% | 0.6 | 0 | 21.5 | 2 | 0 | 0 | 0 |  | 24.1 |  | 26714 - Abercrombie & Fitch Automated Workbench
26718 | 26718 Telstra - EPIC Security Capabilities Review - FFP | Saini, Shagun | Awarded | In Progress | Green | 2017-05-25 | 2017-05-29 | 2017-07-28 |  | 2017-07-17 | 97% | -19% | 0% | Customer Issues | APAC | ANZ | Australia | Security |  |  | TELSTRA CORPORATION-Customer | TELSTRA CORPORATION LIMITED-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | B | 41760 | 0 | 41760 | 27860 | 35859 | -7999 | 0 | 35859 | -7999 | 13900 | 5901 | 33% | 14% | 35859 | -19% | 27860 | 35859 | -7999 | 0 | 35859 | -7999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.8 | 33.8 | 32.9 | 0.9 | 0 | 33.8 | 33.8 | 7.1 | 26.6 | 0% | 0% | 0 | 2 | 25.8 | 7.1 | 0 | 0 | 0 |  | 34.9 | 1 | 26718 Telstra - EPIC Security Capabilities Review - FFP
26729 | 26729 Telecom Italia KENA CGNAT PS Consultancy T&M 55 Days | Masci, Fabio | Awarded | In Progress | Green | 2017-06-27 | 2017-06-01 | 2017-09-30 |  | 2017-06-30 |  | -42% | 0% |  | EMEA | ENA-R-SOUTH | Italy | Network Automation |  |  | TELECOM ITALIA - ANDREUCCI-EndUser | TELECOM ITALIA S.P.A.-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 144485 | 0 | 144485 | 69200 | 0 | 69200 |  |  |  | 75285 |  | 42% | 0% |  | -42% | 69200 | 0 | 69200 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 26729 Telecom Italia KENA CGNAT PS Consultancy T&M 55 Days
26733 | 26733 - Corning AppID Development Free of Charge | Gregory, Mina | Awarded | In Progress | Green |  | 2017-05-22 | 2017-08-18 |  | 2017-07-12 | 22% | 0% | 0% |  | AMER | US TERRITORIES | United States of America | Security |  |  | Leidos | Corning USA | Free of Charge | None | Consulting – Fixed Price Custom |  | A | 0 | 0 | 0 | 14200 | 3133 | 11067 | 10071 | 13204 | 996 | -14200 | -13204 | 0% | 0% | 13204 | 0% | 14200 | 3133 | 11067 | 10071 | 13204 | 996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2.3 | 7.8 | -10.0087 | 0 | 10 | 0 | 0 | 0% | 0% | 0.1 | 0 | 2.3 | 0 | 0 | 0 | 0 |  | 2.4 |  | 26733 - Corning AppID Development Free of Charge
26735 | 26735 Orange (SITA) PS Trial UCPE Batch 2 PS SDN & SEC T&M 30 Days | Masci, Fabio | Awarded | Booked | Green | 2017-07-17 | [5 empty] | -26% | 0% |  | EMEA | France | France | SDN | Security |  | FT/ORANGE Customer | FT ORANGE-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 71875 | 0 | 71875 | 10000 | 0 | 10000 |  |  |  | 61875 |  | 26% | 0% |  | -26% | 0 | 0 | 0 |  |  |  | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 26735 Orange (SITA) PS Trial UCPE Batch 2 PS SDN & SEC T&M 30 Days
26785 | 26785 STC NCDI IPFLOW-AAA-PCRF Phase 1 FFP 6MS | Bin Sabbar, Abdullah | Opportunity | In Progress - Working at Risk | Green | [5 empty] | 0% | -3% | 0% |  | EMEA | MEA | Saudi Arabia | Security |  |  | ARABIAN INTERNET & COMMUNICATIONS SERVICES COMPANY - Customer | STC - End User | PO | Milestone Payments | Consulting – Fixed Price Custom |  | C | 305623 | 0 | 305623 | 204750 | 0 | 204750 | 223450 | 223450 | -18700 | 100873 | 82173 | 30% | 27% | 188030 | -3% | 169330 | 0 | 169330 | 188030 | 188030 | -18700 | 35420 | 0 | 35420 | 0 | 0 | 0 | 0 | 0 | 0 | 199.3 | 0 | 199.3 | -199.25 | 0 | 0 | 0 | 0 | 0% | 0% | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2.5 |  | 26909 STC NDCI Direct 2017 NW Security S-2017-022 ***LEVEL 1*** | 26785 STC NCDI IPFLOW-AAA-PCRF Phase 1 FFP 6MS
26858 | 26858 Cosmo ZTP Workbench | Jeffries, Stephanie | Awarded | In Progress | Green | 2017-05-19 | 2017-05-22 | 2018-08-01 |  | 2017-07-23 | 56% | -12% | 0% | Under/Not Over budget | AMER | US TERRITORIES | United States of America | Network Automation | Core & Edge |  | THE COSMOPOLITAN OF LAS VEGAS-EndUser | THE COSMOPOLITAN OF LAS VEGAS-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 135000 | 0 | 135000 | 79237 | 54275 | 24962 | 41071 | 95347 | -16110 | 55763 | 39653 | 41% | 29% | 87977 | -12% | 71867 | 52680 | 19187 | 35297 | 87977 | -16110 | 7370 | 1596 | 5774 | 0 | 0 | 0 | 0 | 0 | 82 | 82 | 45.9 | 36.1 | 0 | 42 | 42 | 3.5 | 38.5 | 105% | 105% | 1.1 | 1.3 | 41.6 | 3.5 | 0.8 | 0 | 0 |  | 48.2 | 1 | 26858 Cosmo ZTP Workbench
26875 | 26875 OSP G3 ACX Install Q2-2017 FFP xMS | Anchuela, Antonio | Awarded | Booked |  | 2017-05-10 | [5 empty] | -20% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer-EndUser | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  |  | 0 | 31114 | -31114 | 0 | 14878 | -14878 |  |  |  | 0 |  | 20% | 0% |  | -20% | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 14878 | 0 | -14878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 26875 OSP G3 ACX Install Q2-2017 FFP xMS
26891 | 26891 DVZ Dimension Data JSA T&M | Subramaniam, Ragunath | Awarded | Booked |  | 2017-06-30 | [5 empty] | -8% | 0% |  | EMEA | DACH | Germany | Security |  |  | DIMENSION DATA-EndUser | DVZ DATENVERARBEITUNGSZENTRUM M-V GMBH-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 61601 | 0 | 61601 | 55443 | 0 | 55443 |  |  |  | 6158 |  | 8% | 0% |  | -8% | 47043 | 0 | 47043 |  |  |  | 8400 | 0 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 26891 DVZ Dimension Data JSA T&M
26948 | 26948 OSP Simplicity Stream1 Sat Swap FFP XMS | Oliver, Juan | Awarded | Booked |  | 2017-05-30 | 2017-07-03 |  |  |  | 5% | -7% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer-EndUser | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 909591 | 0 | 909591 | 836606 | 3200 | 833406 | 825050 | 828250 | 8356 | 72985 | 81341 | 16% | 9% | 60768 | -7% | 69124 | 3200 | 65924 | 57568 | 60768 | 8356 | 69124 | 0 | 69124 | 0 | 698358 | 0 | 698358 | 0 | 109.2 | 109.2 | 5.8 | 103.5 | 0 | 109.2 | 109.2 | 5.8 | 103.5 | 0% | 0% | 0 | 0 | 0 | 5.8 | 0 | 0 | 0 |  | 5.8 | 1 | 26948 OSP Simplicity Stream1 Sat Swap FFP XMS
26950 | 26950 VF RO SecGW HW Expansion FFP 7 MS | Moreno, Carlos | Awarded | In Progress | Amber | 2017-06-22 | 2017-05-22 | 2017-07-31 |  | 2017-07-12 | 116% | -36% | -16% |  | EMEA | UK-I | Romania | Security |  |  | VODAFONE-EndUser | VODAFONE ROMANIA SA-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 42780 | 0 | 42780 | 26811 | 39269 | -12458 | 2860 | 42129 | -15318 | 15969 | 651 | 37% | 2% | 39269 | -36% | 23951 | 39269 | -15318 | 0 | 39269 | -15318 | 2860 | 0 | 2860 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 30 | 0 | -4.05 | 7.5 | 7.5 | 3 | 4.5 | 40% | 33% | 0 | 0 | 27 | 3 | 0 | 0 | 0 |  | 30 | 1 | 26950 VF RO SecGW HW Expansion FFP 7 MS
26952 | 26952 Infradata UK Nuqleus project T&M 2 DAYS (FOC) | Subramaniam, Ragunath | Awarded | Complete |  |  | 2017-05-25 | 2017-05-30 |  | 2017-06-19 | 45% | 0% | 0% |  | EMEA | UK-I | United Kingdom | SDN | Security |  | INFRADATA | INFRADATA-EndUser | Free of Charge | None | Consulting – T & M |  | A | 0 | 0 | 0 | 100 | 2480 | -2380 | 3157 | 5638 | -5538 | -100 | -5638 | 0% | 0% | 5538 | 0% | 0 | 2480 | -2480 | 3057 | 5538 | -5538 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 2.7 | 3.3 | 0 | 4 | 4 | 0.1 | 3.9 | 200% | 200% | 0 | 0 | 2.6 | 0.1 | 0 | 0 | 0 |  | 2.7 | 1 | 26952 Infradata UK Nuqleus project T&M 2 DAYS (FOC)
26960 | 26960 Ministere de la Justice T&M 4 Days | M, Rahimunnisa | Awarded | Booked |  | 2017-06-21 |  |  |  | 2017-07-10 |  | 57% | 0% |  | EMEA | France | France | Security |  |  | #NAME? | Ministere de la Justice-End User | PO | Fully in Advance | Consulting – T & M |  | A | 12350 | 0 | 12350 | 7470 | 53 | 7417 | 1400 | 1453 | 6017 | 4880 | 10897 | 31% | 88% | 53 | 57% | 6070 | 53 | 6017 | 0 | 53 | 6017 | 1400 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | -0.125 | 0 | 0 | 0.1 | 0 | 0% | 0% | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0 |  | 0.3 |  | 26960 Ministere de la Justice T&M 4 Days
26967 | 26967 Telecom Egypt SBR PS for VoWifi T&M 5 days FOC | Subramaniam, Ragunath | Awarded | Booked | [5 empty] | 2017-06-19 | 3% | 0% | 0% |  | EMEA | MEA | Egypt | Network Automation |  |  | Juniper | TELECOM EGYPT-EndUser | Free of Charge | None | Consulting – T & M |  | A | 0 | 0 | 0 | 1500 | 106 | 1394 | 4771 | 4877 | -3377 | -1500 | -4877 | 0% | 0% | 3377 | 0% | 0 | 106 | -106 | 3271 | 3377 | -3377 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0.2 | 4.8 | 0 | 0 | 0 | 0.2 | 0 | 0% | 3% | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 |  | 0.2 | 1 | 26967 Telecom Egypt SBR PS for VoWifi T&M 5 days FOC
26969 | 26969 Bharti - BRAS PS Consultant Support - T&M | Pathak, Nishant | Awarded | On Hold | Green | 2017-05-17 | 2017-06-01 | 2018-05-30 |  | 2017-06-07 | 0% | -33% | 0% |  | APAC | India | India | Core & Edge |  |  | IBM-Customer | BHARTI AIRTEL LTD-EndUser | PO | Upon Completion | Consulting – T & M |  | A | 45000 | 0 | 45000 | 30160 | 4555 | 25605 |  |  |  | 14840 |  | 33% | 0% |  | -33% | 30160 | 0 | 30160 |  |  |  | 0 | 0 | 0 | 0 | 0 | 4555 | 0 | -4555 | 46 | 46 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 26969 Bharti - BRAS PS Consultant Support - T&M
26986 | 26986 Bharti - BRAS Support 1st Year - FFP | Pathak, Nishant | Awarded | In Progress | Green | 2017-06-20 | 2017-07-01 | 2018-06-30 |  | 2017-07-20 | 0% | -21% | 0% |  | APAC | India | India | Core & Edge |  |  | IBM-Customer | BHARTI AIRTEL LTD-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 100000 | 100000 | 0 | 79190 | 150053 | -70863 |  |  |  | 20810 |  | 21% | 0% |  | -21% | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 79190 | 150053 | 0 | -70863 | 27.5 | 27.5 | 0 | 27.5 | 0 | 13.8 | 13.8 | 0 | 13.8 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 26986 Bharti - BRAS Support 1st Year - FFP
26992 | 26992 OSP Jazztel Interoperability VPN Services FFP 2 MS | Oliver, Juan | Awarded | Booked |  | 2017-07-14 | 2017-06-26 |  |  |  | 1% | -8% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer-EndUser | ORANGE SPAIN | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 9856 | 0 | 9856 | 9867 | 70 | 9797 | 5899 | 5968 | 3899 | -11 | 3888 | 47% | 39% | 5968 | -8% | 9867 | 70 | 9797 | 5899 | 5968 | 3899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7 | 10.7 | 0.1 | 10.6 | 0 | 1.8 | 1.8 | 0.1 | 1.7 | 20% | 20% | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 |  | 0.1 | 1 | 26992 OSP Jazztel Interoperability VPN Services FFP 2 MS
26993 | 26993 OSP LNS Support FFP 2 MS | Oliver, Juan | Awarded | Booked |  | 2017-05-26 | 2017-09-29 |  |  |  |  | 40% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer-EndUser | ORANGE SPAIN | PO | Fully in Advance | Consulting – Fixed Price Custom |  |  | 7800 | 0 | 7800 | 21819 | 139 | 21680 | 924 | 1063 | 20756 | -14019 | 6737 | 46% | 86% | 139 | 40% | 20895 | 139 | 20756 | 0 | 139 | 20756 | 924 | 0 | 924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | -0.25 | 0 | 0 | 0.3 | 0 | 0% | 0% | 0 | 0 | 0 | 0.3 | 0 | 0 | 0 |  | 0.3 |  | 26993 OSP LNS Support FFP 2 MS
27007 | 27007 Telefonica Colombia CGNAT | Almanza, Henry | Awarded | Booked | Green | 2017-06-30 | 2017-06-12 | 2017-12-22 | 2018-01-26 | 2017-07-21 |  | 58% | 0% | Under/Not Over budget | AMER | CALA | Colombia | Core & Edge |  |  | NEC CORPORATION-Customer | TELEFONICA COLOMBIA-EndUser | PO | Upon Completion | Consulting – Fixed Price Custom |  | B | 46374 | 0 | 46374 | 29289 | 0 | 29289 | 740 | 740 | 28549 | 17085 | 45634 | 40% | 98% | 0 | 58% | 28549 | 0 | 28549 | 0 | 0 | 28549 | 740 | 0 | 740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.4 |  | 27007 Telefonica Colombia CGNAT
27025 | 27025 SGIX - ACI Project - CSAT | Jacobs, Christo | Awarded | In Progress | Green |  | 2017-04-28 | 2017-08-04 |  | 2017-07-21 |  | 0% | 0% | Under/Not Over budget | APAC | ASEAN | Singapore | Cloud |  |  | DIMENSION DATA HOLDINGS LTD-Customer | SINGAPORE INTERNET EXCHANGE LTD - EndUser | CSAT | None | Consulting – T & M |  |  | 0 | 0 | 0 | 0 | 2002 | -2002 | 0 | 2002 | -2002 | 0 | -2002 | 0% | 0% | 2002 | 0% | 0 | 2002 | -2002 | 0 | 2002 | -2002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 0 | -2.25 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 2.3 | 0 | 0 | 0 | 0 |  | 2.3 |  | 27025 SGIX - ACI Project - CSAT
27033 | 27033 Inmarsat PS Support T&M Consulting 25 days (Onsite) | Subramaniam, Ragunath | Awarded | Booked |  | 2017-06-28 | [5 empty] | -37% | 0% |  | EMEA | UKI | United Kingdom | SDN |  |  | INMARSAT PRIVATE LIMITED COMPANY | INMARSAT PRIVATE LIMITED COMPANY | PO | Fully in Advance | Consulting – T & M |  | A | 56375 | 0 | 56375 | 42088 | 0 | 42088 |  |  |  | 14287 |  | 37% | 0% |  | -37% | 35588 | 0 | 35588 |  |  |  | 6500 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 27033 Inmarsat PS Support T&M Consulting 25 days (Onsite)
27048 | 27048 WIND MICA T&M 3 Days | Masci, Fabio | Awarded | Complete | Green | 2017-06-30 | 2017-05-18 | 2017-05-19 |  | 2017-06-30 | 92% | 61% | 0% |  | EMEA | ENA-R-SOUTH | Italy | Core & Edge |  |  | SIRTI - Customer | WIND ITALY-EndUser | PO | Upon Completion | Consulting – T & M |  |  | 9000 | 9000 | 0 | 1350 | 2211 | -861 | 1326 | 3537 | -2187 | 7650 | 5463 | 0% | 61% | 2187 | 61% | 0 | 2187 | -2187 | 0 | 2187 | -2187 | 1350 | 24 | 1326 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2.8 | 0.3 | 0 | 3 | 3 | 0 | 3 | 0% | 0% | 0.3 | 0 | 1.8 | 0 | 1 | 0 | 0 |  | 3 | 1 | 27048 WIND MICA T&M 3 Days
27056 | 27056 ORANGE-SITA Cloud CPE Field Trial FFP & 10D T&M | Masci, Fabio | Awarded | In Progress |  | 2017-06-16 | 2017-05-30 | 2017-06-30 |  | 2017-06-30 | 686% | 61% | -586% |  | EMEA | France | France | SDN | Security |  | Orange-Customer | ORANGE-EndUser | PO | Monthly in Advance | Consulting – T & M |  | A | 98913 | 98913 | 0 | 9570 | 20015 | -10445 | 0 | 20015 | -10445 | 89343 | 78898 | 18% | 80% | 16265 | 61% | 6070 | 16265 | -10195 | 0 | 16265 | -10195 | 3500 | 3750 | 0 | -250 | 0 | 0 | 0 | 0 | 5 | 5 | 34.3 | 0 | -29.3125 | 5 | 5 | 0.4 | 4.6 | 0% | 17% | 1.1 | 4 | 33.4 | 0.4 | 0 | 0 | 0.5 |  | 39.4 | 1 | 27056 ORANGE-SITA Cloud CPE Field Trial FFP & 10D T&M
27057 | 27057 VF IT Bologna GiLAN Card Infill FFP 7 MS | Moreno, Carlos | Awarded | In Progress | Green | 2017-06-21 | 2017-06-26 | 2017-09-28 |  | 2017-07-12 | 19% | 1% | 0% |  | EMEA | UK-I | Italy | Security |  |  | VODAFONE-EndUser | VODAFONE ITALY-EndUser | PO | Milestone Payments | Install Custom |  | A | 32810 | 0 | 32810 | 24977 | 18468 | 6509 | 6309 | 24777 | 200 | 7833 | 8033 | 24% | 24% | 1461 | 1% | 1661 | 278 | 1383 | 1183 | 1461 | 200 | 0 | 0 | 0 | 0 | 23316 | 18190 | 5126 | 0 | 2.6 | 2.6 | 0.5 | 2.1 | 0 | 2.6 | 2.6 | 0.5 | 2.1 | 0% | 0% | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 |  | 0.5 | 1 | 27057 VF IT Bologna GiLAN Card Infill FFP 7 MS
27074 | 27074 Interoute Control Plane Testing - PART 2 FFP 1MS | Foster, David | Awarded | In Progress |  | 2017-06-30 | 2017-07-05 | 2017-09-13 |  | 2017-05-04 | 0% | -42% | 0% | Under/Not Over budget | EMEA | UK-I | United Kingdom | Core & Edge |  |  | TELENT COMMUNICATIONS HOLDINGS LTD-Customer | INTEROUTE GENEVA MANAGED SERVICES-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 27740 | 0 | 27740 | 16053 | 0 | 16053 |  |  |  | 11687 |  | 42% | 0% |  | -42% | 16053 | 0 | 16053 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 0 | 18 | 0 | 3 | 3 | 0 | 3 | 20% | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 26149 Interoute Control Plane Testing FFP 2MS - Credits Redemption | 27074 Interoute Control Plane Testing - PART 2 FFP 1MS
27080 | 27080 Telstra - RDN Networks RR Migration - CSAT | Davis, Joseph | Awarded | In Progress | Green |  | 2017-06-26 | 2017-07-28 |  | 2017-07-07 | 65% | 0% | 0% | Under/Not Over budget | APAC | ANZ | Australia | Core & Edge |  |  | TELSTRA CORPORATION-Customer | TELSTRA CORPORATION LIMITED-EndUser | CSAT | None | Consulting – Fixed Price Custom |  | B | 0 | 0 | 0 | 0 | 2431 | -2431 | 1317 | 3748 | -3748 | 0 | -3748 | 0% | 0% | 3748 | 0% | 0 | 2431 | -2431 | 1317 | 3748 | -3748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.5 | 23.5 | 15.3 | 8.3 | 0 | 20.5 | 20.5 | 2.8 | 17.8 | 683% | 683% | 0 | 0 | 12.5 | 2.8 | 0 | 0 | 0 |  | 15.3 | 1 | 24440 Telstra - RDN Networks RR Migration - FFP | 27080 Telstra - RDN Networks RR Migration - CSAT
27087 | 27087 Inmarsat Contrail Service Chaining T&M 10 DAYS (FOC) | Subramaniam, Ragunath | Awarded | Booked | [6 empty] | 43% | 0% | 0% |  | EMEA | UKI | United Kingdom | SDN |  |  | Juniper | Inmarsat-EndUser | Free of Charge | None | Consulting – T & M |  | A | 0 | 0 | 0 | 1500 | 3773 | -2273 | 5744 | 9517 | -8017 | -1500 | -9517 | 0% | 0% | 8017 | 0% | 0 | 3773 | -3773 | 4244 | 8017 | -8017 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 4.3 | 5.7 | 0 | 10 | 10 | 1 | 9 | 0% | 0% | 0 | 0.9 | 3.3 | 1 | 0 | 0 | 0 |  | 5.3 | 1 | 27087 Inmarsat Contrail Service Chaining T&M 10 DAYS (FOC)
27090 | 27090 ORANGE ITE T&M 5 Days | Subramaniam, Ragunath | Awarded | Booked |  | 2017-06-23 | [5 empty] | 23% | 0% |  | EMEA | France | France | Cloud |  |  | Orange-Customer | ORANGE SA-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 11750 | 11750 | 0 | 8470 | 3384 | 5086 | 2400 | 5784 | 2686 | 3280 | 5966 | 28% | 51% | 3384 | 23% | 6070 | 3384 | 2686 | 0 | 3384 | 2686 | 2400 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7 | 0 | -3.6875 | 0 | 0 | 0.2 | 0 | 0% | 5% | 0 | 1 | 3.5 | 0.2 | 0 | 0 | 0 |  | 4.7 |  | 27090 ORANGE ITE T&M 5 Days
27095 | 27095 PSBA - Support - T&M | Jacobs, Christo | Awarded | In Progress | Green | 2017-06-07 | 2017-06-07 | 2017-07-25 |  | 2017-07-14 | 0% | -27% | 0% | Under/Not Over budget | APAC | ANZ | Australia | Core & Edge |  |  | COMMUNICATIONS DESIGN & MANAGEMENT PTY LTD-Customer | PUBLIC SAFETY BUSINESS AGENCY-EndUser | PO | Cash in Advance | Consulting – T & M |  | A | 17056 | 0 | 17056 | 12397 | 10098 | 2299 |  |  |  | 4659 |  | 27% | 0% |  | -27% | 12397 | 0 | 12397 |  |  |  | 0 | 0 | 0 | 0 | 0 | 10098 | 0 | -10098 | 13 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 27095 PSBA - Support - T&M
27096 | 27096 FPT Telecom - Contrail Cloud Jumpstart - FFP | Pathak, Nishant | Awarded | In Progress | Green | 2017-06-27 | 2017-08-01 | 2017-09-19 |  | 2017-06-28 | 0% | -25% | 0% |  | APAC | ASEAN | Vietnam | Cloud |  |  | SV TECHNOLOGIES JSC-Customer | FPT TELECOM - HO CHI MINH-EndUser | PO | Cash in Advance | Consulting – Fixed Price Custom |  | A | 18000 | 0 | 18000 | 13450 | 0 | 13450 |  |  |  | 4550 |  | 25% | 0% |  | -25% | 9900 | 0 | 9900 |  |  |  | 3550 | 0 | 3550 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 12 | 0 | 2 | 2 | 0 | 2 | 20% | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 27096 FPT Telecom - Contrail Cloud Jumpstart - FFP
27101 | 27101 VF IT OpenStack POC Lab Milano T&M 5 Days | M, Rahimunnisa | Awarded | On Hold | Green | 2017-06-02 | 2017-06-05 | 2017-07-31 |  | 2017-07-13 | 25% | 12% | 4% |  | EMEA | UK-I | Italy | Cloud |  |  | VODAFONE-EndUser | VODAFONE ITALY-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 8569 | 8569 | 0 | 8114 | 1242 | 6872 | 5826 | 7067 | 1047 | 455 | 1502 | 5% | 18% | 4757 | 12% | 5804 | 1242 | 4562 | 3516 | 4757 | 1047 | 2310 | 0 | 2310 | 0 | 0 | 0 | 0 | 0 | 6.3 | 6 | 1.5 | 4.5 | 0.25 | 5.3 | 5 | 0.4 | 4.9 | 525% | 500% | 0 | 0.1 | 1.1 | 0.4 | 0 | 0 | 0 |  | 1.6 | 1 | 27101 VF IT OpenStack POC Lab Milano T&M 5 Days
27142 | 27142 SKY DEUTSCHLAND EX & QFX PS Consultancy 5 days T&M | Subramaniam, Ragunath | Awarded | Booked |  | 2017-06-06 |  |  |  |  | 104% | 27% | -4% |  | EMEA | DACH | Germany | Security |  |  | DIMENSION DATA HOLDINGS LTD-Customer | Sky Deutschland-EndUser | PO | Fully in Advance | Consulting – T & M |  | A | 12250 | 12250 | 0 | 5803 | 5301 | 502 | 249 | 5550 | 253 | 6447 | 6700 | 28% | 55% | 4300 | 27% | 4553 | 4300 | 253 | 0 | 4300 | 253 | 1250 | 1001 | 249 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5.2 | 0 | -0.1875 | 5 | 5 | 0.7 | 4.3 | 0% | 2667% | 0 | 1 | 4.5 | 0.7 | 0 | 0 | 0 |  | 6.2 | 1 | 27142 SKY DEUTSCHLAND EX & QFX PS Consultancy 5 days T&M
27151 | 27151 ITD Solutions Partner DC Design Workshop FFP 1 MS | Masci, Fabio | Awarded | Booked | Green | 2017-06-27 | 2017-07-03 | 2017-07-07 |  | 2017-06-30 | 4% | -1141% | 0% |  | EMEA | ENA-R-SOUTH | Italy | Cloud |  |  | ITD SOLUTIONS S.P.A. | ITD SOLUTIONS S.P.A. | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 8200 | 0 | 8200 | 5222 | 5353 | -131 | 93415 | 98768 | -93546 | 2978 | -90568 | 36% | -1104% | 97028 | -1141% | 3482 | 4493 | -1011 | 92535 | 97028 | -93546 | 1740 | 860 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 81.9 | 3.6 | 78.3 | -81.875 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 1.5 | 0 | 0 | 3.6 | 0 | 0 |  | 5.1 |  | 27151 ITD Solutions Partner DC Design Workshop FFP 1 MS
27159 | 27159 Bharti - BRAS Support 2nd Year - FFP | Pathak, Nishant | Awarded | On Hold | Green | 2017-06-20 | 2018-08-01 | 2019-07-31 |  | 2017-06-21 |  | -21% | 0% |  | APAC | India | India | Core & Edge |  |  | IBM-Customer | BHARTI AIRTEL LTD-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 100000 | 0 | 100000 | 79190 | 150053 | -70863 |  |  |  | 20810 |  | 21% | 0% |  | -21% | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 79190 | 150053 | 0 | -70863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 26986 Bharti - BRAS Support 1st Year - FFP | 27159 Bharti - BRAS Support 2nd Year - FFP
27160 | 27160 Bharti - BRAS Support 3rd Year - FFP | Pathak, Nishant | Awarded | On Hold | Green | 2017-06-20 | 2019-08-01 | 2020-08-31 |  | 2017-06-21 |  | -21% | 0% |  | APAC | India | India | Core & Edge |  |  | IBM-Customer | BHARTI AIRTEL LTD-EndUser | PO | Fully in Advance | Consulting – Fixed Price Custom |  | A | 100000 | 0 | 100000 | 79190 | 150053 | -70863 |  |  |  | 20810 |  | 21% | 0% |  | -21% | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 79190 | 150053 | 0 | -70863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 26986 Bharti - BRAS Support 1st Year - FFP | 27160 Bharti - BRAS Support 3rd Year - FFP
27165 | 27165 Asia Investments - New DC - CSAT | Jacobs, Christo | Awarded | In Progress | Green |  | 2017-05-19 | 2017-08-11 |  | 2017-07-21 |  | 0% | 0% | Under/Not Over budget | APAC | ASEAN | Singapore | Cloud |  |  | IBM-Customer | ASIA INVESTMENTS PTE LTD - Enduser | CSAT | None | Consulting – T & M |  |  | 0 | 0 | 0 | 0 | 24916 | -24916 | 0 | 24916 | -24916 | 0 | -24916 | 0% | 0% | 24916 | 0% | 0 | 24916 | -24916 | 0 | 24916 | -24916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.6 | 0 | -46.625 | 0 | 0 | 4 | 0 | 0% | 9% | 0 | 0 | 42.6 | 4 | 0 | 0 | 0 |  | 46.6 |  | 27165 Asia Investments - New DC - CSAT
27172 | 27172 Telstra - REX-Extension-1Month-RE - T&M | Davis, Joseph | Awarded | In Progress | Green | 2017-06-19 | 2017-06-19 | 2017-07-31 |  | 2017-06-20 | 42% | -87% | 0% | Under/Not Over budget | APAC | ANZ | Australia | Core & Edge |  |  | TELSTRA CORPORATION-Customer | TELSTRA CORPORATION LTD-EndUser | PO | Upon Completion | Consulting – T & M |  | A | 21523 | 0 | 21523 | 17515 | 8264 | 9251 | 28052 | 36316 | -18802 | 4008 | -14793 | 19% | -69% | 19874 | -87% | 1072 | 8264 | -7192 | 11610 | 19874 | -18802 | 0 | 0 | 0 | 0 | 16443 | 0 | 16443 | 0 | 21.6 | 21.6 | 9 | 12.6 | 0 | 21.6 | 21.6 | 1.3 | 20.4 | 0% | 0% | 0 | 0 | 7.8 | 1.3 | 0 | 0 | 0 |  | 9 | 1 | 27172 Telstra - REX-Extension-1Month-RE - T&M
27173 | 27173 Telstra - REX-Extension-1Month-R1 - T&M | Davis, Joseph | Awarded | In Progress | Green | 2017-07-19 | 2017-08-01 | 2017-10-30 |  | 2017-07-20 |  | -27% | 0% |  | APAC | ANZ | Australia | Core & Edge |  |  | TELSTRA CORPORATION-Customer | TELSTRA CORPORATION LTD-EndUser | PO | Upon Completion | Consulting – T & M |  | B | 84720 | 0 | 84720 | 61504 | 55872 | 5632 |  |  |  | 23216 |  | 27% | 0% |  | -27% | 61504 | 0 | 61504 |  |  |  | 0 | 0 | 0 | 0 | 0 | 55872 | 0 | -55872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 27173 Telstra - REX-Extension-1Month-R1 - T&M
27192 | 27192 idealo - SRX3K issues T&M 3 days (FOC) | Subramaniam, Ragunath | Awarded | Booked | [6 empty] | 96% | 0% | 0% |  | EMEA | DACH | Germany | Security |  |  | Juniper | IDEALO | Free of Charge | None | Consulting – T & M |  | A | 0 | 0 | 0 | 100 | 1999 | -1899 | 187 | 2186 | -2086 | -100 | -2186 | 0% | 0% | 2086 | 0% | 0 | 1999 | -1999 | 87 | 2086 | -2086 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2.9 | 0.1 | -3 | 0 | 3 | 0.4 | 0 | 0% | 0% | 0 | 0 | 2.5 | 0.4 | 0 | 0 | 0 |  | 2.9 |  | 27192 idealo - SRX3K issues T&M 3 days (FOC)
27193 | 27193 Baader Bank - Upgrade PLan & execution T&M 10 days (FOC) | M, Rahimunnisa | Awarded | Booked | Green |  | 2017-09-09 | 2017-10-31 |  | 2017-07-13 |  | 0% | 0% |  | EMEA | DACH | Germany | Core & Edge |  |  | AXIANS | BAADER BANK-EndUser | Free of Charge | None | Consulting – T & M |  | A | 0 | 0 | 0 | 1000 | 185 | 815 | 1000 | 1185 | -185 | -1000 | -1185 | 0% | 0% | 185 | 0% | 0 | 185 | -185 | 0 | 185 | -185 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | -0.4375 | 0 | 0 | 0.4 | 0 | 0% | 0% | 0 | 0 | 0 | 0.4 | 0 | 0 | 0 |  | 0.4 |  | 27193 Baader Bank - Upgrade PLan & execution T&M 10 days (FOC)
27215 | 27215 Telstra - Senior Consultant - T&M | Saini, Shagun | Awarded | In Progress | Green | 2017-06-22 | 2017-07-17 | 2017-10-16 |  | 2017-06-23 | 1% | -17% | 0% | Under/Not Over budget | APAC | ANZ | Australia | Juniper Strategic Delivery |  |  | TELSTRA CORPORATION-Customer | TELSTRA CORPORATION LTD-EndUser | PO | Upon Completion | Consulting – T & M |  | A | 88362 | 0 | 88362 | 67536 | 53992 | 13544 | 28335 | 82327 | -14791 | 20826 | 6035 | 24% | 7% | 28888 | -17% | 67536 | 552 | 66984 | 28335 | 28888 | 38648 | 0 | 0 | 0 | 0 | 0 | 53439 | 0 | -53439 | 63 | 63 | 0.6 | 62.4 | 0 | 63 | 63 | 0.6 | 62.4 | 0% | 0% | 0.4 | 0 | 0 | 0.6 | 0 | 0 | 0 |  | 1 | 1 | 27215 Telstra - Senior Consultant - T&M
27218 | 27218 Singtel - Wi-Fi Dynamic Bandwidth Management - FFP | Ang, Soon Aun | Awarded | On Hold | Green | 2017-06-30 | 2017-07-10 | 2017-09-30 |  | 2017-07-21 | 2% | -55% | 0% | Under/Not Over budget | APAC | ASEAN | Singapore | Network Automation |  |  | NERA TELECOMMUNICATIONS LTD-Customer | SINGAPORE TELECOMMUNICATIONS LIMITED-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 40000 | 0 | 40000 | 32479 | 29506 | 2973 | 24945 | 54451 | -21972 | 7521 | -14451 | 19% | -36% | 24560 | -55% | 2588 | 722 | 1865 | 23837 | 24560 | -21972 | 0 | 0 | 0 | 0 | 29891 | 28783 | 1108 | 0 | 65.5 | 65.5 | 1.1 | 64.4 | 0 | 5.5 | 5.5 | 1.1 | 4.4 | 9% | 9% | 0.3 | 0 | 0 | 1.1 | 0 | 0 | 0 |  | 1.4 | 1 | 27218 Singtel - Wi-Fi Dynamic Bandwidth Management - FFP
27227 | 27227 - Goldman Sachs Junos Policy Extraction | Kouzionis, Nicholas | Awarded | In Progress | Green | 2017-06-27 | 2017-07-05 | 2017-09-01 | 2018-07-05 | 2017-07-13 | 12% | 5% | 0% |  | AMER | GLOBAL FINANCIAL SERVICES | United States of America | Security |  |  | DIMENSION DATA HOLDINGS LTD-Customer | GOLDMAN SACHS & CO.-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 59565 | 0 | 59565 | 40493 | 4406 | 36087 | 32898 | 37304 | 3189 | 19072 | 22261 | 32% | 37% | 37304 | 5% | 40493 | 4406 | 36087 | 32898 | 37304 | 3189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.2 | 4 | 30.2 | -34.2 | 0 | 14.2 | 0 | 0 | 0% | 71% | 0.8 | 0 | 4 | 0 | 0 | 0 | 0 |  | 4.8 |  | 27227 - Goldman Sachs Junos Policy Extraction
27232 | 27232 OSP TARGOBANK TM 4 Days | M, Rahimunnisa | Awarded | Booked |  | 2017-07-14 | [5 empty] | -55% | 0% |  | EMEA | France | Spain | Core & Edge |  |  | FT/ORANGE Customer-EndUser | ORANGE SPAIN | PO | Upon Completion | Consulting – T & M |  | A | 10400 | 0 | 10400 | 0 | 0 | 0 |  |  |  | 10400 |  | 55% | 0% |  | -55% | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 27232 OSP TARGOBANK TM 4 Days
27244 | 27244 Ericsson Contrail Cloud PS Support - Additinal days T&M Consulting 10 Days | M, Rahimunnisa | Awarded | Booked |  | 2017-06-30 |  |  |  | 2017-07-07 |  | 35% | 0% |  | EMEA | ENA-R-NORTH | Sweden | SDN |  |  | ERICSSON AB | ERICSSON AB | PO | Fully in Advance | Consulting – T & M |  | A | 28575 | 0 | 28575 | 16159 | 106 | 16053 | 3000 | 3106 | 13053 | 12416 | 25469 | 54% | 89% | 106 | 35% | 13159 | 106 | 13053 | 0 | 106 | 13053 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | -0.25 | 0 | 0 | 0.3 | 0 | 0% | 0% | 0 | 0 | 0 | 0.3 | 0 | 0 | 0 |  | 0.3 |  | 27244 Ericsson Contrail Cloud PS Support - Additinal days T&M Consulting 10 Days
27260 | 27260 Telefonica Colombia CG-NAT FoC | Almanza, Henry | Awarded | Complete | Green |  | 2017-06-19 | 2017-07-31 | 2017-09-22 | 2017-07-21 | 176% | 20% | 0% | Under/Not Over budget | AMER | CALA | Colombia | Core & Edge |  |  | NEC CORPORATION-Customer | TELEFONICA COLOMBIA-EndUser | Free of Charge | None | Consulting – Fixed Price Custom |  |  | 21878 | 0 | 21878 | 21877 | 14395 | 7482 | 3133 | 17528 | 4349 | 1 | 4349 | 0% | 20% | 13108 | 20% | 17457 | 13108 | 4349 | 0 | 13108 | 4349 | 4420 | 1287 | 3133 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 17.6 | 0 | -17.625 | 0 | 6 | 0 | 0 | 0% | 52% | 2.3 | 6.5 | 0 | 0 | 0 | 0 | 17.6 |  | 26.4 |  | 27260 Telefonica Colombia CG-NAT FoC
27278 | 27278 Roblox OnBoarding & PS Credits (10) - PO | Kouzionis, Nicholas | Awarded | In Progress | Green | 2017-06-21 | 2017-07-19 | 2018-06-19 | 2017-12-19 | 2017-07-17 | 0% | 0% | 0% | Under/Not Over budget | AMER | US TERRITORIES | United States of America | Core & Edge |  |  | FUSIONSTORM-Customer | Roblox-EndUser | PO | Milestone Payments | Consulting – Packaged | Consulting – Fixed Price Custom | A | 90900 | 19800 | 71100 | 27950 | 0 | 27950 |  |  |  | 62950 |  | 0% | 0% |  | 0% | 22250 | 0 | 22250 |  |  |  | 5700 | 0 | 5700 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 15 | 0 | 0 | 3.5 | 0 | 0 | 0% | 30% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 27278 Roblox OnBoarding & PS Credits (10) - PO
27279 | 27279 Ooredoo Qatar support migration international POPs T&M 5 days FOC | Bhinder, Muhammad Amir Rashid | Awarded | In Progress | Green |  | 2017-06-21 | 2017-08-30 | 2017-12-21 | 2017-07-06 |  | 0% | 0% | Under/Not Over budget | EMEA | MEA | Qatar | Core & Edge |  |  | Juniper | OOREDOO QTEL-EndUser | Free of Charge | None | Consulting – T & M |  | A | 0 | 0 | 0 | 0 | 1388 | -1388 | 0 | 1388 | -1388 | 0 | -1388 | 0% | 0% | 1388 | 0% | 0 | 1388 | -1388 | 0 | 1388 | -1388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 0 | -1.75 | 0 | 0 | 0 | 0 | 0% | 0% | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 1.4 |  | 2.1 |  | 27279 Ooredoo Qatar support migration international POPs T&M 5 days FOC
27286 | 27286 Telecom Italia JSD - NFVI and PE-M120 | Masci, Fabio | Awarded | Booked |  | 2017-06-19 | 2017-06-01 | 2017-08-31 |  | 2017-06-30 |  | 99% | 0% |  | EMEA | ENA-R-SOUTH | Italy | Juniper Strategic Delivery |  |  | #NAME? | TELECOM ITALIA S.P.A.-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | A | 73028 | 0 | 73028 | 0 | 673 | -673 | 0 | 673 | -673 | 73028 | 72355 | 0% | 99% | 673 | 99% | 0 | 673 | -673 | 0 | 673 | -673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | -2 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 2 |  | 27286 Telecom Italia JSD - NFVI and PE-M120
27289 | 27289 COX Communications Extended SDN Deployment | LaSalle, Glenn | Opportunity | In Progress - Working at Risk | Red |  | 2017-06-26 | 2017-12-29 | 2017-12-29 | 2017-07-07 | 1% | 3% | 0% | Under/Not Over budget | AMER | CABLES | United States of America | SDN |  |  | COX COMMUNICATIONS INC-EndUser | COX COMMUNICATIONS-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 520890 | 0 | 520890 | 348372 | 2547 | 345825 | 292112 | 294659 | 53713 | 172518 | 226231 | 40% | 43% | 253359 | 3% | 307072 | 2547 | 304525 | 250812 | 253359 | 53713 | 41300 | 0 | 41300 | 0 | 0 | 0 | 0 | 0 | 217.5 | 217.5 | 2.2 | 215.3 | 0 | 217.5 | 217.5 | 2.2 | 215.3 | 0% | 0% | 0 | 0 | 0 | 2.2 | 0 | 0 | 0 |  | 2.2 | 1 | 27289 COX Communications Extended SDN Deployment
27309 | 27309 TRUE - Junos Space PM Reporting - FFP | Ang, Soon Aun | Awarded | In Progress | Green | 2017-06-27 | 2017-07-17 | 2017-09-11 |  | 2017-07-21 | 5% | -13% | 0% | Under/Not Over budget | APAC | ASEAN | Thailand | Network Automation |  |  | PPLUS VISIONS CO.,LTD.-Customer | TRUE INTERNET CORPORATION COMPANY Limited-EndUser | PO | Milestone Payments | Consulting – Fixed Price Custom |  | B | 76794 | 0 | 76794 | 53353 | 31005 | 22348 | 31963 | 62969 | -9615 | 23441 | 13825 | 31% | 18% | 29549 | -13% | 49333 | 1605 | 47728 | 27943 | 29549 | 19785 | 4020 | 0 | 4020 | 0 | 0 | 29400 | 0 | -29400 | 46 | 46 | 2.5 | 43.5 | 0 | 7 | 7 | 2.5 | 4.5 | 18% | 18% | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 |  | 2.5 | 1 | 27309 TRUE - Junos Space PM Reporting - FFP
27327 | 27327 Orange vEPC T&M 5 Days | M, Rahimunnisa | Awarded | In Progress | Green | 2017-06-26 | 2017-07-07 | 2017-08-31 |  | 2017-07-03 |  | 48% | 0% |  | EMEA | France | France | SDN |  |  | #NAME? | ORANGE SA-EndUser | PO | Upon Completion | Consulting – T & M |  | A | 13750 | 0 | 13750 | 10338 | 1036 | 9302 | 2750 | 3786 | 6552 | 3412 | 9964 | 24% | 72% | 1036 | 48% | 7588 | 1036 | 6552 | 0 | 1036 | 6552 | 2750 | 0 | 2750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | -1.25 | 0 | 0 | 0.3 | 0 | 0% | 25% | 0 | 0 | 1 | 0.3 | 0 | 0 | 0 |  | 1.3 |  | 27327 Orange vEPC T&M 5 Days
27381 | 27381 BT GVA AWR 75 BT GVA Test Support T&M 3 DAYS | Foster, David | Awarded | Booked |  |  | 2017-07-07 | 2017-08-04 |  | 2017-07-07 |  | 3% | 0% |  | EMEA | UK-I | United Kingdom | Core & Edge |  |  | BRITISH TELECOM - Customer | BRITISH TELECOM-EndUser | None | Fully in Advance | Consulting – T & M |  | A | 6027 | 0 | 6027 | 6188 | 0 | 6188 |  |  |  | -161 |  | -3% | 0% |  | 3% | 5438 | 0 | 5438 |  |  |  | 750 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 27381 BT GVA AWR 75 BT GVA Test Support T&M 3 DAYS
27413 | 27413 ZEBRA A.G.R. TECHNOLOGIES Consulting days 2017Q2 T&M 13 Days | Subramaniam, Ragunath | Awarded | Booked |  | 2017-07-02 | 2017-09-04 |  |  |  | 0% | -49% | 0% |  | EMEA | ENA-R-CEE | Israel | Cloud |  |  | Zebra A>G>R Technologies LTD - Customer | ZEBRA TECHNOLOGIES LTD.-Customer | PO | Fully in Advance | Consulting – T & M |  | A | 38608 | 0 | 38608 | 19728 | 0 | 19728 |  |  |  | 18880 |  | 49% | 0% |  | -49% | 19728 | 0 | 19728 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 27413 ZEBRA A.G.R. TECHNOLOGIES Consulting days 2017Q2 T&M 13 Days
27447 | 27447 TEF Fusion GALICIA MAN5 I&C HL3-HL4 FFP xMS | Gil, Jose | Awarded | Booked |  | 2017-07-07 | [5 empty] | 30% | 0% |  | EMEA | Spain | Spain | Core & Edge |  |  | TELEFONICA - Customer | TELEFONICA DE ESPANA-EndUser | PO |  | Install Custom |  | A | 1370637 | 0 | 1370637 | 905000 | 1530 | 903470 | 905000 | 906530 | -1530 | 465637 | 464107 | 4% | 34% | 1530 | 30% | 0 | 1530 | -1530 | 0 | 1530 | -1530 | 5000 | 0 | 5000 | 0 | 900000 | 0 | 900000 | 0 | 0 | 0 | 2.8 | 0 | -2.75 | 0 | 0 | 2.8 | 0 | 0% | 0% | 0 | 0 | 0 | 2.8 | 0 | 0 | 0 |  | 2.8 |  | 27447 TEF Fusion GALICIA MAN5 I&C HL3-HL4 FFP xMS
27460 | 27460 Proximus TITAN POC T&M 10 days | M, Rahimunnisa | Awarded | Booked |  |  | 2017-07-10 | 2017-07-21 |  | 2017-07-10 |  | 0% | 0% |  | EMEA | ENA-R-NORTH | Belgium | Core & Edge |  |  | Telindus - CUSTOMER | Proximus-EndUser | Free of Charge | None | Consulting – T & M |  | A | 0 | 0 | 0 | 6000 | 53 | 5947 | 6000 | 6053 | -53 | -6000 | -6053 | 0% | 0% | 53 | 0% | 0 | 53 | -53 | 0 | 53 | -53 | 6000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | -0.125 | 0 | 0 | 0.1 | 0 | 0% | 0% | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 |  | 0.1 |  | 27460 Proximus TITAN POC T&M 10 days
27479 | 27479 BT AWR 76 JSD Support | Foster, David | Awarded | In Progress |  | 2017-07-21 | 2017-01-01 | 2017-12-31 |  | 2017-07-21 | 0% | 0% | 0% | Under/Not Over budget | EMEA | UK-I | United Kingdom | Juniper Strategic Delivery |  |  | BRITISH TELECOM - Customer | BRITISH TELECOM-EndUser | Reclass | None | Consulting – Fixed Price Custom |  | A | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0% | 0% |  | 0% | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196 | 196 | 0 | 196 | 0 | 6 | 6 | 0 | 6 | 3% | 3% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 27479 BT AWR 76 JSD Support
27487 | 27487 DT ANE RFQ POC T&M 15 days (FOC) | M, Rahimunnisa | Awarded | Booked |  |  | 2017-07-17 |  |  |  |  | 0% | 0% |  | EMEA | DACH | Germany | Core & Edge |  |  | DEUTSCHE TELEKOM-Customer | DEUTSCHE TELEKOM AG-EndUser | Free of Charge | None | Consulting – T & M |  | A | 0 | 0 | 0 | 6500 | 0 | 6500 |  |  |  | -6500 |  | 0% | 0% |  | 0% | 0 | 0 | 0 |  |  |  | 6500 | 0 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 27487 DT ANE RFQ POC T&M 15 days (FOC)
27539 | 27539 DCA Critical outage Support Engagement DWC T&M 5 daysFOC | Subramaniam, Ragunath | Opportunity | In Progress - Working at Risk | [7 empty] | 0% | 0% |  | EMEA | MEA | UAE | Cloud |  |  | Juniper | DCA-EndUser | Free of Charge | None | Consulting – T & M |  | A | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0% | 0% |  | 0% | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 27539 DCA Critical outage Support Engagement DWC T&M 5 daysFOC